## Introduction
Welcome to the The Productive Operating Theatre Programme Planner
What is it?
This spreadsheet is designed to be used in conjunction with the The Productive Operating Theate (TPOT) box set to help you to plan the tasks and activities required for successful implementation. |  |  |  | This symbol ( ) appears frequently throughout this tool. If you hold your cursor over it, additional information will appear.
Please note, this is NOT a comprehensive programme plan. This is intended to be a supporting resource to help you develop your own plan.
Who is it for?
The spreadsheet is intended as a tool for programme managers & implementation leads.
How do I use it?
The spreadsheet contains a series of linked pages which contain resources to aid your implementation. The three main pages are shown below:
| • This tab provides an overview of the key events and milestones in the programme. It highlights the aims for each module and, more importantly, the re-requisites for commencement |  | These tabs can be found at the top of each page. Click the tabs to quickly navigate between pages. In addition to these pages, you will find a number of additional resources, tools, templates and guides on the remaining tabs, many of which are editable for your convenience.
• The Programme Tasks tab provides an overview of the key actions required for each section of the programme together with helpful tips and links to useful tools and resources. It also contains references to the module guides.
• This sheet contains links to each of the other tabs and is a useful navigation point when looking for anything within this tool.
• This contains a sample timeline. You can either use this as a guide to planning your own programme timeline, or you can edit it to suit your own needs.
Every effort has been made to ensure that this resource is print friendly and adaptable to your needs. If you experience any difficulties using it, or have a suggestion to improve it please contact theatres@institute.nhs.uk to let us know.
Note on Q5: Like this!

## Programme Overview
Overview of key programme events and milestones
Event/Milestone | Aim | Pre-requisites | Key Outputs
Programme/Executive Lead preparation | • To ensure good understanding and commitment prior to commencing programme | • Business Plan or Project Initiation Document signed off | • Engaged and informed Executive and Programme leads
Programme team formation | • Recruitment of Programme team • Establish programme infrastructure | • Clear agreement to proceed from Executive Board | • Programme team established • Clear roles and responsibilites • First programme team meeting date set • Draft programme plan • Showcase theatres selected
Establish the steering group | • Steering group established and first meeting held | • Steering group engaged • Draft Programme plan and timescales • Key Resources identified | • Clear structure of steering group • Terms of reference • Agree plans and timescales • Agree resources • Agree funding • Set meeting dates • Provisional dates agreed for workshops
Visioning workshop | • To create a local shared vision for your operating theatre suite that will underpin the work of the programme | • Identification of date when MDT can attend • Engagement of skilled facilitator | • Clear shared vision created and understood by all • Engagement of the team • What are the barriers to the vision? • Identify champions to actively support the programme
Trust board workshop | • Engagement and ongoing support and commitment from the trust board | • Preparation of data and information required • Executive sponsor preparation | • Clear vision • Active support for programme • Commitment to resource • Commitment to participate in theatre visioning session • Commitment to visits / walkabouts
Knowing How We Are Doing and Measures workshop | • To understand current state and measure progress of improvements during the programme Identification of core measures for use during the programme | •Shared vision created and understood by all • Understanding of your information system and what it can deliver • Clarity of what you are already measuring • Actively seek support from the information department • Ongoing active support from information and IT departments | • Identified and agreed programme measures • How measures will be collected analysedand reviewed • Engagement of multidisciplinary team in Knowing How We Are Doing • Training for team in purpose of measures • Understanding how measurement drives behaviour and how to use facts / data to drive improvement • How to set up a visual Knowing How We Are Doing board and review system • Understanding of how you are doing in relation to the overall programme measures
Commencement of a Well Organised Theatre and Operational Status at a Glance | • To provide a solid foundation on which to base further improvement | • Knowing How We Are Doing established and its importance to the programme as a whole and each module understood by all | Well Organised Theatre • Improve workplace organisation • Understand of the 5S methodology • Design their areas to support their processes Operational Status at a Glance • Introduce visual management to theatres • Understand why real time measurement is important • Develop an Operational Status at a Glance system • Identify measures
Commencement of enabler modules - Team-working and scheduling | Team-working • Improved satefy by reducing errors and create a better working atmosphere for the theatre team Scheduling • Work with those involved in scheduling theatre lists to create a reliable and efficient scheduling process | • For foundation modules to be embedded | Team-working • Teams conducting brief, debrief and the checklist • Teams using tools such as SBAR and PACE Scheduling • improved scheduling process that produces reliable, achievable lists in a timely manner
Process modules | • Understand, improve and standardise six key processes, the combined results will have a high impact on achieving the programme aims | • All foundation modules and enablers to be embedded into daily practice | • Safe, reliable processes that have eliminated unnecessary delays and waste, improving the experience of both patients and staff

## Programme Tasks
Event | Task No. | Programme Task List | Links to useful tools (Click links to open) | Other Helpful Resources
Programme/Executive Lead's Preparation | 1. | Read the TPOT Programme Leaders guide and Executive Leaders guide | Programme Overview | Programme Leaders Guide Executive Leaders Guide
| 2. | Create your 'Elevator Pitch' for your programme
| 3. | Identify an appropriate Executive Lead (in not already in place)
| 4. | Ensure your Executive lead understands the programme | Download Leading Improvement ILG | Executive Leaders Guide
| 5. | Set up weekly meetings with your Executive Lead | Meetings - Toolkit (page 7)
| 6. | Define responsiblities with your Executive Lead | Roles & Responsibilites
Programme Team formation and preparation | 7. | Agree resource requirements for Programme Team with Executive Lead |  | Programme Leaders Guide (page 23) Executive Leaders Guide (page 25; 29-31)
| 8. | Recruit Improvement Facilitator |  | Programme Leaders Guide (page 26)
| 9. | Recruit Clinical Leads |  | Programme Leaders Guide (page 27)
| 10. | Recruit Information analyst |  | Programme Leaders Guide (page 28)
| 11. | Establish first date for programme team meeting | Meetings - Toolkit (page 7)
| 12. | Identify showcase theatres | Select a showcase theatre | Programme Leaders Guide (page 42-45)
Establish steering group | 13. | Establish steering group membership | Suggestions for involving others | Programme Leaders Guide (Pages 57-61) Executive Leaders Guide (Pages 33-35)
| 14. | Set date for first Steering group meeting | Meetings - Toolkit (page 7)
| 15. | Agree terms of reference |  | Executive Leaders Guide (Page 34)
| 16. | Agree resource requirements for the implementation
| 17. | Agree funding for implementation
| 18. | Agree frequency and dates of future meetings
| 19. | Set provisional dates for Visioning, Trust board and KHWD workshops |  | Programme Leaders Guide (Pages 62-77) Executive Leaders Guide (Pages 37-45) Knowing How We are Doing (Page 30)
Programme preparation | 20. | Discuss ISP with team and agree needs | TPOT support
| 21. | Project plan and timeline agreed | Programme Timeline | Monthly Module Action Planner
| 22. | Establish your communications strategy | Guide to Stakeholder Analysis [NHS Institute website] | Programme Leaders Guide (Pages 51-55)
| 23. | Link with other Productives
| 24. | Complete the Sustainability model | Sustainability tool [NHS Institute website] | NHS Institute Sustainability Model & Guide
Visioning workshop | 25. | Book venue & send invitations |  | Programme Leaders Guide (Pages 63 - 65)
| 26. | Run Visioning workshop |  | Programme Leaders Guide (Pages 67 - 74)
| 27. | Communicate Vision |  | Programme Leaders Guide (Pages 75 - 76)
Trust board workshop | 28. | Book time slot in Trust Board meeting |  | Executive Leaders Guide (Pages 39 & 42)
| 29. | Identify and collect information for presentation |  | Executive Leaders Guide (Pages 40 - 41)
| 30. | Arrange Leadership walkround | Guide to Leadership walkrounds [NHS Institute website]
| 31. | Run Trust Board Workshop |  | Executive Leaders Guide (Pages 43 - 45)
| 32. | Communicate outcomes
Knowing How We Are Doing | 33. | Plan module | Monthly Module Action Planner | Knowing How We Are Doing (Page 27)
| 34. | Book venue for measures workshop & send invitations |  | Knowing How We Are Doing (Pages 10 - 11; 29 - 35)
| 35. | Run measures workshop |  | Knowing How We Are Doing (Pages 36 - 39; 93 - 101)
| 36. | Confirm Collection & Display for each measure | Measures Checklist | Knowing How We Are Doing (Pages 41 - 59; 104 - 105)
| 37. | Collect baseline data and set ongoing measurement procedures |  | Knowing How We Are Doing (Pages 61 - 73; 83 - 87)
| 38. | Set up regular review meetings |  | Knowing How We Are Doing (Pages 75 - 81; 108)
Well Organised Theatre | 39. | Plan module & hold a mini-measures session | Monthly Module Action Planner | Well Organised Theatre (Pages 15 - 19)
| 40. | Plan the change | 5S Game (Toolkit - Pages 73 - 83) Photographs (Toolkit - Pages 61 - 65) Spaghetti Diagrams (Toolkit - Pages 125 - 127) | Well Organised Theatre (Pages 21 - 41)
| 41. | Do the change | 5S Inventory Sheet | Well Organised Theatre (Pages 43 - 61)
| 42. | Study the new layout |  | Well Organised Theatre (Pages 63 - 67)
| 43. | Act on the learning | Scale Up | Well Organised Theatre (Pages 69 - 85) Audit Planner (Toolkit - Pages 21 - 23)
| 44. | Repeat steps 39 - 42 | WOT Audit Tool
Operational Status At A Glance | 45. | Plan module & hold a mini-measures session | Monthly Module Action Planner | Operational Status At A Glance (Page 13 - 21)
| 46. | Plan the change | Activity Follow (Toolkit - Pages 31 - 45) Interviews (Toolkit - Pages 55 - 59) Photographs (Toolkit - Pages 61 - 65) | Operational Status At A Glance (Pages 23 - 39)
| 47. | Do the change |  | Operational Status At A Glance (Pages 41 - 49)
| 48. | Study the change |  | Operational Status At A Glance (Pages 51 - 57)
| 49. | Act on the learning | Scale Up | Operational Status At A Glance (Pages 59 - 61)
| 50. | Repeat steps 45 - 48
Team-Working | 51. | Organise the Team-Working session | Monthly Module Action Planner | Team-Working (Pages 21 - 23)
| 52. | Run the Team-Working session |  | Team-Working (Page 25)
| 53. | Plan implementation of brief/debrief & hold a mini-measures session | Measures Checklist | Team-Working (Pages 27 - 33)
| 54. | Plan the change: Select a team, raise awareness & identify champions |  | Team-Working (Pages 44 - 47)
| 55. | Plan the change: Choose an idea to implement |  | Team-Working (Pages 47 - 57)
| 56. | Do the change | Weekly Module Action Planner | Team-Working (Pages 58 - 61)
| 57. | Study the change |  | Team-Working (Pages 62 - 65)
| 58. | Act on the learning |  | Team-Working (Pages 66 - 69)
| 59. | Repeat steps 53 - 56
| 60. | Plan implementation of SBAR & hold a mini-measures session | Measures Checklist | Team-Working (Pages 27 - 33)
| 61. | Plan the change | Weekly Module Action Planner | Team-Working (Pages 104 - 111)
| 62. | Do the change |  | Team-Working (Pages 112 - 115)
| 63. | Study the change |  | Team-Working (Pages 116 - 119)
| 64. | Act on the learning | Scale Up | Team-Working (Pages 120 - 127)
| 65. | Repeat steps 61 - 64
Scheduling | 66. | Plan approach to Session utilisation & hold a mini-measures session | Monthly Module Action Planner | Scheduling (Pages 19 - 27)
| 67. | Plan the change: Select a team |  | Scheduling (Pages 34 - 36)
| 68. | Plan the change: Analyse Demand & Capacity | Demand & Capacity Guide [NHS Institute website] | Scheduling (Pages 37 - 39)
| 69. | Plan the change: Collect & Understand your data |  | Scheduling (Pages 41 - 42)
| 70. | Plan the change: Review ideas & select one | Weekly Module Action Planner | Scheduling (Pages 43 - 51)
| 71. | Do the change |  | Scheduling (Pages 52 - 57)
| 72. | Study the change |  | Scheduling (Pages 58 - 61)
| 73. | Act on the learning | Scale Up | Scheduling (Pages 62 - 67)
| 74. | Repeat steps 66 - 71
| 75. | Plan approach to List utilisation & hold a mini-measures session | Measures Checklist | Scheduling (Pages 19 - 27; 69 - 75)
| 76. | Plan the change: Select a team |  | Scheduling (Page 77)
| 77. | Plan the change: Collect & Understand your data |  | Scheduling (Pages 78 - 84)
| 78. | Plan the change: Review ideas & select one | Weekly Module Action Planner | Scheduling (Pages 84 - 91)
| 79. | Do the change: Process mapping | Process Mapping Overview [NHS Institute website] | Scheduling (Pages 92 - 95) Process mapping (Toolkit - pages 85 - 91)
| 80. | Do the change: Test the idea |  | Scheduling (Pages 97 - 103)
| 81. | Study the change |  | Scheduling (Pages 104 - 107)
| 82. | Act on the learning | Scale Up | Scheduling (Pages 108 - 115)
| 83. | Repeat steps 76 - 82
Process Modules | The order of implementing the process modules is down to you and will likely be guided by the outcomes of your visioning session. Each module will run in a similar fashion and should follow these steps
| 1. | Read module & plan the work to be done | Monthly Module Action Planner | Process module handbooks
| 2. | Run a mini-measures session | Measures Checklist | Process module handbooks
| 3. | Plan the change: Select a team |  | Process module handbooks
| 4. | Plan the change: Understand your current state | Weekly Module Action Planner | Process module handbooks
| 5. | Do the change |  | Process module handbooks
| 6. | Study the change |  | Process module handbooks
| 7. | Act on the learning | Scale Up | Process module handbooks
| 8. | Repeat the PDSA cycle for each new idea | Process Module PDSA cycle
Note on D4: Links to useful tools The links below provide access to a wealth of resources to help run your campaign. Just click on the links to access the resources. Some web-based tools require you to log in to the NHS Institute website. Registration on this site is free to all NHS England staff.
Note on C5: It is helpful to read through the rest of the toolkit if you are able, but the two leaders guides are a must at this stage
Note on C6: When asked "what is TPOT?", you need to have a short and articulate response. You will need to repeat this a great many times during the programme
Note on C7: If possible, consider who might be most interested in the programme, or who has an understanding of Theatres
Note on C8: Ensure that the Executive lead has read the Executive Leader's Guide so that they are aware of the required commitment to the programme and understand's their role
Note on C9: You will need to develop strong partnership working with your executive leader. As they will be required to support you through the tough times and to help overcome obstacles that are beyond your gift
Note on C10: You and your executive leader will become more and more responsible for the implementation of TPOT. To make things clear early on, share the table below with your executive leader and discuss the implications on how you should work together
Note on C11: The success and sustainability of this programme are dependent upon sufficient investment. This is a vital part of the programme and a key part of the Executive Lead's role
Note on C12: Improvement Facilitator should either be internal or external to Theatres, dependent on whether the Programme Lead is internal or external. It is best to have one of these two who is not from Theatres so as to provide a neutral viewpoint during the implementation
Note on C13: Ideally Clinical leads should be enthusiastic and strongly supportive of the programme. Two leads is ideal, one Surgical and one Anaesthetic so as to maximise clinical engagement
Note on C14: A key success factor for TPOT is good data, so find an analyst who is not only keen, but able to turn around data quickly and who is able to attend operational meetings when required
Note on C15: Getting the first date in the diary is always the hardest, ensure that ALL of the programme team are present for this meeting as it will set the tone for the rest of the programme. It is helpful for the Executive lead to attend this first meeting to set expectations and to meet the team
Note on C16: This should be done at the first team meeting. It is important that you select an area which is neither the 'best' or the 'worst' but one that has capability and enthusiasm for improvement
Note on C17: Ensure that the steering group contains senior members from each key area (this may change as you move between different modules, but the core group should remain the same)
Note on C18: As for the programme group, the first session is the most important in that it sets the tone for the remaining meetings. Try to ensure that the executive lead is vigorously encouraging others to attend
Note on C19: The steering group has distinct roles at different phases of the implementation, these need to be agreed
Note on C20: This includes people, time, equipment, office space, etc
Note on C21: Should be based on resource requirements
Note on C22: These should be arranged frequently enough to ensure direction can be maintained (every four to six weeks is recommended)
Note on C23: Try to arrange dates as soon as possible in order to ensure that diaries are available. It is usually advisable to several months ahead to get adequate space on a Trust Board agenda
Note on C24: Assess where you may need additional support during the implementation (human factors training, measurement for improvement, Trust board, etc...) and select the support you require. Ensure this has been costed and funded (if applicable)
Note on C25: You should by now be able to start preparing a project plan setting out key milestones and an estimated timeline. Start to think about what actions will be required for each module
Note on C26: You will need to engage your communications lead to assist you with developing this
Note on C27: Consider how you can link this programme with the other productives which are already running in your Trust. These all utilise the same methodology so there will be valuable learning and experiences you can tap in to
Note on C28: You need to build in sustainability to your programme from the start. Use the sustainability model to diagnose areas which might need development and to identify actions. This should be repeated at regular intervals to ensure sustainability for the programme
Note on C29: Invites to these events should be sent to all theatre staff, surgeons, anaesthetists, etc... at least 6 weeks prior to the event to ensure maximum attendance Personally addressed invites can elicit better results, especially if sent by the Exec lead
Note on C30: This is a great opportunity to identify champions for different modules. If someone feels very strongly about a particular issue then invite them to champion that module
Note on C31: Don't forget to include all those who were not present at the workshop. It is important for everyone to have an input
Note on C32: You should aim to book a slot at least two months in advance. The session should last for two hours, our experience suggests that shorter time slots will overrun
Note on C33: Complete the self assessment exercise to gather a comprehensive set of data for the workshop. This should be revied by the steering group
Note on C34: Most Executives have never been inside Theatres and are not aware of the issues you face so this is a valuable part of the preparation. The walkround should include both Executives and Non-Executives
Note on C35: It is important that the Theatre staff are involved in presenting to the Board. Ensure that cover has been arranged
Note on C36: Celebrate your success by raising awareness of the Board commitment to your staff
Note on C37: Read the module and complete the aims milestone checklist (Page 27). This will ensure that you have completed all the pre-work required for the measures workshop and planned all the actions required to complete successfully
Note on C38: Ensure that you have invited the appropriate mix of staff for the event and completed preparation work
Note on C39: Allow adequate time to run the workshop and ensure that the facilitator has a good grasp of measurement for improvement. It is vital that you ensure that the a balanced set of measures are chosen. Do not be tempted to choose only value & efficiency measures
Note on C40: You might want to set up Knowing How We Are Doing boards to display your data, ensure that you have obtained funds to purchase if required
Note on C41: Once the baseline data has been collected, you will need to continue to collect, analyse and present the data for as long as is needed to ensure an improvement has been achieved
Note on C42: Review meetings are the most important part of the KHWD process so ensure that these are not overlooked
Note on C43: Read the module, plan required actions and hold a mini-measures session. This will establish your aims for this module (linked to the Theatre vision) & the measures to be used
Note on C44: Choose an area to test the process, train the team on 5S, establish the baseline and plan the approach
Note on C45: Complete the Sort, Set & Shine steps in the chosen area
Note on C46: Determine whether the new layout is more effective, or whether it needs further improvements & report on KHWD boards
Note on C47: Continue to improve until the layout is confirmed then complete the Standardise & Sustain steps. Don't forget your measures!
Note on C48: You will need to repeat this process for each area. You may want to plan the areas to be organised using an audit tool which can be customised to your needs
Note on C49: Read the module, plan the required actions, clarify your aims and select a balanced set of measures
Note on C50: Gather information on current coordination process and select an initial change.
Note on C51: Create your OSAG boards and set up review meetings
Note on C52: Evaluate the effectiveness of the boards - report on KHWD boards
Note on C53: Implement/adapt new ideas to continually improve the boards
Note on C54: Continue to refine the process until it is fit for purpose
Note on C55: Read the module. It is vital that you have the right people leading this session and that you give at least 6 weeks notice to plan the session. Ensure that if you use an audit afternoon that all staff will be available to attend. You may need to cancel a list to do this so ensure your Exec is supporting this
Note on C56: You should allow at least half a day for this session. Our experience suggests that shorter sessions will usually overrun
Note on C57: Plan the required actions, clarify your aims and select a balanced set of measures for Brief/Debrief
Note on C58: It is usually best to start with an enthusiastic team, but you will still need to communicate regularly with them
Note on C59: Review ideas that have worked and select one to implement (or else come up with your own)
Note on C60: Train the team in brief/debrief use, implement and set up review meetings
Note on C61: Evaluate the effectiveness of the intervention & report on KHWD boards
Note on C62: Adopt, adapt or abandon as required to continually improve
Note on C63: Continue to refine briefing/debriefing until you are ready to try on a larger scale. Remember start small and build up gradually
Note on C64: Plan the required actions, clarify your aims and select a balanced set of measures for SBAR
Note on C65: Identify a team to pilot SBAR, raise awareness, identify champions, review ideas that have worked and select one to implement (or else come up with your own)
Note on C66: Train the team in SBAR use, implement and set up review meetings
Note on C67: Evaluate the effectiveness of the intervention & report on KHWD boards
Note on C68: Adopt, adapt or abandon as required to continually improve
Note on C69: Continue to refine SBAR until you are ready to try on a larger scale. Remember start small and build up gradually
Note on C70: Read the module, plan the required actions, clarify your aims and select a balanced set of measures for session utilisation
Note on C71: Scheduling is a process which crosses many organisational boundaries. In order to successfully tackle this you will need representation from all areas which are involved in the process
Note on C72: Before starting to make changes you will need to understand how you current demand matches your capacity
Note on C73: Collect your baseline data and utilise your analytical support to understand what it tells you about your service
Note on C74: Liaise with other sites & organisations to identify potential solutions that may work in your area, then choose one to pilot
Note on C75: Test the idea and set up regular review meetings to monitor progress
Note on C76: Evaluate the effectiveness of the intervention & report on KHWD boards
Note on C77: Adopt, adapt or abandon as required to continually improve
Note on C78: Continue to refine your ideas until you are ready to try on a larger scale. Remember, don't roll out an idea too quickly as it is easier to fix a small problem than a large one
Note on C79: Plan the required actions, clarify your aims and select a balanced set of measures for list utilisation. Remeber that you might want to link this with other process modules such as Patient Turnaround and/or Session Start-up
Note on C80: There are various groups involved in the different stages of creating a list and it is important they are all involved in this project
Note on C81: Collect your baseline data and utilise your analytical support to understand what it tells you about your service
Note on C82: Liaise with other sites & organisations to identify potential solutions that may work in your area, then choose one to pilot
Note on C83: Process map current and future states to ensure that you fully understand the whole process. It is vital that you include representatives from every area involved to do this effectively
Note on C84: Test the idea and set up regular review meetings to monitor progress
Note on C85: Evaluate the effectiveness of the intervention & report on KHWD boards
Note on C86: Adopt, adapt or abandon as required to continually improve
Note on C87: Continue to refine your ideas until you are ready to try on a larger scale. Remember, PDSA works best when done incrementally, don't rush ahead
Note on C90: The first step is to clarify your aims for the module. Use the visioning outputs to guide you
Note on C91: It is important that you choose new measures relevant to each module and that your KHWD boards are updated to show what is the current work being done
Note on C92: Each time select a new team that is relevant to the module - refer to the module handbooks for guidance on who should be included
Note on C93: Gather data, and map the current process to identify the opportunities for improvement
Note on C94: Implement the change on a small scale & monitor progress
Note on C95: Evaluate the effectiveness of the idea & report on KHWD boards
Note on C96: Adopt, Adapt or abandon the idea as required. Remember to celebrate successes and to ensure that they are continually monitored to ensure sustainability
Note on C97: As you get into the habit of testing new ideas on a small scale, measuring success and reviewing, you will begin to embed a culture of continuous improvement that will ensure that being Productive is the way you work

## Programme Timeline
Week
Event | Task No. | Programme Task List | Date Completed | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Programme & Executive Lead's Preparation | 1. | Read the TPOT Programme Leaders guide and Executive Leaders guide | bar: Week 1
| 2. | Create your 'Elevator Pitch' | bar: Week 1 to Week 2
| 3. | Identify an appropriate Executive Lead (in not already in place) | bar: Week 2
| 4. | Ensure your Executive lead understands the programme | bar: Week 2 to Week 3
| 5. | Set up weekly meetings with your Executive Lead | bar: Week 2
| 6. | Define responsiblities with your Executive Lead | bar: Week 2 to Week 3
Programme Team formation and preparation | 7. | Agree resource requirements with Executive Lead | bar: Week 3
| 8. | Recruit Improvement Facilitator | bar: Week 4 to Week 6
| 9. | Recruit Clinical Leads | bar: Week 4 to Week 6
| 10. | Recruit Information analyst | bar: Week 4 to Week 6
| 11. | Establish first date for programme team meeting | bar: Week 6
| 12. | Identify potential showcase theatres | bar: Week 7
Establish steering group | 13. | Establish steering group membership | bar: Week 5 to Week 7
| 14. | Set date for first Steering group meeting | bar: Week 7 to Week 8
| 15. | Agree terms of reference | bar: Week 9
| 16. | Agree resource requirements for the implementation | bar: Week 9
| 17. | Agree funding for implementation | bar: Week 9
| 18. | Agree frequency and dates of future meetings | bar: Week 9
| 19. | Set provisional dates for Visioning, Trust board and KHWD workshops | bar: Week 9 to Week 10
Programme preparation | 20. | Discuss ISP with team and agree needs | bar: Week 6
| 21. | Project plan and timeline agreed | bar: Week 6 to Week 9
| 22. | Establish your communications strategy | bar: Week 10 to Week 11
| 23. | Link with other Productives | bar: Week 7 to Week 13
| 24. | Sustainability | bar: Week 11 to Week 12; Week 27 to Week 28; Week 43 to Week 44
Visioning workshop | 25. | Book venue & send invitations | bar: Week 11
| 26. | Run Visioning workshop | bar: Week 17
| 27. | Communicate Vision | bar: Week 17 to Week 19
Trust board workshop | 28. | Book time slot in Trust Board meeting | bar: Week 11
| 29. | Identify and collect information for presentation | bar: Week 11 to Week 16
| 30. | Arrange Leadership walkround | bar: Week 17 to Week 19
| 31. | Run Trust Board Workshop | bar: Week 20
| 32. | Communicate outcomes | bar: Week 20 to Week 22
Knowing How We Are Doing | 33. | Plan module | bar: Week 14
| 34. | Book venue for measures workshop & send invitations | bar: Week 11
| 35. | Run measures workshop | bar: Week 21
| 36. | Confirm Collection & Display for each measure | bar: Week 21 to Week 22
| 37. | Collect baseline data and set ongoing measurement procedures | bar: Week 23 to Week 26
| 38. | Set up regular review meetings | bar: Week 22
Well Organised Theatre | 39. | Plan module & hold a mini-measures session | bar: Week 26 to Week 27
| 40. | Plan the change | bar: Week 28
| 41. | Do the change | bar: Week 28
| 42. | Study the new layout | bar: Week 29
| 43. | Act on the learning | bar: Week 29
| 44. | Repeat steps 39 - 42 | bar: Week 29 to Week 52
Operational Status At A Glance | 45. | Plan module & hold a mini-measures session | bar: Week 26 to Week 27
| 46. | Plan the change | bar: Week 28
| 47. | Do the change | bar: Week 28
| 48. | Study the change | bar: Week 29
| 49. | Act on the learning | bar: Week 29
| 50. | Repeat steps 45 - 48 | bar: Week 29 to Week 52
Team-Working | 51. | Organise the Team-Working session | bar: Week 14 to Week 28
| 52. | Run the Team-Working session | bar: Week 29
| 53. | Plan implementation of brief/debrief & hold a mini-measures session | bar: Week 30
| 54. | Plan the change: Select a team, raise awareness & identify champions | bar: Week 29 to Week 31
| 55. | Plan the change: Choose an idea to implement | bar: Week 31
| 56. | Do the change | bar: Week 32 to Week 35
| 57. | Study the change | bar: Week 36
| 58. | Act on the learning | bar: Week 36
| 59. | Repeat steps 53 - 56 | bar: Week 36 to Week 52
| 60. | Plan implementation of SBAR & hold a mini-measures session | bar: Week 29 to Week 31
| 61. | Plan the change | bar: Week 31
| 62. | Do the change | bar: Week 32 to Week 35
| 63. | Study the change | bar: Week 36
| 64. | Act on the learning | bar: Week 36
| 65. | Repeat steps 53 - 56 | bar: Week 36 to Week 52
Scheduling | 66. | Plan approach to Session utilisation & hold a mini-measures session | bar: Week 32 to Week 33
| 67. | Plan the change: Select a team | bar: Week 32
| 68. | Plan the change: Analyse Demand & Capacity | bar: Week 34 to Week 37
| 69. | Plan the change: Collect & Understand your data | bar: Week 34 to Week 37
| 70. | Plan the change: Review ideas & select one | bar: Week 36 to Week 38
| 71. | Do the change | bar: Week 39 to Week 42
| 72. | Study the change | bar: Week 43 to Week 44
| 73. | Act on the learning | bar: Week 44 to Week 47
| 74. | Repeat steps 66 - 71 | bar: Week 45 to Week 52
| 75. | Plan approach to List utilisation & hold a mini-measures session | bar: Week 32 to Week 33
| 76. | Plan the change: Select a team | bar: Week 32
| 77. | Plan the change: Collect & Understand your data | bar: Week 34 to Week 37
| 78. | Plan the change: Review ideas & select one | bar: Week 36 to Week 38
| 79. | Do the change: Process mapping | bar: Week 34 to Week 37
| 80. | Do the change: Test the idea | bar: Week 39 to Week 42
| 81. | Study the change | bar: Week 43 to Week 44
| 82. | Act on the learning | bar: Week 44 to Week 47
| 83. | Repeat steps 66 - 71 | bar: Week 45 to Week 52

## Roles & Responsibilities
Roles & Responsibilities
Executive Lead
Is responsible for: | Is not responsible for:
Being visible as the person responsible for TPOT within the organisation | Micro-managing teams
Chairing and leading the TPOT steering group | Leaving TPOT entirely to the Programme Lead
Briefing the Executive Team
Overseeing planning and progress
Securing necessary resources
Coaching Programme Lead
Establishing a robust governance structure
Ensuring prominance and strategic fit with organisational objectives
Programme Lead
Is responsible for: | Is not responsible for:
Programme Planning (Implementation, communications, strategy & resourcing) | Work outside the scope of the Programme
Training and Coaching | Micro-managing Theatres
Managing expectations
Arranging and leading key events
Leading Programme Team
Tracking Progress & Quality
Enabling Theatre Teams
Ensuring Executive Leader is up to date, escalating issues and challenges as required
Engaging the MDT
Lead the planning and measurement phase of each stage
Improvement Facilitator
Is responsible for: | Is not responsible for:
Spread the knowledge and use of improvement tools | Securing resources
Contributing to planning and measures | Managing the areas of change
Thinking creatively | Directing change without the knowledge of the Programme Leader
Help to develop a culture for continuous improvement
Motivating team
Supporting Champions in their work
Recording progress
Collecting and sharing data
Organising and doing
Clinical Lead (Both Surgical & Anaesthetic)
Is responsible for: | Is not responsible for:
Committing time to the Programme | Being an passive member of the team
Attending Steering Group and programme team meetings when required
Promoting the programme to other Clinicians
Supporting the implementation through their own practice e.g. Piloting briefings
Information Analyst | Is NOT:
Is responsible for: | Is not responsible for:
Identifying what information is already routinely collected | Being responsible for data collection
Work with the teams to develop measures
Identify how measures will be collected ongoing
Develop ways to analyse data and present findings
Educating the team about the use of information
Champion
Is responsible for: | Is not responsible for:
To be ambassadors of the programme | Being a passive member of the team
To show commitment
To promote the work
Engaging other staff
To show visibility in theatres
Help to implement the changes on the ground
Deal with challenging behaviour from peers
Develop skills in the use of improvement tools

## Involving others
NB. This is not an exhaustive list - consider how your organisation works when deciding on who to involve

## Select a showcase
Theatre number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Selecting a Theatre
Has a history of service improvement and innovation
There is a strong culture of multidisciplinary working
The team leader and multidisciplinary team want to be the showcase theatre
It is not going to have major changes in the next year, ie theatre move, renovation
The team leader is collaborative not autocratic in leadership style
The team leader and lead surgeon and anaesthetist once trained in The Productive Operating Theatre methods, are willing and able to coach and advise other theatres on implementation
Number of ticks (Select theatre with most ticks)

## TPOT Support
Support Opportunities available from the NHS Institute
KEY
Find out more
Find out more
Find out more
Find out more
Find out more
Usually delivered at Trust
Usually delivered off-site

## Monthly module action planner
Monthly module action planner
Theatre: |  | Module action plan for:
DATE
NO. | TASK | WHO | WHEN | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1
2
3
4
5
6
7
8
9
10
11
© Copyright NHS Institute for Innovation and Improvement 2009
DATE
NO. | TASK | WHO | WHEN | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
12
13
14
15
16
17
18
19
20
21
22
23
24
25
© Copyright NHS Institute for Innovation and Improvement 2009

## Weekly Module Action Planner
Weekly Module Action Planner
| Action | Who | When | Progress | Initials
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
= Understood
= Underway
= Complete
= Sustained

## 5S Inventory Sheet
5S Inventory Sheet
Inventory Sheet No:
Department: |  |  |  | Area:
Ref# | Item Description |  | Current |  |  |  | Proposed
|  |  | Location |  | Quantity | Cost | New Location | Quantity Required | Cost
Ref# | Item Description |  | Current |  |  |  | Proposed
|  |  | Location |  | Quantity | Cost | New Location | Quantity Required | Cost

## WOT Audit
5S Audit Tool | WOT Lead/Champion | Date planned | Date completed | Measured improvements | Owner
Theatres
Theatre 1
Anaesthetic room
Prep room
Sluice
Desk
Theatre 2
Anaesthetic room
Prep room
Sluice
Desk
Theatre 3
Anaesthetic room
Prep room
Sluice
Desk
Theatre 4
Anaesthetic room
Prep room
Sluice
Desk
Theatre 5
Anaesthetic room
Prep room
Sluice
Desk
Theatre 6
Anaesthetic room
Prep room
Sluice
Desk
Theatre 7
Anaesthetic room
Prep room
Sluice
Desk
Theatre 8
Anaesthetic room
Prep room
Sluice
Desk
Theatre 9
Anaesthetic room
Prep room
Sluice
Desk
Theatre 10
Anaesthetic room
Prep room
Sluice
Desk
Store rooms
Store room 1
Store room 2
Store room 3
Main Store Room
Ortho Tray Room
Ortho Pros Room
DSU
Male Side
Nursing Station
Female Side
Nursing Station
Sluice
Quiet Room
Bathrooms Female
Bathroom Male
Recovery
Paeds
Main
Blood gas station
Sluice
CD Trolley
Crash Trolley
HDU Trolley
Nursing Station

## Process modules PDSA
Each process module is structured to take you through the model for improvement. Within each module you will implement many small changes, developing and testing each one through smaller cycles of the model for improvement. The cumulative impact of these changes come together to achieve the objectives of the different process modules. For each module follow this process to achieve successful implementation.

## Scale up
Site name:
Module Theatre | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Key
Well organised Theatre | [21 empty] | Not yet started
Operating Status at a Glance | [20 empty] | 20% | Created teams & agreed aims
Team Working | [20 empty] | 40% | Identified measures
Scheduling | [20 empty] | 60% | Understand current state
Session Start Up | [20 empty] | 80% | Testing changes
Patient Preparation | [20 empty] | 99% | Measurable improvement
Patient Turnaround | [20 empty] | 100% | Achieved aims
Handover
Consumables & Equipment
Recovery
Site name:
Module Theatre | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Well organised Theatre
Operating Status at a Glance
Team Working
Scheduling
Session Start Up
Patient Preparation
Patient Turnaround
Handover
Consumables & Equipment
Recovery

## Measures Checklist
Measures Checklist
Every time you select a measure you should complete the measures checklist. The measures checklist provides a simple way to ensure that you consistently collect valid and reliable data for your improvement.
Try to ensure that you are collecting a balanced set of measures before making any changes.
PART 1: Measures Setup
Measure description | Measure name
Hold your cursor over any section to get more information
Why is it important? (Provides justification and any links to organisation strategy)
Who owns this measure? (Person responsible for making it happen)
Measure definition | What is the definition? (Spell it out very clearly in words)
What data items do you need?
What is the calculation?
Which groups are to be covered?
Goal setting | What is the numeric goal you are setting yourselves?
Who is responsible for setting this?
When will it be achieved by?
PART 2: Measurement process
Collect | Is the data available? (Currently available / Available with minor changes / Prospective collection needed)
Who is responsible for data collection?
What is the process of collection?
Analyse | Who is responsible for the analysis?
How often is the analysis completed?
What is the process for presenting results?
Review | Where will decisions be made based on results?
Who is responsible for reviewing?
Note on B7: A Balanced Set of Measures When collecting data for improvement it is useful to understand the three different types of measures that you might want to use (Outcome, Process & Balance measures). Make sure you have the right blend of measures so that you can track progress effectively: Outcome measures - Does it make a difference? An outcome measure, as the name suggests, measures outcomes (e.g. mortality rates, % prescription errors, patient experience, etc...). You should have several core outcome measures throughout the life of the programme to understand how you are progressing toward your programme aims. Process measures - Does the system work? A process measure indicates how well a new process is being adhered to (e.g. proportion of referrals being made according to criteria, % staff attending training, etc...). An important point to remember when choosing measures is that achieving improvement in process measures does not neccessarily result in an improvement in outcomes. So you cannot rely on process measures alone... Balance measures - Was there an unintentional consequence? Occasionally when you (as an implementation lead) suggest a change to a process, someone in the room will say 'Hang on, if you change that then XXXX will be affected'. Rather than ignoring that comment, or even disputing it, measure whether XXXX is affected as you make your changes. That is a balance measure. Balance measures are used to ensure that there are no unintended consequences to your improvements. When improving services, you will always need outcome measures, you will usually need process measures & you will occasionally need balance measures.
Note on C10: Measure Name The measure name should be brief and be linked to the process or outcome that it is measuring. It is generally this name to which a measure is referred to during conversation (as opposed to the lengthier definition - see below) E.g. Surgery Start Time
Note on C12: Why is it important? It is sometimes necessary to explain to people (especially those who are being asked to do the data collection) why the work is important. This box helps to link the measurement work to the programme aims (through the linkages defined in the driver diagram) and hence to the organisational strategy and objectives (to which the programme is aligned).
Note on C14: Who owns the measure? This box refers to the responsible person, i.e. The person who will be asking why? if the data is not collected and analysed. It is usually better to name a role than a person. E.g. Ward matron NB: This person is not neccesarily the same person who collects the data or performs the analysis.
Note on C16: What is the definition? A typical issue with measurement is that people often make the assumption that their understanding of a typical term is the same as everyone elses'. E.g. Surgery start time - sounds simple enough right? think again... When we asked theatre teams what their definition of start time was we generally got back 3-4 different definitions (knife to skin time, anaesthetic start time, when patient enters theatre, etc...). There is no right answer to the question, but as long as everyone agrees and understands the definition you will get reliable data. In order to collect reliable, valid data, it is important that whoever is collecting it understands exactly what it is that is being measured. A detailed definition in this box can prevent headaches. There is nothing worse than finding out 6 months after starting that you have been collecting different data all along because of a misunderstood definition! When writing the description be as specific as possible. Remember, not everyone is as expert as you! E.g. Surgery start time - could be defined as... 'The time that anaethesia preperation begins on first patient on the list'
Note on C18: What data items do you need? This defines all the different pieces of information you will need in order to calculate your specified measure. This is often obvious for simple measures, but defining the data items here can prevent confusion for more complicated measures. E.g. for the measure defined as 'proportion of patients operated on with completed time-out per day' You might need to collect: (depending on how information is coded) • Total number of patients operated on per day • Total number of patients operated on with completed time out per day
Note on C20: What is the calculation? Now that you have identified what data items to collect, how are they used to calculate the measure? E.g. for the measure defined as 'proportion of patients operated on with completed time-out per day' The calculation would be: Proportion of patients operated on with completed time-out per day = Total number of patients operated on with completed time out per day / Total number of patients operated on per day
Note on C22: Which groups are to be covered? This section defines the scope of the measure and the areas in which to collect the data. Are you looking at all patients? patients in one Theatre? Are you looking at the whole Trust? a single store room? etc... E.g. for the measure defined as 'proportion of patients operated on with completed time-out per day' The groups covered may be 'all patients who pass through Theatre 1 each day'
Note on C24: What is the numeric goal you are setting yourselves? If you have a particular goal in mind then this is the place to set it. If you don't have a goal initially, don't worry this isn't a neccessity. You might want to consider setting one at some point as goals can be helpful to get people to understand what 'good looks like'. NB: realistic, achievable goals can be motivating, unrealistic goals are almost always demotivating.
Note on C26: Who is responsible for setting this? If you do have a goal, who chooses what it is? Who is responsible for re-setting the target if the original is deemed unachievable? Depending on what you are measuring, you may want to consider letting the team decide their own target.
Note on C28: When will it be achived by? What is the target date for achieving your goal? Try not to set arbitrary dates, but consider how long you need to collect data for in order to show progress. I.e. If you are trying to reduce inpatient length of stay then you may want to collect data over at least a 6 month period before expecting to see any significant changes.
Note on C31: Is the data available? Can you collect the required data items at the required frequency from existing data sources? If so your task will be easier. If not however, you will need to consider how you could collect this data. Your IT/information support should be able to help with extracting data from IT systems. But you may need to consider creating a data capture form if the data has not been measured before. One note of caution before using IT systems. Do check that the data is valid before drawing conclusions from the data. E.g. Datix is a commonly used system to capture incidents and near misses, but is well known to be under used. The data you get from this system may not be an accurate reflection of non-serious incidents. Consider running a spot audit to check the validity of exisiting data sources if you are concerned that they might be unreliable.
Note on C33: Who is responsible for data collection? Who is actually going to be collecting the data? If there is an IT system, this might be one person. If you are using ward based data capture forms, is there a particular role who would be responsible for collecting the data? NB: It is VITAL that the person collecting the data understands the definition (consider taking them through this checklist before collection)
Note on C35: What is the process of collection? How is the data to be collected? Will someone need to submit a request to the information team? If so, when and what is the agreed timescale for returning the data? If using data capture sheets, where do they go when completed? How often are they sent? Are they to be collated in one place? Who is responsible for collating the data? How often should data be collated?
Note on C37: Who is responsible for the analysis? When it comes to analysing the data, who is going to be 'crunching the numbers'? If there is a requirement to understand analytical techniques? If so, who has the required skill set? Have you got an information specialist as part of the team? How much time do they have allocated for TPOT? How much are you expecting them to do? It might be better to ask them to do the more complicated work rather than just handing over everything to them. You might be waiting a long time for your results otherwise! Think if there a way of spreading the load amongst the wider workforce? For example, ifyou have productive wards, there may already be someone who is able to do this in each ward. This will make a big difference if you suddenly decide to roll out the programme and need to analyse huge amounts of data for a whole Trust.
Note on C39: How often is the analysis completed? Whilst you might measure something daily, you won't neccessarily want to analyse the data daily. Weekly or monthly might be more realistic. Consider how often you want to review the data. This can help to guide how often you will need to analyse it.
Note on C41: What is the process for presenting results? When using data, good use of visual charts can turn a complex data set into a simple illustration that tells the story behind the data. There are two types of chart that will cover most of your needs when presenting data: The bar/column chart & the line chart (or SPC chart). Bar/Column Chart Line/SPC chart [Shows relative importance/reasons] [Shows progress over time]
Note on C43: Where will decisions be made based on results? If you do not review your data and make decisions based on what it tells you then you have wasted your time (and everyone elses'). The basic rule of measurement - if you're not going to use it, don't measure it! Reviewing is the most important part of the measurement process. You should plan in advance when and where data will be reviewed (weekly/monthly).
Note on C45: Who is responsible for reviewing? Who will be involved in the review process? Who is going to be responsible for ensuring arising actions are completed?