## Action Plan
Independent Investigation Action Plan for Mr EF |  |  |  |  | STEIS Ref No: 2014/17418
Report date: July 2017 Report published: August 2017
Enfield CCG will seek assurance and monitor the action plan through the Clinical Quality Review Group (CORG). The CORG provides commissioner assurance by reviewing a range of evidence, provided by the Trust, to receive assurance that services are clinically safe, effective, promote patient experience and are responsive and well led in line with the requirements stipulated within the contracts held between the CCGs and the Trust, the NHS Constitution and Fundamental Standards of Care regulations. The meeting regularly receives reports on the Trusts compliance with the National Framework for Serious Incidents, application of the duty of Candour and identification and dissemination of learning from investigation findings. In this context the meeting will be able to monitor and receive assurance on the Trust’s implementation of specific SI investigations such as Domestic Homicide Reviews and Mental Health Homicide Reviews and the action plans that are part of these reviews.
Rec No. | Organisation | Recommendation | Actions to achieve recommendation | Implementation Lead | Implementation by when | Evidence of Completion | Monitoring & evaluation arrangements
1 | Barnet, Enfield and Haringey NHS Trust | Although we recognise that the capital implications and future plans for the site must be taken into account, we recommend that, in conjunction with its commissioners the Trust takes urgent steps to ensure that all admission wards are gender specific or, at a minimum, to create gender-specific bedroom and functional areas within mixed-sex wards. | 1. Plans for the new St.Ann’s will include only wards which are gender specific or have gender-specific bedroom and functional areas within mixed-sex wards. | Director of Strategic Improvement, (DOSI) | Plans completed March 2017 | DOSI confirms that the action around ensuring the new inpatient facilities at St Ann’s meet the latest guidance on single sex accommodation and privacy will be taken forward as part of the design process. The latest timescale for the new facilities to come into use by patients is December 2019 | BEH Serious Incident Review Group & Quality & Safety Committee.
|  |  | 2. In the interim, all our wards are compliant with this. All acute wards are single sex, and one older adult ward has gender specific bedroom and functional areas. | Clinical Directors to assure this in respect of all current wards | Completed and Ongoing
|  |  | 3. Bed management must check for risk/unsuitability for a patient for a particular admission environment, and escalate where concerns are identified. | Deputy Chief Operating Officer. | Completed and Ongoing
4. Reported/suspected breach is reported as an incident via DATIX and investigated
|  |  | 5. Incidents of breaches are reported on the Trust Performance & Quality Dashboard. |  |  |  | BEH Trust Serious Incident Review Group
6. Breaches are reported on performance report(balanced scorecard) at Joint Performance & Quality Review Group (commissioner and trust meeting).
2 | Barnet, Enfield and Haringey NHS Trust | The Trust ensures that equipment that is currently free-standing (bench, basketball hoop) in the garden area of the ward from which the patient went missing is fixed to the floor. The aim is to put barriers in place, recognising that a recreational area can be high risk | 1. The fence the patient climbed was raised promptly after the escape. All loose objects in recreational areas which could be used to assist climbing over fences/walls have subsequently been reviewed and secured | Director of Estates | Completed September 2014 | All loose objects used to assist climbing over fences/walls secured. Garden security checklist used on wards. Director of Estates has visited and inspected all ward garden areas | BEH Health & Safety Committee
|  |  | 2. Trust will conduct a yearly review of estate | Director of Estates | October 2017 | Minutes of H&S committee | BEH Health & Safety Committee
3 | Barnet, Enfield and Haringey NHS Trust | The Trust undertakes a detailed and comprehensive audit of the safety and security of the Sussex ward. | 1. Review to be commissioned by Chief Operating Officer | Chief Operating Officer | October 2017 | Minutes of H&S committee demonstrating actions | BEH Health & Safety Committee
|  |  | 2. Review to consider security of all acute wards, against accepted standards for adult acute wards | Chief Operating Officer | October 2017 | Minutes of H&S committee demonstrating actions | BEH Health & Safety Committee
4 | Barnet, Enfield and Haringey NHS Trust | The Trust should ensure that all service users with psychosis who misuse alcohol and/or illicit substances are considered for referral to substance misuse services. If the decision is to not make a referral, the rationale for the decision should be recorded. | 1. To be carried out as part of care plans for inpatients, as set out in physical health care policy. | Borough Clinical Directors (CDs) | December 2017 | Physical healthcare Policy - Medical Director's Quality report | BEH Trust Board
|  |  | 2. This forms part of CPA care plans for users subject to CPA in the community (CPA policy) | CD Enfield- leading on CPA review | December 2017 | CPA Policy - Deep Dive results on compliance with CPA policy | BEH Quarterly Governance Review meetings
5 | Barnet, Enfield and Haringey NHS Trust | Commissioners and the Trust consider working together to devise a more innovative, assertive outreach type of service for those service users who do not organise their lives by diaries and appointments and who move readily and frequently between organisational boundaries. Such services would be more flexible in going to service users where they are and remaining open to service users who move across team or service boundaries within the Trust. | 1. BEH Chief Operating Officer will table a discussion with the lead commissioner, Enfield CCG re flexible outreach services. | Chief Operating Officers, Enfield CCG and BEH | September 2017 | Minutes of Joint Contract meetings with commissioners | Contract Meetings, Enfield CCG and BEH
|  |  | 2. Current service development plans in the trust Adult Pathway Review are to develop locality based services for all service users. The aim of the plans is to minimise the boundaries between services and make it more likely that service users who lose contact with services can be followed up in primary care (by the new primary care linkworkers). | Chief Operating Officer & All Borough Clinical Directors | Barnet service implemented 01/04/17 Enfield, 09/17 Haringey 09/17 | Quality Impact Assessments on the plans | BEH Borough Clinical Quality Review Group
6 | Barnet, Enfield and Haringey NHS Trust | The Trust should follow the clinical risk assessment policy and deploy qualified staff to the CPA care coordinator role. If, in exceptional circumstances, a student is considered appropriate for the role, arrangements for role preparation (understanding of the role and appropriate training) should be made with the university programme head and include monitoring by appointed external examiners to the course. | 1. CPA Policy to include clear statement that no students of any discipline should take on Care Co-ordinator role. | Clinical Director Enfield to ensure this is stated in CPA policy | September 2017 | CPA policy Clinical Risk policy | BEH Trust Policy Review Group BEH Trust Serious Incident Review Group
|  |  | 2. Decision to be communicated to all appropriate educational leads | Medical Director to ensure distribution and awareness of updated policy once completed | September 2017 | Clinical Governance (Deep Dive & local governance meetings minutes Reports will go to Borough meetings and Quality & Safety Committee. | BEH Quality & Safety Committee
|  |  | 3. Supervision of care co-ordinators is essential for the safe management of high risk clients; CPA policy to state supervision arrangements | Medical Director to ensure distribution and awareness of updated policy once completed | September 2017 | Supervision policy and audit of records | BEH Quality & Safety Committee
7 | Barnet, Enfield and Haringey NHS Trust | The Trust moves towards the development of a more personalised approach to risk assessment, which is individual to each patient, assesses current risk factors and past history and includes a management plan that follows on from the risk assessment. In the meantime, we recommend that the current training on risk assessment and guidance on the use of the existing tool is strengthened. | 1. Review of Risk Assessment to be facilitated by Deputy t Director of Quality, (DDQ). DDQ will review national risk assessments and seek guidance from professional bodies on the complex area of best practice in use risk assessment/summary proformas. | Deputy Director of Quality | Review commnenced May 2017, development of new risk summary for RiO March 2018 | Trust wide SIRG minutes Risk Assessment audits | BEH Quality & Safety Committee
|  |  | 2. DDQ will liase with clinical leads on collating best practice and outcome of review nationally as all trusts use risk assessment and summeries differently. The current risk summary is not a predictive tool but does include a requirement that the service user is allocated to a level of risk of high, medium or low. This cannot be justified and should be removed and replaced with a box for an individualised narrative formulation. | DDQ Medical Director | Liaison completed May 2016 December 2017 | DDQ has completed liaising. Inquiries to a range of Trusts nationally suggest that there is no risk predicition tool in general use, and this is in line with the recommendation of NCISH that checklists should be avoided. Review of RiO risk summary template Minutes of Quality and Safety Committee | Not Applicable BEH Quality and Safety Committee
|  |  | 3. Risk Assessment Training currently provided by external providers - Procurement document for risk assessment training provider is to include requirement that advice on use of RiO documentation is provided Medical Director to discuss Trust Requirements with Procurement. | Assistant Director of Learning & Development Medical Director | October 2017 | Procurement documentation | BEH Trust Serious Incident Review Group
8 | Barnet, Enfield and Haringey NHS Trust | The Trust should revise the CPA policy in order to ensure that the status of care coordinators is consistent with the clinical risk assessment policy. | 1. CPA policy currently under review. | Medical Director | October 2017 | 1. Updated policy in place | BEH Trust Serious Incident Review Group and Borough Clinical Governance Meetings, (Deep Dives)
|  |  | 2. CPA policy review to link and be consistant with the Clinical Risk Assessement Policy | Clinical Director Enfield | September 2017 | 2. Audit of CPA policy 3. Audit of Clinical Risk Assessment Policy | BEH Trust Policy Review Group BEH Trust Serious Incident Review Group
9 | NHS England | In future instances of homicide by a service user in contact with mental health services, and where practicable, the Trust should offer professional support to meet any mental health needs arising from the incident and should signpost families to help with any other needs arising from the incident, such as financial costs. If the victim is unknown to the Trust, a senior manager should approach the police victim liaison officer to offer assistance to victim’s relatives and put them in touch with the Trust if support is requested. | 1. NHS England(London) will develop, facilitate and support implementation of guidance for Mental health provider organisations on supporting families of victims of homicides. This guidance will include details of support avaialble for families. | Director of Nursing(NWL) and Lead for Patient Safety | November 2017 | Guidance for Mental health providers on supporting families of victims of homicide | Independent Investigation Review Group, NHS England
| Barnet, Enfield and Haringey NHS Trust |  | 2. Trust will work with the third sector organsiations and Family Liaison officers to ensure that support for families can be identified and delivered in a timely way | MD to lead discussions with third sector and Family Liaison Officers on developing robust support and information processes | December 2017 | Joint Working Protocols | BEH Quality & Safety Committee