## Action Plan
Independent Investigation Action Plan for Mr L | [5 empty] | STEIS Ref No: 2013/17516
Report date: August 2017 Report published: August 2017
East London NHS Foundation Trust Statement: The independent investigators made five recommendations. Four relate to care. The fifth concerns management of records when a serious incident occurs and the support given to individuals involved in an investigation. All actions associated with these five recommendations will be monitored by the committees appropriately identified in the action plan. Overall evidence of completion will be monitored by the Associate Director of Governance & Risk Management. The investigation report will be tabled at the Quality Committee, Quality Assurance Committee (Board sub committee) and at the Clinical Quality Review Meeting (CQRM). CCG Statement Newham CCG would like to extend our deepest sympathies to all affected by this tragic case. This case relates to the Domestic Homicide Review (AB) undertaken on behalf of Newham Community Safety Partnership, the report of which can be found at: https://www.newham.gov.uk/Pages/ServiceChild/Domestic-homicide-reviews.aspx Newham CCG works with East London Foundation Trust to seek assurance that services they provide are: safe; effective; caring; responsive; and well led. Newham CCG will monitor the implementation of the action plan through a number of monitoring processes these include (but are not limited to): The Clinical Quality Review Meeting (CQRM) - The CQRM provides commissioners with assurance by reviewing a range of evidence, provided by the Trust, to ensure they are providing services in line with the requirements stipulated within the contract held between the CCG and the Trust, the NHS Constitution, and Fundamental Standards of Care regulations. In this context, the meeting monitors and receives assurance on the Trust’s implementation of specific actions resulting from Serious Incident investigations, Domestic Homicide Reviews, and Mental Health Homicide Reviews such as this case. Quality Assurance visits - Newham CCG carry out quality assurance visits to a range of services providing care. Through these visits the CCG will look for assurance that actions from this investigation have been implemented and are embedded into practice. Review of Serious Incidents - The CCG is responsible for reviewing all Serious Incidents reported by the Trust relating to services delivered within Newham. The CCG will ensure that any trends or themes arising are effectively addressed, and any additional assurance required will be requested from the Trust.
Rec No. | Priority | Organisation | Recommendation | Actions to achieve recommendation | Implementation Lead | Implementation by when | Evidence of Completion | Monitoring & evaluation arrangements
1 | 1 | East London NHS Foundation Trust | The Trust must provide assurance that carer’s assessments and support are offered and documented in line with the Trust strategy and that there is a system for care co-ordinators to initiate monthly contact with carers of clients who are on Care Programme Approach. | At the time of the incident social care was provided by the Trust under a Section 75 agreement with the local authority but responsibility for social care has now been transferred back to the local authority. The Trust therefore does not undertake carer’s assessments as these are the responsibility of the local authority. The Trust will ensure there is a system for ensuring monthly contact for carers of patients who are on CPA The Trust will ensure drop in sessions are available at the Recovery teams There will be monthly Carers' group meetings in the inpatient unit Care coordinators will have monthly contacts with carers in accordance with agreed key performance indicators The Borough Director Newham to discuss with Interim Head at London Borough of Newham (LBN) at a Joint Implementation Board Meeting on 03.08.2017. | Borough Director, Newham | 31.08.2017 | Provision of: Carers' strategy Information leaflet advertising monthly Carers Group in the hospital Performance report showing monthly contacts Directorate Learning Lessons Bulletin Learning events material Copy of minutes from Joint Implementation Board Meeting(s). | The Newham Directorate Management Team meets monthly and reviews the Performance Report which includes data on compliance with monthly contacts Healthcare Governance meeting (monthly) also reviews performance and is attended by all managers. Any reduction in compliance and reasons for this is picked up at this meeting and a remedial plan is put in place. Quarterly Performance Meeting monitors all Key Performance Indicators and is held with Senior Trust Executive members. A Clinical Governance bulletin is issued monthly which highlights performance issues and feedback from carers and service users. This is circulated to all directorate staff. In addition, Learning Lessons seminars are held quarterly and are themed depending on information from Incidents and Complaints. Carers have been the focus of these seminars Interface issues and concerns will be monitored and addressed through the regular Joint Implementation Board meetings.
2 | 3 | East London NHS Foundation Trust | The Trust must ensure that staff take responsibility for issuing formal invitations to all those they believe should be present at a Care Programme Approach meeting, or document discussions where this intention is changed. | The Trust will ensure that care coordinators are responsible for drawing up an invitation list to CPA meetings and that all relevant people are invited including family members (subject to consent). The invite list will be reviewed by care coordinators at each CPA meeting to ensure they reflect the people currently supporting the patient | Borough Director, Newham | 31.10.2017 | Provision of: CPA policy where care coordinator responsibilities are clearly defined. This includes discussion with service users prior to CPA meetings about who should attend Directorate Learning Lessons Bulletin Learning event material | Arrangements for CPA meetings including attendance, timeliness and effectiveness are discussed in supervision The CPA policy states that service users must be involved and consulted about who they wish to attend. The CPA policy is audited regularly and this audit reviews quality as well as adherence to policy. The operational Managers have access to policy minutes, attendance sheets etc and will raise issues and questions with care coordinators in supervision. Operational Team Leads hold a 'drop in' session for any service user or carer who wishes to speak with them.
3 | 1 | East London NHS Foundation Trust | The Trust must ensure that appropriate support is given to clients wishing to apply for self-directed support funding, who are known to have gambling habits. | Applications for Self-directed funding are no longer undertaken by trust staff as the local authority now operates a separate system. Trust staff would always provide relevant information to the local authority in relation to any applications, including any risks associated with the use of self-directed funds providing the service user gives consent The Borough Director Newham to discuss with Interim Head at LBN at a Joint Implementation Board Meeting on 03.08.2017. | Borough Director, Newham | 31.08.2017 | Copy of agenda and minutes of the Joint Implementation Board meeting(s). | The Borough Director has contacted the Interim Manager of the Adult Mental Health service in the London Borough of Newham to confirm that ELFT staff will share appropriate information about service users wishing to apply for Self Directed Support where they have permission from the service user to do so. In addition, ELFT will support service users to make an application for SDS, again, if appropriate. Interface issues and concerns will be monitored and addressed through the regular Joint Implementation Board meetings.
4 | 1 | East London NHS Foundation Trust | The Trust must assure itself that risk assessments and risk management plans are reviewed when new information comes to light. The Trust must also implement an ongoing audit programme to provide assurance about organisational compliance with this requirement | The risk assessment will be reviewed and updated at every CPA meeting and more frequently if required. This will be audited via a quarterly CPA and risk assessment audit | Borough Director, Newham | 31.10.2017 | Provision of: CPA policy Quarterly CPA & risk assessment audit | The Quality Assurance team coordinate a quarterly audit which reviews completion and quality of the risk assessment including current information and the audit results are monitored via the performance monitoring in the directorate. In addition, the audit results are discussed in the Trust Quality Assurance meeting and are noted in the Directorate Management Team which meets monthly. These are also seen by the CCG and any concerns about performance are addressed via these meetings. A Clinical Governance bulletin is issued monthly which highlights performance issues and feedback from carers and service users. This is circulated to all directorate staff. In addition, Learning Lessons seminars are held quarterly and are themed depending on information from Incidents and Complaints.
5 | 2 | East London NHS Foundation Trust | The Trust must revise the Incident Policy or develop additional guidance, and provide appropriate training to ensure staff are clear about *the type of records to be created and stored when conducting an investigation *storage and retrieval of clinical records & reporting of misplaced clinical records required for internal & external investigations The policy must also include clear guidance about ensuring that staff who have been involved in serious incidents are given access to the investigation report & their welfare & support needs are checked after the process has been completed. The Trust should also ensure that where possible staff being interviewed should have access to clients' records prior to being interviewed | The Incident policy will be revised to include guidance on the creation, storage and retention of records when conducting an investigation. The incident policy will include direction on raising an incident when records cannot be located. The incident policy will contain guidance on ensuring staff involved in an incident investigation are given support during and after the investigation including provision of clients' records. The corporate incident team will receive specific training on the management of records relating to an investigation The corporate incident team will be given written guidance on supporting staff involved in an investigation. | Associate Director of Governance & Risk Management | 31.12.2017 | Provision of: Updated Incident policy Corporate investigation team training records Audit demonstrating that documentation relating to incident investigations (including clinical records) has been correctly stored Staff feedback forms on support given during & after an investigation | The policy will be approved at the Quality Committee. Its effectiveness will be monitored through the regular update report to the Quality Committee. Individual investigator training records will be addressed during supervision Evidence that the required changes have been acted upon will be included in the quarterly incident report for Quality Committee. This is subsequently shared with the CCG via the Clinical Quality Review Monitoring meeting.
Priority One: The recommendation is considered fundamental in that it addresses issues that are essential to achieve key systems or process objectives and without which, the delivery of safe and effective clinical care would, in our view, be compromised.
Priority Two: The recommendation is considered important in that it addresses issues that affect the ability to fully achieve all systems or process objectives. The area of concern does not compromise the safety of patients, but identifies important improvement in the delivery of care required.
Priority Three: The recommendation addresses areas that are not considered important to the achievement of systems or process objectives. The area of concern relates to minor improvements in relation to the quality of service provision.