## Sheet1
Independent Investigation Action Plan for Mr R |  |  | STEIS Ref No: 2012/32877
South West London and St Georges Mental Health NHS Trust Statement We offer our full condolences to the family. The Trust are addressing the recommendations made in the independent investigation by ensuring actions are implemented to improve practice and to embed the lessons learned. The actions will be reviewed by lead clinicians in the Quality Sub-Committee and directly monitored by the Trust Board of Directors. We hope this offers some assurance that lessons have been learnt from this very tragic incident.
Wandsworth CCG Statement Wandsworth CCG has worked with and continues to monitor South West London and St Georges Mental Health NHS Trust to make sure the services they provide are safe; effective; caring and responsive. We continue to monitor the actions and learning from the original implementation plan through a monthly quality assurance meeting. At this meeting we review the evidence provided by the Trust to ensure the services they provide meet the requirements stipulated within the contract held between the CCG and the Trust, the NHS Constitution, and Fundamental Standards of Care regulations.
Rec No. | Recommendation | Actions to achieve recommendation | Implementation Lead | Implementation by when | Evidence of Completion | Monitoring & evaluation arrangements
| Develop a quality improvement around the role of the care co-ordinator: Ensuring it is more fit for purpose in terms of ability to deliver optimal care to a complex population | Identify core competencies and link these to training being provided within the Trust and associated universities | Head of Nursing and Quality (Community Services) | Ongoing- Draft competencies were developed in 2018. These were refined in consultation with clinicians and service users through a workshop. Competencies will be fully launched as part the Care Coordinator development work in 2019. | i. An established competency framework ii. Training programme iii. Register of attendees at training | Competencies to be signed off and monitored by the monthly Community Service Line Governance Meeting and Trust wide at the monthly Quality Governance Group (QGG), chaired by the Executive Director of Nursing and Quality
|  | Multidisciplinary input into development and implementation of clinical formulations for all service users | Head of Nursing and Quality (Community Services) | Completed- Clinical formulation is included in Risk Assessment Training and Education (RATE) . RATE training was made mandatory and training is ongoing and well embedded through 2018. | i. Training programme ii. RATE training records for Care Co-ordinators iii. Train the Trainer programme has been developed and there are now trainers in each Service Line delivering RATE training | This is reported on in monthly Performance Quality Reviews, chaired by the Executive Director of Nursing and Quality
|  | Commission training sessions for care co-ordinators on treatment for patients with dual diagnosis (patients with mental health and substance misuse concerns) | Head of Nursing and Quality (Community Services) and external Substance Misuse Provider | Ongoing-Dual diagnosis training has been placed on the Trust's Needs Analysis and will be commissioned in 2019 in conjunction with a wider review that commenced in January 2019 and new Dual Diagnosis Clinical Reference Group being established in April 2019. (To note work was done on dual diagnosis immediately following this incident and the RCA in 2012- however the trust has recognised we need to strengthen the overall approach to this area). Senior consultant has been identified to support | i. Training programme ii. Register of attendees at training iii. Outcome of review | Workforce and Organisational Development Committee (meets monthly)
|  | Once training has been delivered, dual diagnosis Champions within each team will be identified. These staff will champion and provide expert advice and support to staff about patients/service users with a dual diagnosis | Head of Nursing and Quality (Community Services) | Ongoing-The anticipated training for November 2018 has been delayed and will be established after the recently agreed review of Dual Diagnosis is completed. This is a clear trust priority for 2019-2020. | i. Clinical Reference Group established i. Training programme ii. Register of expert staff within the organisation iii. Sessions provided by expert staff
|  | Develop care pathway for psychosis | Quality Improvement (QI) Lead | Ongoing-Care pathway review commenced in mid 2018 under the QI framework and the outcome is being delivered through the Community Transformation Programme that commenced in February 2019. | i. A new pathway document | QGG (meets monthly) and is chaired by the Executive Director of Nursing and Quality
|  | Trust to develop a caseload weighting tool and pilot in Community Mental Health teams. This should be rolled out across all teams once pilot is concluded | Head of Nursing and Quality (Community Services) | Completed-Pilot commenced in August 2017 across five teams in the Community Service Line. Rollout Trust wide completed September 2018. | i. Caseload tool ii. Implemented case weighting tool | Community Service Line Governance Meeting (meets monthly)
|  | Implementation of named individual providing practice leadership to head the production of a development programme for the care co-coordinator role | Head of Nursing and Quality (Community Services) | Completed in December 2017. | Head of Nursing and Quality for Community Services has been identified as the named individual. Liaison with other Trusts with regards competencies has taken place and draft competencies have now been developed | Head of Nursing and Quality for Community Services will provide updates on the development programme to the monthly Community Service Line Governance meeting
|  | Ensure service user and carer input to the development programme by running a workshop | Assistant Head of Service (Community Services) | Completed - Workshop took place on the 11th of April 2018. | i. Agenda ii. Register of attendees iii. Follow up actions | Community Service Line Governance Meeting (meets monthly)
|  | Care Co-ordinators to continue to invite service users and carers to all Care Programme Approach (CPA) meetings | Head of Nursing and Quality (Community Services) | Completed-Monthly case records audit introduced in October 2017. Bi-annual notes audit of RiO (patient electronic record system) to commence in 2018.Audits of service user & carers attendance at CPA meetings will be undertaken bi-annually. . | i. Audit results ii. Follow up actions | Community Service Line Governance Meeting (meets monthly)
|  | Sign off development programme for care co-ordinator role | Head of Nursing and Quality (Community Services) | Ongoing-This will be delivered in the care coordinators development 2019 work plan. | Copy of the development programme | QGG (meets monthly)
2 | Develop a quality improvement programme around working with carers to address the day-to-day need for support and information | Develop Carer's Charter and raise awareness of charter | Head of Therapies | Completed-i. Charter developed and in place (fulfilling the core requirements relating to identification, engagement and support) ii. Events planned in the Trust in June 2018 to launch the involvement plan which will include publicising the charter ii. Charter has been concluded | i. Carer's Charter ii. Events Agendas iii. Registers of attendees | The evaluation of Carer's experiences will be reported to the Involvement Plan monitoring group (will meet bi-monthly)
|  | Embed best practice from the Triangle of Care (an approach developed by carers and staff to improve carer engagement in services) - Trust is working with the Carer's Trust to progress to level 2 membership scheme for Triangle of Care | Head of Therapies | Ongoing- Noting the changes nationally to triangle of care. i. The Board has made achieving Triangle of Care best practice a key corporate objective for 2018/19. There is a robust governance and reporting structure to ensure that internal and external stakeholders are engaged and aware of progress at all levels. Triangle of Care re-audits and self-assessments completed by the end of May 2018 (including all community teams). This has been achieved. | i. Completed self-assessments ii. Action plans to address any areas of improvement | Task and Finish Group chaired by Head of Therapies (meets monthly). Attended by Carer's networks from all five boroughs, Service Lines, Service Users and Carers representatives
|  | Production of Carer and Service User Involvement Plan | Head of Therapies | Completed-A full co-produced plan was developed over a 6-month period. The plan has been co-produced and was presented at the well-attended Trust bi-monthly Leadership Conference in March 2018 (ahead of plan) which has executive attendance. The plan signed off at the Quality and Safety Assurance Committee (QSAC) in 2018. The CQC commended the approach plan during their recent inspection. The Trust has agreed a 2018/19 corporate objective to support the implementation of the involvement plan. Involvement Group established and working through plans | i. Involvement Plan ii. Agenda and minutes of QSAC | Involvement Plan monitoring group to be established (plan to meet bi-monthly with first group meeting in June 2018). Service Line specific actions will also be monitored through the monthly Service Line governance meetings
|  | Address partnership working requirements, including a whole family approach to care delivery | Head of Service (Community Services) | Ongoing-i. Set up initial scoping meeting in May 2018 with all Carer's centres to re-engage with this work and agree future working arrangements. ii. Meetings took place with Carer's Trust quarterly commencing in June 2018 to drive the 'Think Family' agenda (this strategy promotes co-ordinated thinking and delivery of services to safeguard children, young people, adults, and their families/carers) and the Triangle of Care. This meeting is chaired by the Director of Nursing and Quality and includes representatives from all five boroughs ii. Expand the 'Think Family' agenda throughout Wandsworth in 2019/20 | i. Agenda and minutes of scoping meeting ii. Agenda and minutes of quarterly meetings | Quarterly meetings chaired by the Executive Director of Nursing and Quality
|  | Evaluate Carer's experience of support provided by the Trust | Head of Therapies | Ongoing-Attain (an external Health Consultancy partner who supported the development of the Involvement Plan) to undertake a qualitative review including Carer survey feedback. Survey to take place in January 2020 (after implementation and embedding of Involvement Plan). | Survey results | Involvement Plan monitoring group (will meet bi-monthly). Will report to QGG, monthly meeting chaired by the Executive Director of Nursing and Quality
3 | Develop a quality improvement programme around inter-agency working between Community Mental Health teams, housing and Mind | Produce and implement an agreed protocol for inter-agency working. Representatives from statutory and voluntary sectors to be brought together with frontline staff, carers and services users at a workshop to analyse and explore ways to mitigate factors that impede effective joint working. This will form the basis for the development of the inter-agency protocol. | Assistant Head of Service (Community Services) | Ongoing- i. Since 2012 work around effective interagency working has radically improved and this was cited by the CQC through their feedback from external stakeholders. A key area of interagency working relates to the Serenity Integrated Mentoring (SIM) project in partnership the Metropolitan Police launched on the 19 April 2018.There remains some additional items of development that is being progress; ii. Workshop completed in April 2018. ii. Stakeholder events commenced in late 2018 and the programme continues through 2019 iii. Risk Forums and pathway meeting now established that involve all key stakeholders iiii. Operational polices are being informed by the on-going stakeholder events and engagement, for example the Single Point of Access has made it clear the interagency roles iiii. Approval and ratification process to take place in April 2019 | i. Workshop agenda ii. Workshop register of attendees iii. Protocol / Operational Polices | i. Workshop agenda ii. Workshop register of attendees iii. Protocol iv. Minutes of meeting where protocol is ratified
|  | Monitoring of protocol (measurement indicators will be included in the protocol) | Assistant Head of Service (Community Services) | Ongoing-Agreed protocol will be shared and endorsed with stakeholders by May 2019 and the monitoring arrangements established. | i. Audit results ii. Follow up actions | Community Service Line Governance Meeting (meets monthly)