## Action Log
SI 2019/13576 Independent Investigation and Domestic Homicide Review
Recommendation | Scope of recommendation i.e. local or regional | Action to take | Lead agency | Key milestones achieved in enacting recommendation | Target date | Completion date and outcome
Recommendation No. 1.1 NHS Morecambe Bay CCG must: Ensure that General Practitioners are reminded to consider a referral for a carer’s assessment when carer responsibilities are indicated. | Local | 1) General Practitioners to be reminded of responsibilities under the Care Act, 2014, to request assessment of care and support needs for individuals presenting with indicators of needs arising from physical or mental health impairment or illness, resulting in a significant impact on the individuals well-being. 2) General Practitioners to be reminded to consider referral for a carer’s assessment when carer responsibilities are indicated. 3) Reminder to be shared via Protected Learning Time sessions (PLT) and Safeguarding forums. 4) A learning brief will be issued to Primary Care colleagues across MBCCG, via the Primary Care Newsletter, following the completion of the DHR / MHHR. 5) Feedback will be provided at Primary Care Quality Assurance visits. 6) Audit to be undertaken to evidence implementation of learning following publication of the DHR / MHHR. 7) Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. MBCCG Audit to ascertain implementation of learning. | 2022-11-01 | Completed 23.05.2022 with additional embedding work to be completed on publication of the DHR. Increased General Practice awareness of the need for Care Act compliant assessments of care and support needs, along with carers assessments where appropriate, resulting in increased referrals from Primary Care to Adult Social Care and improved care and support for adults in need.
Recommendation No. 1.2 Encourage General Practitioners and Primary Care staff to consider risk assessment for the safety of key patient contacts, referring to specialist services where appropriate. | Local | 1) Information regarding risk assessment tools to be shared via Protected Learning Time sessions (PLT) and Safeguarding forums. 2) A learning brief will be issued to Primary Care colleagues across MBCCG, via the Primary Care Newsletter, following the completion of the DHR / MHHR. 3) Feedback will be provided at Primary Care Quality Assurance visits. 4) Practitioners to be encouraged to ensure that in addition to general contact details, Crisis and Out of Hours contact details / sources of support are made available to relatives of those suffering from deteriorating mental health. 5) Audit to be undertaken to evidence implementation of learning following publication of the DHR / MHHR. 6) Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. MBCCG Audit to ascertain implementation of learning. | 2022-11-01 | Completed 23.05.2022 with additional embedding work to be completed on publication of the DHR. Increased General Practice awareness of the need for Care Act compliant assessments of care and support needs, along with carers assessments where appropriate, resulting in increased referrals from Primary Care to Adult Social Care and improved care and support for adults in need.
Recommendation No. 1.3 Ensure that General Practitioners are reminded to consider adding safety alerts to relevant patient notes where an individual is known or suspected to pose a risk to others. | Local | 1) Discussion to be held with Primary Care colleagues regarding strengthening information sharing between Primary and Secondary Care health records systems. 2) Reminder to be shared via Protected Learning Time sessions (PLT) and Safeguarding forums. 3) A learning brief will be issued to Primary Care colleagues across MBCCG, via the Primary Care Newsletter, following the completion of the DHR / MHHR. 4) Feedback will be provided at Primary Care Quality Assurance visits. Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. MBCCG Audit to ascertain implementation of learning. | 2022-11-01 | Completed 23.05.2022 with additional embedding work to be completed on publication of the DHR. Improved information sharing processes implemented across Primary and Secondary healthcare services leading to improved patient and practitioner safety.
Recommendation No. 1.4 Explore whether there are systems available to assess the safety of family members and informal care providers who are supporting patients with mental health issues in the community and advise GP practices accordingly. | Local | 1) Confirm safety systems available (i.e. risk assessments, MAPPA / MARE / probation processes) and feedback to Primary Care. 2) Findings to be shared via Protected Learning Time sessions (PLT) and Safeguarding forums. 3) A learning brief will be issued to Primary Care colleagues across MBCCG, via the Primary Care Newsletter, following the completion of the DHR / MHHR. 4) Feedback will be provided at Primary Care Quality Assurance visits. 5) Audit to be undertaken to evidence implementation of learning following publication of the DHR / MHHR. 6) Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. MBCCG Audit to ascertain implementation of learning. | 2022-11-01 | Partially completed - refreshed briefing with up to date processes to be shared following DHR publication. Better understanding of systems available to keep family members and informal care providers safe, with the intention of sharing this information with Primay Care, leading to increased referrals and reduced risk of harm.
Recommendation No. 1.5 Encourage GP’s to audit against recommendation No. 1.4 | Local | 1) Audit will be encouraged at Protected Learning Time sessions (PLT) and Safeguarding forums. 2) A learning brief will be issued to Primary Care colleagues across MBCCG, via the Primary Care Newsletter, following the completion of the DHR / MHHR. Audit of internal processed to be recommended within the briefing. 3) Audit suggestion will be made at Primary Care Quality Assurance visits 4) Audit to be undertaken to evidence implementation of learning following publication of the DHR / MHHR. Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. MBCCG Audit to ascertain implementation of learning. | 2023-04-01 | To be completed by 01.04.2023. Assurance that Primary Care services have taken on board the recommendations of the DHR, have adapted practice accordingly and further reduced risk of harm to others.
Recommendation No.1.6 Work with providers and medicines management teams to try and develop a process by which the GP / Practice Pharmacist are notified of patients failing to collect prescriptions and communicate this effectively to relevant parties, particularly where a shared care agreement is in place. | Local | 1) Discuss with Medicines Management Leads – for progression to regional Local Pharmaceutical Committee. 2) Learning will be shared with Designated Adult Safeguarding Leads across Lancashire and South Cumbria ICS, along with MBCCG executive leads, to support system wide learning. | Morecambe Bay Clinical Commissioning Group – Quality and Safeguarding Team. | MBCCG Quality and Safeguarding Team to evidence actions through meeting agendas and feedback, along with archived Safeguarding newsletters. Assurance to be provided to MBCCG at the Safeguarding Formal Leadership Meeting. | 2023-06-01 | Action completed but resolution to issue not yet found. Work around this is ongoing. Improved communication between pharmacy services and prescribers to highlight medication concordance and improve health outcomes.
Recommendation No 2 Cumbria and Lancashire Rehabilitation Company must provide assurance that: • Risk assessments are updated at expected intervals and communicated to other agencies. • There is a policy that applies where the individual is open to multiple agencies, clarifying when information and risk assessments must be shared with the other agencies involved. This should relate to the Probation Service from June 2021 | Regional | Implementation of National Standards 2021 across the Probation Delivery Unit (PDU) | County-wide Senior Probation Officers (SPOs) | Probation Service Performance Measures Individual Case Audit activity – regional audit activity will take place on a rolling annual basis and will look to deep dive into the practice of all individual Probation Practitioners at set intervals annually. Specific DHR related internal audits to be done at 6-month point – Terms of Reference to be developed by SPO and Deputy Head and implemented by QDO and SPO; they will focus on - Quality of Assessment - Information Gathering - Sharing of asst and information - Significant Event & review | 2022-04-29 | The following NS will be fully implemented across the PDU by end of April, which specifically target the learning identified through this review: 5.5 - Engagement with community resources is facilitated as an integral part of implementing the Plan. 1.2 - Records are kept up to date, stored securely, and are accessible to appropriate parties. 4.3.1 - The identification of risk of serious harm, reoffending, and the needs of the individual. 4.3.3 - A completed risk management plan where the individual presents a medium /high or v high risk of serious harm 4.3.4 - Others involved in the delivery of the sentence are named and contact expectations made clear. 8.1 - Risk of causing serious harm is managed, using a multi-agency approach where appropriate. 10.1 - The assessment and plan is reviewed whenever there is information indicating a significant change that impacts on the risk of re-offending and/or serious harm posed by the person on probation
Recommendation No 2 Cumbria and Lancashire Rehabilitation Company must provide assurance that: • Risk assessments are updated at expected intervals and communicated to other agencies. • There is a policy that applies where the individual is open to multiple agencies, clarifying when information and risk assessments must be shared with the other agencies involved. This should relate to the Probation Service from June 2021 |  | Full implementation of Touch Points (Management Oversight) Model across the caseload National_Standards_2021_-_Supporting_transition_to_the_Unified_Model_-_June_2021__in_English_.pdf (publishing.service.gov.uk) | The Probation Service - Lead Senior Probation Officer (SPO) / Deputy Head of Probation Delivery Unit (PDU) | Overview of TPM Report in Performance Mtg Individual Case Audit activity – regional audit activity will take place on a rolling annual basis and will look to deep dive into the practice of all individual Probation Practitioners at set intervals annually. Specific DHR related internal audits to be done at 6-month point – Terms of Reference to be developed by SPO and Deputy Head and implemented by QDO and SPO; they will focus on: - Quality of Assessment - Information Gathering - Sharing of asst and information - Significant Event & review | 2022-04-29 | TPM fully implemented across full caseload and demonstrable positive impact evidenced
Recommendation No 2 The Probation Service: Cumbria and Lancashire Rehabilitation Company must provide assurance that: • Risk assessments are updated at expected intervals and communicated to other agencies. • There is a policy that applies where the individual is open to multiple agencies, clarifying when information and risk assessments must be shared with the other agencies involved. This should relate to the Probation Service from June 2021 |  | Facilitate PDU wide improvements to understanding and working with MH | The Probation Service - Mental Health Lead Senior Probation Officer (MH SPO) / Deputy Head of Probation Delivery Unit (PDU) | Head of PDU feedback re: strategic engagement and links Feedback from Teams re: working relationships with MH and outcomes | 2022-04-29 | Ensure Probation represented at relevant MH Strategy Groups Agree and implement MH escalation process where inter-agency disagreement Review the previously implemented Mental Health Treatment Requirement (MHTR) Protocol to ensure remains fit for purpose and re-implement if required Identify Cumbria training / development offer from North and South Providers Identify MH practitioner Single Point of Contact (SPOCs) across the PDU
Recommendation No: 3 Prison health care providers must ensure that systems are in place to share secondary prison health care consultations and information with GPs on discharge or release. |  | Spectrum to send discharge information to the community GP until GP2GP connects to prison electronic records. | HMP Preston Spectrum - Head of Healthcare | Submission of Quality Schedule to NHS England for assurance | 2021-06-30 | GPs to receive information for continuity of care.
Recommendation No: 3 Prison health care providers must ensure that systems are in place to share secondary prison health care consultations and information with GPs on discharge or release. |  | Information to GPs on discharge back to the wing | HMP Preston Spectrum - Head of Healthcare | Submission of Quality Schedule to NHS England for assurance | 2021-06-30 | All prison health records are on one electronic patient record system which all health providers working in the prison have access to.
Recommendation No: 3 Prison health care providers must ensure that systems are in place to share secondary prison health care consultations and information with GPs on |  | Referral to external secondary mental health services must be made where indicated. | HMP Preston Spectrum - Head of Healthcare | Submission of Quality Schedule to NHS England for assurance | 2021-06-30 | Referral was made to Guild Lodge, assessment was completed and found he did not meet the criteria for secondary mental health services at the time.
Recommendation No 4 The Trust must ensure that there is clear guidance to be followed for the care of patients who present as sexually disinhibited, which adheres to national guidance on same sex accommodation. | Local | No further action required. The Trust developed a Sexual Safety Policy and Procedure (CL074), which was ratified on 17/3/2021. This is supported by the Same Sex Accommodation Policy (CL049). Implementation of the Sexual Safety Policy and Procedure is overseen by the Trust’s Sexual Safety Group. The Sexual Safety Policy and Procedure was communicated to staff in the Policy and Procedure update in June 2021. | The Trust | Policy and procedure in place. Compliance will be provided by future audit of the policy and procedure. | 2023-09-30 | Sexual Safety Policy and Procedure (CL074) Same Sex Accommodation Policy (CL049) Notification to staff of new Sexual Safety Policy and Procedure
Recommendation No 5 The Trust must ensure the use of Section 17 leave is supported by robust risk assessment and clear care plans that are agreed by the multidisciplinary team (MDT) and families as appropriate. | Local | Re-audit of section 17 leave procedure | The Trust | Section 17 leave procedure and form | 2023-09-30 | Demonstrate improved compliance with procedure
Recommendation No 5 The Trust must ensure the use of Section 17 leave is supported by robust risk assessment and clear care plans that are agreed by the multidisciplinary team (MDT) and families as appropriate. | Local | Discuss results of most recent audit at Inpatient Best Practice Group, care quality delivery groups or equivalent meetings for ward managers/nurse consultants/matrons for each locality | The Trust |  | 2023-09-30 | Staff are aware of audit results and work with their teams to drive continuous improvement
Recommendation No 5 The Trust must ensure the use of Section 17 leave is supported by robust risk assessment and clear care plans that are agreed by the multidisciplinary team (MDT) and families as appropriate. | Local | Review code of practice wording re sharing S17 leave form with carers etc. | The Trust |  | 2023-09-30 | To ensure the code is understood and being implemented
Recommendation No 5 The Trust must ensure the use of Section 17 leave is supported by robust risk assessment and clear care plans that are agreed by the multidisciplinary team (MDT) and families as appropriate. | Local | Following review of code of practice regarding sharing S17 leave form, review and revise Rio form if required | The Trust |  | 2023-09-30 | To be able to record whether the S17 leave form has been shared and if not, why not
Recommendation No 5 The Trust must ensure the use of Section 17 leave is supported by robust risk assessment and clear care plans that are agreed by the multidisciplinary team (MDT) and families as appropriate. | Local |  | The Trust |  | 2023-09-30 | Background information: The Trust has completed a recent audit of section 17 leave. Data was collected during June and July in 2021 and the report completed in October 2021. The results are being evaluated to develop a deeper understanding of the variable levels of compliance, which in turn will enable targeted improvement work to improve overall compliance across the Trust. This demonstrated the following compliance: • Standard 1 (5.3) The granting leave and details of any conditions attached must be recorded on one or more of the Trust’s standard LOA forms and a copy given to the patient and, with the patient’s consent, and where appropriate, to the carer, relative or other support agencies directly involved Recording of leave and details of conditions of leave was recorded in 100% of cases with a copy given to the patient and where appropriate the carer, relative or other support agency directly involved in 26% of cases. The audit report noted that the S17 authorisation form on RiO (current clinical record system) does not have any area to note that the form has been shared, whereas the form on ECR (previous clinical record system) did and this may explain the low levels of compliance • Standard 2 (5.5) Risk assessments in relation to leave will be recorded by the responsible clinician on the patient’s electronic record prior to granting leave and following multi-disciplinary discussions. Compliance 93% The Inpatient Safety Matrix Q.31 reports compliance to the question “Is there clear evidence that the patient and, where appropriate their carer / family have received a copy of the section 17 form?” In October 2021 compliance was 77% (76/99).
Recommendation No 6 The Trust must demonstrate that referrals for Psychiatric Intensive Care Unit (PICU and/or out-of-area treatment) include clinical assessment and recommendations. | Local | The Trust will add this to the audit plan, to audit a sample of records to demonstrate that referrals for Psychiatric Intensive Care Unit (PICU and/or out-of-area treatment) include clinical assessment and recommendations. Prior to the trust audit, matrons will be asked to spot-audit the last five admissions to each PICU, to check that referrals for Psychiatric Intensive Care Unit (PICU and/or out-of-area treatment) include clinical assessment and recommendations. | The Trust | Psychiatric Intensive Care Units (PICU) Standard Operating Procedure (MH 003) approved May 2019 Inpatient SOP Section 5.2.3 | 2023-09-30 | Clinical audit results
Recommendation No 7 The Trust must ensure that evidence-based treatment plans are in place, that are in line with NICE treatment guidance ‘Psychosis and schizophrenia in adults: prevention and management’ (2014). | Local | The Trust has an improvement plan for Early Intervention Services (EIS), which it is working on with support with NHSE and overseen by LSCFT Medical Director. The Trust participate in the national clinical audit of psychosis and the 2021 data will be used to demonstrate compliance. Any areas identified as non-compliant will be included in the improvement plan. | The Trust | 2020 Summary of Trust results in the national clinical audit of psychosis | 2023-09-30 | Demonstrate compliance with the with NICE treatment guidance ‘Psychosis and schizophrenia in adults: prevention and management’ (2014).
Recommendation No 8 Any changes to the risk assessment tools used by the Trust should be informed by current research and recommendations from independent bodies. Any newly developed tools should be based on current knowledge and informed by independent experts in risk assessment in mental health services. They should also be subject to independent evaluation by experts in risk assessment before they are implemented. | Local | A multi-professional review of the Trust’s approach to Clinical Risk is being undertaken; this is being aligned with the move from CPA to Dialog/Dialog+. | The Trust |  | 2023-09-30 | Review of the Trust’s risk assessment tool
Recommendation No 8 Any changes to the risk assessment tools used by the Trust should be informed by current research and recommendations from independent bodies. Any newly developed tools should be based on current knowledge and informed by independent experts in risk assessment in mental health services. They should also be subject to independent evaluation by experts in risk assessment before they are implemented. |  | Review of the Trust’s risk assessment tool | The Trust |  | 2023-09-30 | Background information: At the time of this incident, South Cumbria mental health services were using a different risk assessment tool from the rest of LSCFT. All LSCFT mental health services are now using the same risk assessment tools. Please see recommendations 11, 12, 23 and 25 regarding management of ongoing risk whilst the review is underway. Clinical Risk Level 2 training was introduced in Autumn 2020, following the updating of the LSCFT Clinical Risk Manual. The Associate Medical Director for Patient Safety and the Head of Nursing & Professional Practice are working together to ensure that learning from recent SIs and any changes in national guidance are included within the Level 2 Clinical Risk Training. Following on from this, there is a need to review risk assessment and risk management planning with the move from CPA to Dialog/Dialog+.
Recommendation No: 9 Cygnet Health Care: Must ensure that the risks identified by local services are clearly visible in any risk assessment completed by Bearsted Ward, and that when risks are identified they are recorded and mitigation plans developed. |  | 1) All nursing, medical, assistant psychologists, qualified Social Workers, Psychologists and Occupational Therapists to attend START training (1 day) to ensure competent with completing START paperwork. 2) START to line up with DRA as they feed into each other. 3) The START includes a written formulation of risk which will be completed for all patients. 4) The MDT to review the START at ward round. 5) The ward to keep, maintain and update the skills required to implement a number of evidence based risk assessment tools relevant to a number of risk domains including: • Violence and aggression • Suicide and self-harm • Vulnerability • Potential for offending in the context of mental disorder e.g. sexual risk, fire setting, etc. 6) Risk assessments to include consideration of adult safeguarding, child protection, victim considerations, and other vulnerabilities (for example alcohol and drug use, financial exploitation). 7) On admission every service user has a START risk assessment completed and this is updated following any significant events but at a minimum of weekly. | Cygnet Health Care - Nursing & MDT |  | 2019-12-31 | Corporate - Agreed PICU/Acute ward round templates have been approved that focuses on risk formulation and shared MDT decision making. Corporate - All patients that are considered for discharge from PICU now has to be discussed with the site Senior Management Team. START Training figures Ward Rounds with MDT review of risks Weekly audits which we reviewed in Head of Care meeting covering planning and communications Random spot checks carried out by Medical Director covering risk assessment and formulation
Recommendation No 10 The Trust must ensure that families and carers are appropriately involved in care planning and risk assessment. | Local | No further action required. The Trust has implemented an inpatient safety matrix, which audits a sample of clinical records monthly and specifically asks: “If appropriate, is there evidence that the carer has been involved with completing the risk assessment with clear evidence that their views and opinions are recorded?” A Community MH Safety Matrix is currently being piloted and includes similar questions in relation to family and carer involvement. Furthermore, there is a strong focus on family and carer involvement within the CMHT Transformation Programme. | The Trust | Care plan procedure | 2023-09-30 | Inpatient Safety Matrix results shows increasing compliance (q.41) for involving families in risk assessment
Recommendation No 11 The Trust must ensure that it is recognised that supportive families may also be at risk of harm, and that comprehensive assessments and supportive plans are developed. | Local | No further action required This would form part of process of assessing the risk the service user presents to others and be addressed as part of the service users’ risk assessment, leave risk assessment and whether a safeguarding referral is needed. From 1 April 2021, new Safeguarding Level 3 training was launched. Eligible professionally registered health or social care practitioners working for LSCFT need to complete 8 hours of mandatory safeguarding training, plus an additional 4 hours of CPD at Level 3, every 3 years. The Level 3 training brings together training for children and adults as a Think Family training package (appendix 3). Compliance with safeguarding training is monitored and reported regularly. | The Trust | Clinical risk assessment policy and procedure Section 17 leave policy Safeguarding level 3 training | 2023-09-30 | Safeguarding Level 3 compliance at 2/11/2021 was 85.72% and plans are in place to drive increased compliance.
Recommendation No 12 The Trust must seek assurance that safeguarding supervision is accessible and provided to staff within ward environments in accordance with NHS England Safeguarding Accountability and Assurance Framework 2019. | Local | No further action required. Safeguarding supervision is in place for inpatient units. Safeguarding supervision is inputted onto ESR, but is not mandated. Safeguarding Specialist Practitioners are currently supporting implementation in the localities. The localities provide assurance reports to the Safeguarding sub-committee bi-monthly. There is also best practice guidance to support implementation of quarterly supervision groups. | The Trust | Quarterly Safeguarding report extract detailing groups that took place in Q2 | 2023-09-30 | Evidence of safeguarding supervision within ward environments
Recommendation No 13 The Trust must seek assurance that the Trust Safeguarding Service is made aware of Trust incidents where there is harm caused to a service user to ensure appropriate safeguarding oversight. | Local | No further action required. • The Safeguarding team has a duty practitioner, who reviews all safeguarding incidents and receives notifications • Safeguarding have issued a 7 minute briefing to reiterate what constitutes a safeguarding incident • Safeguarding practitioners attend the weekly locality Serious Incident Review Panels • Weekly call between Safeguarding and Head of Patient Safety to review incidents • Patient Safety Team review all moderate harm and above incidents and escalate to Safeguarding when Safeguarding not previously identified • SI notifications sent to Safeguarding lead and shared with Safeguarding team via the safeguarding pathway • The safeguarding team are currently strengthening and formalising pathways between themselves and FTSU Guardian, Complaints and CQC teams • Incident reporting training for staff includes how to code and report safeguarding incidents | The Trust | SOP for Safeguarding duty role. SI notification pathway for Safeguarding. | 2023-09-30 | Evidence that the Trust Safeguarding Service is made aware of Trust incidents where there is harm caused to a service user to ensure appropriate safeguarding oversight.
Recommendation No 14 Lancashire and South Cumbria Foundation Trust and Cumbria County Council, Adult Social Care: Staff must consider how best to communicate information to Nearest Relatives, so they can be assured that the Nearest Relative clearly understands their role and rights under the Mental Health Act. Simplified versions of written materials are recommended, where they are not already in use. |  | Cumbria County Council, Adult Social Care, have issued the DoH’s easy read Nearest Relative document to all Approved Mental Health Professionals (AMHPs). The AMHP will offer this document to Nearest Relatives – as appropriate – in the course of their duties assessing a person under the MHAct. This will be communicated formally to all AMHP’s via email; it will be reiterated through team meetings and the Cumbria AMHP forum | Cumbria County Council - Senior Manager for Mental Health, Learning Disabilities and Autism | An easy read document produced by the Department of Health regarding the Nearest Relative and their rights. | 2021-11-02 | Complete 02/11/2021 For clear information on the role of the Nearest Relative to be made available at the point of assessment and admission; to support ‘nearest relatives’ to understand their role in making decisions about the detention of their relative.
Recommendation No 14 Lancashire and South Cumbria Foundation Trust and Cumbria County Council, Adult Social Care: Staff must consider how best to communicate information to Nearest Relatives, so they can be assured that the Nearest Relative clearly understands their role and rights under the Mental Health Act. Simplified versions of written materials are recommended, where they are not already in use. |  | On admission LSCFT Mental Health Law Team write to the nearest relative with an information leaflet if the patient gives consent (s132 rights). If the patient lacks capacity the Mental Health Law Team would look to write to the NR anyway, as it’s in the interests of the patient. LSCFT Mental Health Law Team write to the nearest relative on discharge. The DoH easy read document has now been included in the document being issued | Cumbria County Council - Interim Head of Mental Health Law |  |  | Related documents 1) Patieint Information - ADMISSION TO HOSPITAL FOR ASSESSMENT (Section 2 of the Mental Health Act 1983) 2) Patieint Information - ADMISSION TO HOSPITAL FOR TREATMENT (Section 3 of the Mental Health Act 1983) 3) Letter to Nearest Relative 4) Appendix 1- Record of Patient Rights under Section 132 MHA 1983 5) YOUR NEAREST RELATIVE UNDER THE MENTAL HEALTH ACT 1983 (Sections 26-30 of the Mental Health Act 1983) 6) An easy read fact sheet - Your Nearest Relative
Recommendation No: 15 & 26 15. NHS England should share learning identified with the First Tier Tribunal (Mental Health) regarding providing guidance to families about how any confidential information they share may be used. 16. NHS England should share the learning with the First Tier Tribunal (Mental Health) about parricide and risk to family members, and how sensitive third-party information is managed. |  | To arrange a call with the First Tier Tribunal representative’s to share the learning outlined in the draft report, regarding confidential information families share, how sensitive third party information is managed, and parricide and risk to family members. | NHS England | Call to be arranged in 2023 |  | For First Tier Tribal to be aware of the report and the recommendations made. For them consider their own protocols on how they share information received and how they manage risks for family members re parricide
Recommendation No 16 The Trust must ensure that serious incident investigations are carried out at the appropriate levels, within expected timescales and that they provide evidence of action plan implementation | Local | No further action required. There is weekly review of progress with serious incident investigations within the Patient Safety Team, at the weekly Safety Summit chaired by the medical director and weekly progress reports are sent to network triumvirate leads. This is also reported monthly to commissioners. | The Trust | Weekly serious incident meeting. Weekly Safety Summit Weekly SI performance report Information sent to commissioners monthly | 2023-09-30 | Serious incident investigations are carried out at the appropriate levels, within expected timescales
Recommendation No: 17 Must ensure that serious incident investigations are carried out at the appropriate levels, within expected timescales and that they meet expected NHS England national standards. |  | 1) Closer liaison between investigator and Police regarding investigations and court cases to confirm next of kin details and understand when they can be contacted to support a Cygnet internal investigation. 2) Investigation RCA guidance to include direction to investigator to liaise with Police constable appointed. 3) Memorandum of understanding to be created which includes responsibilities of the appointed investigator - this to be shared with investor/s at time of appointment. 4) Final RCA investigation report to be shared with mother. | Cygnet Health Care - Appointed investigator & Corporate Risk Manager |  |  | Weekly audits reviewed at Head of Care meetings SipRep and Head of Care meetings covering SI review and Duty of Candour. Final report shared by investigator- completed. Corporate - Investigator Memorandum of understanding completed. Corporate - RCA guidance updated including close liaison with Police to clarify aspects of investigation/ communication. Corporate - Investigation report change log developed which is reviewed at Group Safety Committee - this includes a section for family liaison/duty of candour check.
Recommendation No: 18 Policies should clearly demonstrate the sign off and governance process. |  | Create a new Policy Implementation Group (PIG) | Healthcare (North) - Managing Director |  | 2021-01-06 | Corporate Policy Implementation Group will: • Demonstrate the sign off process and governance arrangements in place for policies. • Ensure identified leads in place for all policy reviews. • Define the policy implementation process and ensure clear lines of responsibility and timescales for implementation. • Ensure training or resource requirements and extra support has been identified if required. • Promote inclusive culture within all policies. • Ensure that policies are appropriate for all relevant service types. • Agree and prioritise implementation and understand any barriers or risk to implementation. • Review implementation progress at local level and escalate to local risk register as required. • Oversight of and review the list of forthcoming routine reviews, extraordinary reviews and proposed new policies.
Recommendation No: 19 Must demonstrate and provide assurance to commissioners that their admission, discharge and Care Programme Approach (CPA) policies are adhered to. |  | 1) Discharge CPA/Section 117 meeting to be arranged by Medical Secretary where possible for those where discharged is planned (i.e. not recalled patients). 2) When date for meeting is agreed with the Consultant, the Medical Secretary will liaise with the home team, funder, care co-ordinator and carer to ensure attendance at this meeting. | Cygnet Health Care - Consultant/Ward Manager |  | 2019-12-31 | Corporate -. Discharge summaries are audited across the portfolio to ensure we send out comprehensive care summaries within 10 working days of discharge Corporate - Cygnet wide Transfer and Discharge policy has been launched across the portfolio with clear standards of process and procedure with regards to discharge Corporate - Discharge notification template designed to go out on the same day as discharge with clear discharge plan, medication list and brief summary of care. Operational discharge policy outlining process is on ward. Weekly discharge process audit. All discharge notifications are being checked by the consultant before being sent off Random spot checks carried out by Medical Director.
Recommendation No: 20 NHS England: Should gain assurance about the quality of private PICU provision following the principles of host commissioning arrangements. This is to ensure that the local CCG/ICS monitors and has quality oversight for providers in their locality. Quality issues should be raised via the quality system oversight groups |  | NHS England currently have hosting commissioning principles in place mainly for LD services. There are some areas that are following this guidance. However, there is a national plan for highlighting roles and responsibilities for hosting commissioners and placing commissioners for mental health services. The draft communications are expected in June/July 2022, this will be articulated nationally. | NHS England | Host Commissioner Guidance | 31/01/2022 31/07/2022 | NHSE will be expecting national guidance following the same principles for Mental Health service as Learning Disability placements. We will get formal agreement. This will support placements for other neuro diverse needs. It is expected that this principle will come into effect immediately.
Recommendation No 21 Safer Cumbria and local Community Safety Partnerships (CSPs): Should develop systems to ensure there is oversight of the implementation of action plans from Domestic Homicide Reviews (DHR). |  | The recently agreed joint DHR protocol between the CSPs and Safer Cumbria sets out some principles about how the actions and lessons learned from DHRs should be embedded and audited. The Safer Cumbria Domestic Abuse Group has agreed to establish a sub-group to receive action plans from DHRs at the earliest possible opportunity. This Group will: • Receive and consider all Incident Management Review (IMR) findings, DHR findings and DHR recommendations to ensure that any systems or multi-agency recommendations are progressed. • Report to the CSPs on systems or multi-agency recommendations • Work with the CSPs to audit individual organisations actions to ensure that all organisations are embedding agreed actions and learning • Provide check and challenge around any action plans • Provide reports to the Domestice Abuse Group (DAG) on actions and assurance and escalate in issues of concern. The DAG will report upwards to the Safer Cumbria – Community Safety Group any issues that it cannot resolve. | Cumbria Domestic Abuse Group - The Chair | Notes from DA & DHR Groups to consider response to recommendations. | 2021-07-22 | Process in place to ensure effective embedding and audit of emerging action plans. Historic Audit of actions commenced.
Recommendation No 22 The Trust must ensure that risk to families is considered as part of risk assessment and management, with collateral information from family members. | Local | See recommendation 11 and 12. | The Trust |  | 2023-09-30
Recommendation No 23 Safer Cumbria: Must develop and implement a comprehensive domestic abuse strategy which includes learning from this review. |  | Safer Cumbria has previously taken a decision that in order to drive improvement it would no longer produce strategies but instead focus on developing and delivering action plans. As a result, the Domestic Abuse Group of Safer Cumbria has produced an action plan setting out key priority areas and associated implementation plans. The Domestic Abuse Group will be reviewing these action plans in light of the recommendations contains in this report. | Cumbria Domestic Abuse Group - The Chair | Safer Cumbria – Community Safety Group Business Plan | 2022-12-31
Recommendation No 24 The Trust must incorporate the understanding of potential risk of harm to parents into risk assessment training, policy and procedures. | Local | Please see recommendation 11 and 12 Clinical risk assessment policy and procedure embedded | The Trust | Clinical risk assessment policy and procedure | 2023-09-30
Recommendation No 24 The Trust must incorporate the understanding of potential risk of harm to parents into risk assessment training, policy and procedures. | Local | The Clinical Risk Training Manual is being reviewed, particularly in relation to broader social determinants of relapse and harms. | The Trust |  | 2023-09-30 | Revised clinical risk manual
Recommendation No 24 The Trust must incorporate the understanding of potential risk of harm to parents into risk assessment training, policy and procedures. | Local | No further action required. Safeguarding Level 3 training has been revised so that it is now a ‘Think Family’ training package. Training compliance is monitored via the GAPP report | The Trust | Safeguarding Level 3 training information | 2023-09-30
Recommendation No: 25 NHS England: Should share learning identified about parricide with the Home Office. |  | Telephone call and feedback rport provided to the Home Office | NHS England | Home Office Feedback Joint DHR & II recommendations | 2022-01-13 | Complete 13/01/2022. For the Home Office to consider future inclusion of the risk of parricide into policies and protocols.
Recommendation No: 26 NHS England: Should share the learning with the First Tier Tribunal (Mental Health) about parricide and risk to family members, and how sensitive third-party information is managed. |  | See recommendation 15 above | NHS England