## Sheet1
EMIS PCN Hub Clincial System Functionality Issues
EMIS issues have been updated at time of publication. All of the issues are still being discussed with EMIS and updates will be provided to document once an issue has been resolved.
Functionality | Functionality Description | Issue | Case for Change | Current Status - FHR PCN Comments | FHR PCN - Latest Update | EMIS Comment | Date of EMIS comment
Patient Trace - Appointment Book Workflow | Patient Trace is the functionality that is used to register a patient within an EMIS Clinical Service. | When a practice books into the EMIS Clinical Service via an EMIS to EMIS cross-organisational appointment booking it is not possible to efficiently trace the patient from the appointment book. Instead, the user has to manually take a note of the outline demographics of the patient that has been booked into the appointment book, and then enter them into the Patient Trace screen. Alternatively, the booking practice would need to be asked to manually add the NHS number to the slot notes when booking the appointment. This would then be copied and pasted by the EMIS Clinical Service user from the appointment slot notes into the Patient Trace screen. | The EMIS Clinical Service surfaces a set of patient demographics within the appointment booking. The Patient Trace screen should be directly accessible from the appointment that has been booked. The EMIS Clinical Service should be able to pull the known set of patient demographics into the Patient Trace screen when accessed from the booked appointment. This would result in a more efficient process for registering the patient that reduces human error in the manual registration process. | No EMIS development planned. The current position from EMIS is that organisations using an EMIS Clinical Service are encouraged to use GP Connect to make cross organisational appointment bookings. This is on the basis that GP Connect manages the patient registration automatically, meaning the patient does not need to be manually registered in the EMIS Clinical Service. If an organisation uses GP Connect for cross organisational appointment booking they will be subject to other limitations - not being able to target appointments from a specific PCN service for example. Furthermore, a separate view within EMIS is required in order to make GP Connect bookings, and see and GP Connect bookings that have been made for patients. | 2023-05-25 | Under review, however preference is to improve GPC Appointments rather than indefinitely keep & enhance EMIS-EMIS Cross Org | 14th July 23
Patient Trace - Document Management Workflow | Patient Trace is the functionality that us used to register a patient within an EMIS Clinical Service. | When a document is received into the EMIS Clinical Service workflow it is not possible to efficiently register the associated patient in the EMIS Clinical Service. Instead, the user has to manually take a note of the outline demographics or NHS number, contained within the document, and then enter them directly into the Patient Trace screen. | The EMIS Clinical Service should be able to pull the known set of patient demographics from the document into the Patient Trace screen from the Workflow module. This would result in a more efficient process for registering the patient that reduces human error in the manual registration process. | EMIS have now developed an enhancement that is aimed at addressing this issue. Awaiting demonstration and expected deployment timescales. | 2023-05-25 | Dev complete, awaiting release post EMIS 64 bit upgrade. FHR attended demo of functionality . | 14th July
Consultation Write Back - Practice to Practice Write Back | Consultation write back is triggered based upon patient registration types. This means that in the many to many technical sharing agreement setup there will be consultations written back between practice systems, as well as hub to practice. | There is no ability to configure consultation write back to rule out practice to practice write back. | In a PCN Hub operating model the problem statement that consultation write back needs to address is coding a hub derived consultation back into the GP record. Practice to practice consultation write back experienced during the pilot caused significant issues as it was not viable to manage this additional scope of presentations being written back to practice records in terms of staff training, medicines management and audit. | A series of one to one technical sharing agreements were used to successfully address this issue within the pilot. EMIS did not deem this approach to be scalable once the functionality was on general release. Due to a consultation write back incident that occurred outside of the pilot, but by which the pilot was impacted, EMIS have prioritised development of an enhanced sharing agreement within which practice to practice consultation write back can be configured out. Awaiting development timelines. Interim measure is that EMIS has agreed to configure PCNs with one to one consutlation write back techncial DSAs upon request to EMIS Account Manager. | 2023-05-25 | Top CWB enhancement. All Discovery complete with relevant depts. Currently awaiting start date from dev team (8 week dev / Test estimate) Mitigated by potential use of 1 to 1 sharing agreements in PCNs. | 14th July
Consultation Write Back - Audit | There is a need to be able to audit entries within the GP record that have occurred as a result of the Consultation Write Back functionality. | Although consultation send status is now a field that can be reported upon within EMIS it is not possible to determine the organisation from which the consultation write back entry was sent. This field is populated with the word 'national' regardless of which organisation sent the consultation back to the practice. | An organisation that has activated multiple consultation write back agreements must have suitable audit tools available to them in order to investigate incidents, manage service and rule such entries in, or out, of any reporting. | Issue was formally raised with EMIS Support January 2023 [see: CS1065594]. Issue still currently being investigated by EMIS - currently awaiting resolution. | 2023-05-25 | Still under investigation. Not consistent across all sites. Will escalate internally for resolution ASAP. | 14th July
Consultation Write Back - Visual Prompt | There is an icon within the care record screen that indicates that an entry in the record has occurred as a result of consultation write back. | This icon does not appear in other views of the patient record such as within the 'Medications' or 'Documents' screen. | The visual prompt for consultation write back entries should be visible in all views of the patient record in the same way that it is for shared care record views. A user must be able to clearly identify when an entry in a patient's record has been made by another organisation. | This is on EMIS enhancement list for consultation write back. Currently scheduled to be reviewed in October 2023. | 2023-05-25 | Q4 dev candidate. | 14th July
Consultation Write Back - Third Party Suppliers | When utilising third party products to write into the patient’s record within the EMIS Clinical Service the consultation write back functionality will not be triggered. | Third party products (such as accuRx, eConsult toolbar etc) being used to add entries into the GP record are utilising a consultation type that the will trigger the consultation write back functionality. | These third party products are seamlessly adding to the patient's record in EMIS Web at the GP practices, this equivalent functionality should be included in the scope of consultation write back. Currently a manual workaround has to be used, which is subject to human error. This involves editing a consultation entry that has been made by a third party product and changing the conusltation type in order to force the entry to send via consultation write back. This will only work if the third party product consultation is being edited for the first time. | This is on EMIS enhancement list for consultation write back. It is currently listed as the second priority. Currently scheduled to be reviewed in August 2023. | 2023-05-25 | Was initially a Q3 goal. Now moved due to new sharing agreement type taking top priority. Currently #3. #1 = New DSA type #2 = Resend Option #3 = 3rd Party Products also write back | 14th July
EMIS Clinical Service - third party accreditation status | Difficult for a customer or a third-party supplier to understand whether an accreditation is in place for use of product within an EMIS Clinical Service. | Third party suppliers do not understand the EMIS accreditation process for EMIS Clinical Service. There are a number of third party suppliers that have been configured into EMIS Clinical Service without having the relevant EMIS accreditation status. | There needs to be a consistent assurance process in place from EMIS. This will ensure that both third party suppliers, and customers, will understand whether a product is accredited for use within an EMIS Clinical Service. | EMIS has listed a number of third part suppliers on EMIS Now that are accredited for use within an EMIS Clinical Service. EMIS are actively working through third party accreditation status for existing partners and have amended their initial accreditation process for new partners to make clear what is required for use within an EMIS Clinical Service. | 2023-05-25 | EMIS Partner team advise all new Partners of PCN working and accreditation requirements. Legacy solutions going through accreditation (including Graphnet who are in final stages) List of PCN partners on EMIS Now page. | 14th July
eMED3 (fit notes) | Ability to issue fit notes within an EMIS Clinical Service. | This functionality is not currently available. | Making this functionality available would increase the scope of what the PCN Hub can deal with, and reduce the amount of work that has to be sent back to constituent practices for completion. | This functionality is now in pilot at Folkestone, Hythe and Rural PCN. Pending outcome of pilot this functionality will be available to other EMIS Clinical Service customers. | 2023-05-25 | Pilot succesful - functionality rolled out 13th July | 14th July
Integrated eRS (Electronic Referral Service) | Ability to use integrated e-RS functionality within EMIS Clinical Service at PCN Hub level. | This functionality is not currently available. | Making this functionality available would increase the scope of what the PCN Hub can deal with, and reduce the amount of work that has to be sent back to constituent practices for completion. | EMIS testing of this functionality scheduled for June 2023. | 2023-05-25 | Testing complete and with a few minor tweaks we can enable outbound eRS referrals. Will require pilot to test functionality and how useful this can be for PCN working | 14th July
EPS - Service Level Prescribing | Ability to prescribe via EPS at service, rather than organisational level. | This functionality is not currently available. | Making this functionality available within the PCN Hub would enable better management of service level prescribing and the ability to issue prescriptions by service electronically. | Awaiting confirmation from EMIS as to whether this functionality is already available, or if not when it will be developed. | 2023-05-25 | This is available - EMIS AD to get in touch. | 14th July
ICB Level Shared Care Record Solution | Integration of ICB shared care record solution into an EMIS Clinical Service. | The Kent and Medway ICB strategic care record solution, Graphnet, is not accredited for use within an EMIS Clinical Service. | To provide the most informed care a user of PCN Hub should have access to the shared care record at the same level that they have within the EMIS Web system. | Update received from Graphnet stating that "[...] in the final stages of Accreditation with the EMIS partners team. [...] we are finalising providing the last set of documentation to EMIS after which EMIS will submit for final signoff. [...] unable yet to give you a final ETA but good progress is being made." | 2023-05-26 | Graphnet are in final stages. The ball is in their court in terms of documentation. | 14th July
EMIS Enterprise, Search & Reports patient sharing preferences | This system has been purchased on the basis that it will allow searches to be run at a PCN level. | If a patient registered at one of the constituent PCN practices has opted out of sharing their healthcare record with ‘third parties,’ they will not be pulled through to the results of PCN Enterprise level searches. The same applies for EMIS-to-EMIS care record sharing between PCN practice and PCN Hub. | There needs to be an enhancement that allows a sharing preference on the GP record to be set on an organisational basis to allow for better patient management within a PCN operating model. | Is listed as a potential enhancement by EMIS but currently no timescales available as will be a significant piece of development work. | 2023-05-26 | FHR comment applies. Known gap. | 14th July
Consultation Write Back - duplicate entries | Ability to hide duplicate entries that occur because of consultation write back. | Viewing ‘All’ records within EMIS leads to multiple duplicate entries, making navigation of the combined record inefficient. | Removing duplicate entries in care record view would make it much easier for a user to navigate. | Currently scheduled for EMIS review Q3/4 2023. | 2023-05-25 | Q4 dev candidate. | 14th July
ICE test requests | Replacement test request system that is currently being deployed across Kent and Medway. Integrates with EMIS Web. | This system is not currently accredited for EMIS Clinical Service. | If this system was accredited for use within an EMIS Clinical Service there would be an opportunity for a PCN Hub to raise test requests, with the results being sent back to the registered GP practice. | EMIS has confirmed that ICE can currently be configured into an EMIS Clinical Service. Now awaiting confirmation that the configuration to allow results to be sent back to GP practice is available for implementation. | 2023-05-25 | This functionality is possible depending on ICE version - this isnt a dependency on EMIS. | 14th July
GP Connect Appointment Booking | GP Connect booking from practice to Hub as an alternative to EMIS to EMIS cross organisational appointment booking, | Currently not able to differentiate between hub appointments delivered at multiple locations. If a user were to look for a Hub appt via GP Connect, the registered address of the PCN is displayed rather than the location where the appt will be delivered. | In order to safely utilise GP Connect booking functionality the 'location' address needs to refer to the location from which the service is being provided, not the registered address associated with the organisation. This will cause confusion to the end user as will not be directed to the appropriate location for the service required. There is a risk that a patient will be booked into an appointment at one location but be provided with the address of another (the registered location of the PCN). | Some interface improvements have been implemented. Now awaiting meeting with relevant EMIS Product Manager to progress final requirements. Enhancements are limited by national specification. | 2023-05-25 | EMIS to set up meeting with relevant stakeholders. | 14th July
GP Connect Appointment Booking | GP Connect booking from practice to Hub as an alternative to EMIS to EMIS cross organisational appointment booking, | Currently not able to target specific service in the Hub when searching for an appointment. Standard for sending appt availability does not include a service field in the development nor is there a requirement to look at national specification for this. | This will support automated patient registration in the PCN Hub as a GP Connect booking will register the patient, rather than relying upon a manual patient trace. | Some interface improvements have been implemented. Now awaiting meeting with relevant EMIS Product Manager to progress final requirements. Enhancements are limited by national specification. | 2023-05-25 | EMIS to set up meeting with relevant stakeholders. | 14th July
Management of existing medications on GP record | Staff consulting within the PCN require the ability to manage existing medications on the GP record. | At present, the operating model will allow the issuing of a new prescription but not the management of an existing medication on the GP record. | If a patient consultation is being recorded in the EMIS Clinical Service, and an amendment to an existing repeat prescription is required, there is currently no option other than either tasking this back to the practice or issuing a new repeat and requesting that the practice close the existing repeat. This is not a safe or efficient way of working. there is a risk that multiple repeat prescriptions will be open on the patient record. | Nature of the scope of the current pilot that is being provided does not include repeat prescriptions - minor illness focus with acute prescribing only. FH&R are not looking for this functionality to be in place. However, for those PCNs that are looking to provide GP led consultation with a wider scope than minor illness, this functionality gap will become an issue. EMIS Update: At current not possible to deliver in this model setup. | 2023-05-25 | FHR comment applies. Known gap. | 14th July
Providers outside of general practice with capability to utilise Consultation Write Back | Providers other than the GP practices theoretically have the capability to be able to write back into the patient record under consultation write back - this would present as GP activity in the record, via patient access as well as in any local reports or national extracts from the GP system. | Multiple providers would theoretically be entering content and prescribing that has not come from the practice itself, yet it looks as if it was delivered by the practice. Legal position needs addressing, and practices need to understand the implications of activating consultation write back. | To ensure the integrity of the GP record the provision of consultation write back must be more closely managed. It is recommended that any consultation write back deployment be authorised via an ICB level process. | Potential issues rasied with NHSE, EMIS and Kent and Medway ICB. | 2023-07-17 | Currently no "EMIS Community" organisations will be setup by Deployment. There are however legacy clinical services that have requested we enable CWB. Action - EMIS to update guidance with specific/ explicit implications of doing so. | 14th July
EMIS to EMIS sharing agreement and ARRS role profiles | EMIS to EMIS sharing agreements enable functionality such as the sharing of care records between the constituent practices and the EMIs Clinical Service. | New ARRS role profiles have been added to the EMIS Web and EMIS Clinical Service systems. Any EMIS to EMIS sharing agreements that were in place before these roles were released will cease to function for any users that have been assigned an ARRS role profile. This is because when sharing agreements were originally set up the EMIS ARRS role profiles did not exist, so are not in the list of roles that are permitted to utilise the functionality. | ARRS roles require access to system functionality that is equivalent to that of other national role profiles within the system. | Logged worth EMIS in January, now open under ticket CS1102577 and yet to be resolved. | 2023-05-25 | EMIS have reviewed with IG/ Deployment - awaiting next step for identification and update of other "All roles" sharing agreements. | 14th July
EMIS Enterprise Appointment Bookings | The EMIS Consultation Write Back technical data sharing agreement sits within an EMIS Enterprise appointment sharing agreement. | If a practice makes an EMIS Enterprise appointment booking (from practice to hub) the EMIS Clinical Service assumes that an Enterprise, consultation is going to be conducted (even though in this model the patient is going to be 'traced' into the system, with the consultation occurring within the EMIS Clinical Service. This means that when the clinician that is consulting in the hub uses the 'Call in' functionality within the appointment book a remote, or Enterprise, consultation is automatically initiated. | The automatic triggering of an Enterprise, consultation in this scenario causes two issues. Firstly, the clinician has to wait for the Enterprise consultation to open, which can take a considerable amount of time, before closing it. Secondly, for new staff in particular, there is a risk that the consultation will be entered directly into the practice record. This will cause significant issues if the user attempts to prescribe as EPS is not available within an Enterprise consultation. If multiple Enterprise consultations are initiated there is a higher risk that the system will crash. | No current solution identified. GP Connect appointment booking does not cause this issue, but EMIS to EMIS appointment booking functionality still offers more functionality in this PCN Hub approach. | 2023-06-14 | Will be mitigated by new PCN DSA type. | 14th July
EMIS Patient record sharing preferences. | EMIS Web provides the functionality to set a patient's record sharing preferences. | When a patient's record in a practice EMIS Web system has a sharing preference of 'Patient does not wish to share the detailed record' it is not visible to users of the EMIS Clinical Service via the shared care record technical data sharing agreement. | If a patient is consulted with within the EMIS Clinical Service the clinician needs to access the patient's GP record in order to deliver an informed consultation. | No current solution identified. Organisation level sharing preferences not currently available within EMIS Web and there are no plan to enhance EMIS sharing preferences functionality at present. The current workaround is for the user to initiate an Enterprise consultation, if the patient was booked into the EMIS Clinical Service by a practice. Alternatively the user would need to log directly into the practice EMIS Web system where the patient is registered in order to view the patient's care record. | 2023-06-14 | FHR comment applies. Known gap. | 14th July