## Plan
Draft CCG SDM Implementation Project Plan |  |  | 2013-01-01
Workstream | Task | Responsible | 2013-01-07 | 2012-01-14 | 2012-01-21 | 2012-01-28
Coordination, Leadership and Stakeholder Support | Agree project lead and clinical lead/s
Agree first draft of project plan
Finalise stakeholders lists for pathways and agree communications strategy i.e. How, what and when
Letter to main providers regarding SDM and request meeting with clinical lead
Project Board/ Group meetings
Briefing for lead/s
Briefing for Health and Social Care Board
Briefing for Local Healthwatch
Engaging Patients and Carers | Agree general and pathway specific patients and user groups to inform about SDM
Link SDM to local patient engagement strategy and other patient involvement work
Engagement with voluntary sector and disease specific support groups
Agree patient role in awareness raising/ training clinical teams
Engaging Staff | Agree team to undertake awareness raising/ training
Agree information to be shared with clinical teams regarding SDM (presentation agreed by project team)
Agree format of Primary Care SDM awareness raising/ training package
Agree contributors and content for training
Training content available to teams virtually
Arrange SDM awareness raising events/ briefings
Resources | Ensure links in place for information system enablers for SDM in primary care and secondary care
Briefing on SDM included in staff communication/ intranet
Agree hard copy resources e.g. Promotional material required for primary care, community and secondary care services
Link SDM into local Choose and Book systems/ Referral proforma
Link SDM to local referral forms
Securing and Sustaining Change | Agree SDM into acute and community contracts
Review of QOF QP/ LES
Review of CQUIN
Agree SDM implementation in other pathways/ next wave
Evaluation | Agree evaluation methods for projects
Local evaluation/ case study completed
Note on B29: For example, including Shared Decision Making Sheets, in localised pathway maps, map of medicine, GP intranet.
Note on B46: For example, qualitative or quantitative methods or both. To understand the acceptability and impact of SDM in practice, among both patients and clinicians you may want to use interviews as part of your evaluation. To evaluate decision quality and decision readiness the SURE score can be used. To understand the impact of SDM in terms of intervention rates and treatments then quantitative analysis using activity data would be useful as an evaluation method.
Note on D1: Add in dates in lime with local implementation