## Guide
NHS England Specialised Services Policy Pipeline
Last updated: 17/07/26
Guide (click to be directed to the relevant tab):
What's new: Additions and changes to draft clinical commissioning policy titles since the previous policy pipeline update are highlighted here. Please note that status changes are not reported here.
Work programme: Details of draft clinical commissioning policies under development, including where development has been paused or stopped.
Paused policies: Details of why draft clinical commissioning policies have been paused.
Stopped policies: Details of why draft clinical commissioning policies have been stopped since April 2020.
Published Policies: Details of policies which have been published since April 2020
Rejected Preliminary Policy Proposals: Details of Preliminary Policy Proposals which have been submitted and considered by Specialised Services Clinical Panel. Clinical Panel has agreed that these topics will not be added to the work programme.
Key to the work programme:
ID: Each draft clinical commissioning policy has a unique reference number. These are numbered sequentially across both clinical commissioning policies and service specifications.
Type: Identifies whether the document is a full clinical commissioning policy or an interim clinical commissioning policy statement.
Title: The draft clinical commissioning policy title.
NPoC: Outlines which Programme of Care the draft clinical commissioning policy falls under: Internal Medicine, Cancer, Mental Health, Trauma, Women & Children or Blood & Infection.
Status: The following status options are available:
-Added to work programme
-Evidence review in progress
-Policy proposition in progress
-Stakeholder testing in progress
-Impact assessment in progress
-Public Consultation in progress
-Awaiting CPAG meeting/ prioritisation meeting/ prioritisation meeting outcomes
-Awaiting publication
-Policy Published
NB. Where draft policies are paused or stopped, these will be marked and further details are provided on the 'Paused policies' or 'Stopped policies' tabs.
Target: This is the target date at which the draft clinical commissioning policy is likely to be considered by CPAG. If the draft clinical commissioning policy is likely to be considered as an In-Year Service Development, the policy will be marked as IYSD Potential until completion of the Impact Assessment when this can be confirmed. The target date may change and where this is the case, it will be marked on 'What's New'.

## What's New
As of 23/03/2026 | Type | Title
2606 | Policy | Tocilizumab in the treatment of patients of all ages with Relapsing Polychondritis not responsive to conventional therapies
2607 | Policy | Trastuzumab for human epidermal growth factor receptor 2 positive (HER2-positive) salivary gland cancer (adults)

## List (hidden)
Added to work programme
Evidence review in progress
Policy proposition in progress
Stakeholder testing in progress
Impact assessment in progress
Consultation in progress
Awaiting CPAG meeting
Awaiting approval by SCOG
Policy Published
Paused
Stopped
In progress via CSP
2017/18 Q3/4 | #REF!
2018/19 Q1/2 | #REF!
2018/19 Q3/4 | #REF!
2017/2018 IYSD | #REF!
2017/18 IYSD Potential | #REF!
2018/19 IYSD Potential | #REF!
2017/18 IYSD | #REF!
2018/19 IYSD | #REF!
Not applicable | #REF!
TBC | #REF!

## Work Programme
As of 17/07/2026
ID | Intervention | Indication | NPOC | Product | Status
1871 | Gondal and genital surgery | for infants and children with differences in sex development (DSD) | Women & Children | Policy | Awaiting public consultation
2122 | Pre-implantation Genetic Testing | of embryos at significant risk of serious genetic conditions | Women & Children | Policy | Awaiting publication
2318 | Vemurafenib and Rituximab | for the treatment of BRAF-mutated classic hairy cell leukaemia for classic hairy cell leukaemia with BRAF mutation (adults) | Cancer | Policy | Awaiting publication
2337 | Pasireotide pamoate long-acting repeatable (LAR) injection | for the management of acromegaly (adults) | Internal Medicine | Policy | Awaiting Publication
2406 | Thalidomide | to treat patients with arteriovenous malformations (AVMs) of in adults | Internal Medicine | Policy | Policy Proposition in progress
2408 | Regional nerve graft | for corneal denervation (neurotrophic keratopathy) (all ages) | Trauma | Policy | Awaiting CPAG meeting
2415 | Trametinib | for BRAF wild-type histiocytic neoplasms (all ages) | Cancer | Policy | Policy Proposition in progress
2419 | Centrifugal-flow magnetic levitation left ventricular assist devices | as destination therapy in Adults with advanced heart failure | Internal Medicine | Policy | Impact assessment in progress
2421 | Non-invasively lengthened spinal rods | for scoliosis | Trauma | Policy | Policy Proposition in progress
2422b | Octreotide | for polycystic liver disease (PLD) | Internal Medicine | Policy | Awaiting public consultation
2425 | Cabotegravir and rilpivirine treatment | of HIV-1 where licence conditions are not met | Blood & Infection | Policy | Policy Proposition in progress
2426 | Neoadjuvant adjuvant Pembrolizumab | for the treatment of macroscopic resectable stage III melanoma | Cancer | Policy | Awaiting CPAG meeting
2427 | Phrenic nerve pacing | for congenital central hypoventilation syndrome | Internal Medicine | Policy | Awaiting publication
2417 | Feminising medicines | in the management of gender incongruence | Gender | Policy | Policy Proposition in progress
2602 | Masculinising medicines | in the management of gender incongruence | Gender | Policy | Policy Proposition in progress
2501 | Melphalan via percutaneous hepatic perfusion | Melphalan via percutaneous hepatic perfusion for unresectable or non-ablative liver dominant metastatic uveal melanoma | Cancer | Policy | Impact assessment in progress
2502 | Selective internal radiation therapy (SIRT) | for neuroendocrine tumours (NETS) that have metastasised to the liver | Cancer | Policy | Impact assessment in progress
2504 | Recombinant von Willebrand factor (vonicog alfa) | Recombinant von Willebrand factor (vonicog alfa) long term prophylaxis in von Willebrand disease (VWD) | Blood & Infection | Policy | Policy Proposition in progress
2505 | Plerixafor | for stem cell mobilisation in allogeneic stem cell transplant donors | Blood & Infection | Policy | Policy Proposition in progress
2526 | Eculizumab | for the treatment of transplant associated thrombotic microangiopathy (TA-TMA) in allogenic stem cell recipients | Blood & Infection | Policy | Policy Proposition in progress
2527 | Lutetium (177Lu) oxodotreotide | for malignant and inoperable phaeochromocytoma and paragangliomas | Cancer | Policy | Impact assessment in progress
2529 | Caplacizumab with plasma exchange and immunosuppression | for treating acute acquired thrombotic thrombocytopenic purpura in young people who either weigh less than 40 kg or are under 12 years old | Blood & Infection | Policy | Impact assessment in progress
2530 | Renal denervation | for resistant hypertension | Internal Medicine | Policy | Policy Proposition in progress
2532 | Cochlear implantation | in single sided deafness | Trauma | Policy | Policy Proposition in progress
2533 | Bictegravir/emtricitabine/tenofovir alafenamide | for adults with HIV-1 | Blood & Infection | Policy | Policy Proposition in progress
2535 | Use of emicizumab prophylaxis | to reduce spontaneous bleeding in people with acquired Haemophilia A | Blood & Infection | Policy | Policy Proposition in progress
2536 | Transcatheter edge-to-edge repair of severe tricuspid regurgitation | in patients who remain symptomatic despite optimal medical therapy | Internal Medicine | Policy | Policy Proposition in progress
2537 | Miglustat | for tangier disease | Women & Children | Policy | Policy Proposition in progress
2538 | Feminising and masculinising medicines | in the management of gender incongruence (children and young people) | Gender | Policy | Post Public Consultation Amends in progress
2539 | Transcatheter Aortic Valve Implantation (TAVI) | for aortic valve disease | Internal Medicine | Policy | Evidence review in progress
2601 | Paclitaxel albumin (nab-paclitaxel) | for gynaecological cancers | Cancer | Policy | Policy Proposition in progress
2603 | Mitochondrial Donation | to Prevent Transmission of Mitochondrial DNA Disease (adult) | Women & Children | Policy | Evidence review in progress
2604 | Total Pancreatectomy and Islet Auto-transplantation (TPIAT) | in Children (children and young adults) | Women & Children | Policy | Evidence review in progress
2605 | Second allogeneic haematopoietic stem cell transplant | for relapsed disease (all ages) | Blood & Infection | Policy | Added to work programme
2606 | Tociliziumab | in the treatment of patients of all ages with Relapsing Polychondritis not responsive to conventional therapies | Internal Medicine | Policy | Added to work programme
2607 | Trastuzumab | for human epidermal growth factor receptor 2 positive (HER2-positive) salivary gland cancer (adults) | Cancer | Policy | Added to work programme

## Paused policies
As of 17/07/2026
ID | Type | Title | NPoC | Reason
2407 | Vedolizumab | for pre-pubescent children with Inflammatory Bowel Disease (all ages) | Women & Children | A trial for the population is currently underway.
2254 | Transcatheter Edge to Edge Repair (TEER)/percutaneous mitral valve leaflet repair | for secondary mitral regurgitation | Internal Medicine | The policy was initially submitted to CPAG for consideration in May 2024; however, it was not prioritised at that time. The clinical lead has requested an opportunity to review and update the documentation ahead of a future resubmission to CPAG. Consequently, the policy has been placed on hold pending completion of this review.

## Stopped policies
From 01/04/2026-Present
ID | Type | Title | Status | Reason
2534a | Proton Beam Therapy | in pregnancy | Cancer | Due to insufficient evidence, it has been decided that further research is required
2534b | Proton Beam Therapy | in gastro-oesophageal cancers | Cancer | Due to insufficient evidence, it has been decided that further research is required
2409 | Rituximab | Rituximab for first line treatment of aquaporin-4 antibodies (AQP4-IgG) positive neuromyelitis optica spectrum disorder (NMOSD) | Trauma | Rituximab has been removed from the NHS Payment Scheme (Annex A; high-cost drugs) and is now included in tariff; consequently, a clinical commissioning policy is not required for its use.
2410 | Rituximab | for the treatment of Chronic inflammatory demyelinating polyradiculoneuropathy (CIDP) (all ages) | Trauma | Rituximab has been removed from the NHS Payment Scheme (Annex A; high-cost drugs) and is now included in tariff; consequently, a clinical commissioning policy is not required for its use.
2528 | Intravitreal Cerliponase alfa | for the treatment of CLN2 Battens disease related retinal dystrophy | Women & Children/ Trauma | The policy proposition was paused on the 22/07/2025 until the publication of Highly specialised technologies (HST) guidance 12: cerliponase alfa for treating neuronal ceroid lipofuscinosis type 2. The HST is for the administration of an infusion via a surgically implanted intracerebroventricular (ICV) access device. NICE HST34 was published on 18 February 2026 and does not recommend cerliponase alfa. The PPP proposed that patients would only receive intravitreal cerliponase alfa if they are also receiving it via the ICV route. This policy proposition is being stopped as the starting criteria of receiving cerliponase alfa via an ICV is not commissioned.

## Published policies
From 01/04/2026-Present
ID | Type | Title | NPOC
2338 | Mercaptamine bitartrate | for the treatment of nephropathic cystinosis (all ages) | Internal Medicine
2341 | Prolonged-released (PR) fampridine | as a treatment of adults with Multiple Sclerosis and associated walking impairment | Trauma
2342 | Gamma Knife Stereotactic Radiosurgery | for essential tremor (adults) | Trauma/Cancer
2344 | Lenacapavir for the treatment | of multi-drug resistance HIV-1 infection (adults) | Blood & Infection
2402 | Lonafarnib | for Hutchinson-Gilford Progeria Syndrome and Progeroid Laminopathies (all ages) | Women & Children
2404 | Bendamustine and brentuximab vedotin | in relapsed/refractory Hodgkin lymphoma (all ages) | Cancer
2316 | Sirolimus | for treatment of complicated and symptomatic congenital vascular malformations (CVMs) | Internal Medicine
2330 | Crizotinib paediatric anaplastic lymphoma | for positive anaplastic large cell lymphoma | Cancer
2331 | Osilodrostat phosphate | an oral medical therapy for the management of endogenous Cushing’s syndrome in adults | Internal Medicine
2332 | Stereotactic Ablative Radiotherapy (SABR) | for patients with localised, non-metastatic, renal cancer who are medically unfit for surgery (adults) | Cancer
2121 | Obinutuzumab | or systemic lupus erythematosus with secondary non-response to rituximab (adults and post-pubescent children) | Internal Medicine
2206 | Direct skeletal fixation | for transfemoral limb loss (adults) | Trauma
2268 | Dabrafenib | for histiocytic neoplasms with BRAFV600E mutation (all ages) | Cancer
2269 | Vismodegib | for locally advanced BCC as a neoadjuvant to definitive treatment (surgery or radiotherapy) for lesions likely to result in significant functional or aesthetic sequalae (adults) | Cancer
2309 | Abatacept | for for autoimmune complications of primary immune deficiency disorders (adults and children over 2 years) | Blood & Infection
2418 | Pembrolizumab | in combination with dabrafenib & trametinib for BRAF mutated anaplastic thyroid cancer (All ages) | Cancer
2422a | Lanreotide | for polycystic liver disease (PLD) | Internal Medicine
2423 | Gemcitabine-Nab-Paclitaxel combination chemotherapy | for the treatment of locally advanced non-metastatic pancreatic cancer (LANPC) | Cancer
2106 | Stereotactic ablative radiotherapy (SABR) | for the treatment of localised prostate cancer (adults) | Cancer
2426 | Neoadjuvant adjuvant Pembrolizumab | for the treatment of macroscopic resectable stage III melanoma | Cancer

## PPPs not supported
From April 2016-Present
ID | Intervention | Indication | NPOC | Date not supported
P0032/16 | Alemtuzumab | Prevention and treatment of rejection in kidney transplantation | Internal Medicine | 2016-04-13
P0033/16 | Cochlear implants | Tinnitus | Trauma | 2016-04-13
P0034/16 | Percutaenous cervical cordotomy | Cancer Pain | Trauma | 2016-04-13
P0035/16 | Gamete tissue cryoperservation | Children under the age of 18 undergoing cancer treatment for future fertility treatment | Cancer | 2016-04-13
P0036/16 | Intrathecal drug delivery | Chronic non-cancer pain | Trauma | 2016-04-13
P0037/16 | Metreleptin | Lipodystrophy | Women & Children | 2016-04-13
P0050/16 | Gemcitabine and capecitabine chemotherapy | for the adjuvant treatment of pancreatic cancer | Cancer | 2016-09-21
P0060/16 | Peptide receptor radionucleotide therapy | Metastatic neuroendocrine tumours that have radiological, biochemical and symptomatic signs of progression | Cancer | 2016-10-19
P0072/16 | Lumacaftor/ivacaftor | Indicated and licensed patients as per the SMC | Internal Medicine | 2016-11-15
P0052/16 | Pembrolizumab | Metastatic merkel cell carcinoma | Cancer | 2016-11-16
P0061/16 | Provision of eculizumab | Adult patients who have biopsy-proven Cg3 and acute kidney injury | Internal Medicine | 2016-12-20
P0002/17 | Bendamustine monotherapy as a treatment option | Relapsed or refractory Hodgkin lymphoma | Cancer | 2017-03-14
P0018/17 | Haemopoietic stem cell transplantation | Inborn errors of metabolism | Blood & Infection | 2017-06-21
P0074/16 | Long term red cell blood transfusion programmes | Sickle cell disease (primary and secondary prevention of complications) | Blood & Infection | 2017-09-20
P0024/17 | Fluciclovine | Imaging recurrent prostate cancer | Cancer | 2017-09-20
P0027/17 | Bevacizumab | Platinum resistant ovarian cancer | Cancer | 2017-10-18
P0031/17 | 68Ga-PSMA PET use | Patients with prostate cancer | Cancer | 2017-10-18
P0043/17 | Dinutuximab beta | first-line treatment for high-risk neuroblastoma | Cancer | 2017-11-15
P0025/17 | Sapropterin | Phenylketonuria | Women & Children | 2017-12-19
P0051/17 | Use of TNF blockers | Osteomyelitis (CRMO) | Women & Children | 2017-12-19
P0067/17 | Anti-TNF alfa | Deficiency of adenosine deaminase 2 (DADA2) causing inflammatory vasculitis or other disease | Women & Children | 2018-01-17
P0077/17 | Sapropterin | Phenylketonuria | Women & Children | 2018-01-17
P0003/18 | Somatostatin analogues | Growth hormone excess in children | Women & Children | 2018-02-21
P0006/18 | Stem cell transplantation | Adults with sickle cell disease | Blood & Infection | 2018-02-21
P0061/17 | Laser interstitial thermal therapy | Refractory focal epilepsy suitable for ablation, not suitable for conventional neurosurgery | Trauma | 2018-03-21
P0034/18 | CHOEP chemotherapy | First line peripheral T cell lymphoma | Cancer | 2018-05-09
P0058/18: | Efmoroctocog alfa | for treatment and prophylaxis of bleeding in patients with haemophilia A (congenital factor VIII deficiency) | Blood & Infection | 2018-09-18
P006918 | Tenofovir alafenamide | Patients infected with hepatitis B virus | Blood & Infection | 2018-11-21
P0033/18 | Amyloid PET | in in patients with atypical dementia in whom a differential diagnosis of Alzheimer's disease (AD)or an inflammatory disorder is considered | Trauma | 2018-12-12
P0092/18 | High dose Alglucosidase alfa enzyme replacement therapy (ERT) | for Infantile Onset Pompe Disease (IOPD) | Women & Children | 2018-12-12
P0063/18 | Tecfidera (dimethyl fumarate) | for use in Relapsing Remitting Multiple Sclerosis patients switching from first line DMTs for efficacy reasons | Trauma | 2019-01-16
P0011/19 | Dolutegravir 50mg / lamivudine 300mg is a fixed dose tablet | for the treatment of Human Immunodeficiency Virus (HIV) infected adults and adolescents | Blood & Infection | 2019-04-17
P0045/19 | Use of ultra-hypofractionation | hypofractionation in men with low or intermediate risk localised prostate cancer is hypofractionated radiotherapy using 5 or 7 treatments as effective as longer schedules | Cancer | 2019-11-20
P0034/19 | Burosumab | use in children and young people with well-defined rare monogenic conditions when there is demonstrable bone disease/rickets due to hypophosphataemia- | Cancer | 2019-11-20
P0037/19 | Stereotactic Gene Therapy | for aromatic L-amino acid decarboxylase deficiency | Women & Children | 2019-12-18
P0053/19 | Post-operative contact X-ray brachytherapy (Papillon) | for early rectal cancer within a malignant polyp following incomplete local surgical resection or complete surgical resection in polyps with adverse (high risk) features, in patients who are not suitable for completion surgical resection | Cancer | 2020-07-15
P0058/19 | Omalizumab | for treatment of severe sight threatening allergic eye disease in children and young people | Trauma | 2020-09-16
P0024/20 | Idebenone for the treatment of Leber's Hereditary Optic Neuropathy | for the treatment of Leber's Hereditary Optic Neuropathy | Trauma | 2021-01-20
P100/21 | Medicinal cannabis based treatments | for Refractory epilepsy | Women & Children | 2021-03-17
PRN19/21 | Sacituzumab govitecan for the treatment of metastatic triple-negative breast cancer (mTNBC) who have received at least 2 prior therapies | for the treatment of metastatic triple-negative breast cancer (mTNBC) who have received at least 2 prior therapies | Cancer | 2021-05-19
PRN100/20 | Surgical Insertion of Gastric Electrical Stimulator (Enterra II) | for the treatment of refractory Gastroparesis | Internal Medicine | 2021-05-19
PRN20/21 | Bulevritide | for the treatment of chronic hepatitis delta virus infection in adult patients with advanced liver fibrosis at risk of imminent harm | Blood & Infection | 2021-08-18
PRN24/21 | Brentuximab vedotin 12 months maintenance monotherapy | for the treatment of relapsed/refractory paediatric Hodgkin's Lymphoma | Cancer | 2021-09-15
P0052-21 | Amyloid PET | in Alzheimer's disease | Trauma | 2021-11-22
P022-19 | Adalimumab | for the treatment of neurosarcoidosis | Trauma | 2021-11-22
PRN18-21 | Use of tamoxifen | to prevent breast cancer | Cancer | 2021-11-22
PRN30-21 | Use of caplacizumab | in children < 12 years old in acute TTP | Blood & Infection | 2021-11-22
PRN2-21 | Bevazicumab, irinotecan and temozolomide | for children and child people with relapsed or refractory neuroblastoma | Cancer | 2022-01-31
PRN15-21 | Oncotype DX Breast Recurrence Score® test |  | Cancer | 2022-02-08
PRN23/21 | Human cytomegalovirus immunoglobulin | for the prophylaxis of clinical manifestations of CMV disease in immunosuppressed individuals in heart and/or lung transplant patients | Internal Medicine | 2022-02-16
PRN32/21 | Flourine-18 labelled Choline (FCH) Positron Emission Tomography/Computed Tomography (PET/CT) | in patients with primary hyperparathyroidism (adults) | Cancer | 2022-03-16
PRN45/21 | Deferiprone | treatment in patients with superficial siderosis | Trauma | 2022-05-18
P028/20 | Treatment pathway | for relapsed amyloid light-chain (AL) amyloidosis with anti-myeloma drugs approved in the NICE clinical algorithm. | Cancer | 2022-05-23
PRN55-21 | Gonadotrophin therapy | to stimulate spermatogenesis in men with hypogonadotrophic hypogonadism (HH) | Internal Medicine | 2022-06-08
PRN5/22 | Vemurafenib | for BRAFV600E mutated histiocytic neoplasms | Cancer | 2022-06-15
PRN8/22 | Cobimetinib | for BRAFV600E mutated histiocytic neoplasms | Cancer | 2022-06-15
PRN26-22 | Belumosudil 200mg oral tablets | as treatment of patients aged 12 years and older with chronic graft-versus-host disease (chronic GVHD) who have received at least two prior systemic therapies | Blood & Infection | 2022-11-15
PRN36-21 | Advanced Pelvic Exenteration surgery | for complex pelvic cancers | Cancer | 2022-11-15
PRN38-22 | Ziconotide (intrathecal delivery) | for chronic cancer pain | Trauma | 2023-01-04
PRN5-22 | Vemurafenib | for BRAFV600E mutated histiocytic neoplasms | Cancer | 2023-01-18
PRN8-22 | Cobimetinib | for histiocytic neoplasms | Cancer | 2023-01-18
PRN2-23 | Restarting androgen receptor targeted inhibitors | in metastatic prostate cancer | Cancer | 2023-05-12
PRN1-23 | Eptacog alfa (Cevanfacta) | for treatment and prevention of bleeding in congenital bleeding disorders | Blood & Infection | 2023-09-20
PRN21-21 | Growth Hormone for Growth Failure | due to noonan syndrome | Women & Children | 2023-09-20
PRN37-21 | Rituximab | for children under the age of 12 years with relapsing remitting multiple sclerosis | Women & Children | 2023-09-20
PRN41-22 | Uridine monophosphate | for CAD trifunctional protein deficiency related disorders | Women & Children | 2023-09-20
PRN59-22 | Everolimus and low dose tacrolimus | for immunosuppression in patients undergoing liver transplantation for neuroendocrine tumour liver metastases | Internal Medicine | 2023-09-20
PRN15-23 | Home use of Real-Time Continuous Glucose Monitoring | for infants/children/adults with Congenital Hyperinsulinism who have limited fasting tolerance (not appropriate for their age), requiring overnight continuous enteral glucose delivery via a gastrostomy and overnight feed pump | Women & Children | 2023-10-23
PRN38-23 | Improving metastatic colorectal cancer survival through combining Bevacizumab biosimilars with chemotherapy treatments |  | Cancer | 2023-11-02
PRN15-23 | Home use of Real-Time Continuous Glucose Monitoring | for infants/children/adults with Congenital Hyperinsulinism who have limited fasting tolerance (not appropriate for their age), requiring overnight continuous enteral glucose delivery via a gastrostomy and overnight feed pump | Women & Children | 2023-11-15
PRN56-21 | Home use of subcutaneous Octreotide administration via a continuous infusion pump (CSII) | in children with Congenital Hyperinsulinism | Women & Children | 2023-11-15
PRN38-23 | Bevacizumab biosimilars with chemotherapy treatments | for improving metastatic colorectal cancer survival | Cancer | 2023-11-15
PRN4-22 | Bevacizumab | in platinum resistant ovarian cancer | Cancer | 2023-11-15
PRN47-21 | Cytoreductive surgery with Heated Intra-peritoneal Chemotherapy | for Peritoneal Mesothelioma | Internal Medicine/Cancer | 2024-01-17
PRN39-23 | Emicizumab | for prevention of bleeding in people with type 3 Von Willebrand Disease | Blood & Infection | 2024-02-21
PRN26-22 | Belumosudil | for chronic graft-versus-host disease (cGVHD) | Cancer/Blood & Infection | 2024-03-13
PRN60-21 | Prophylactic antiviral therapy | for all cancer patients at risk of hepatitis B virus reactivation undergoing chemotherapy or immunosuppressive regimens | Cancer | 2024-03-17
PRN32-23 | Measurement of liver iron concentration | using the standardised spin-density-projection-assisted proton transverse relaxometry magnetic resonance imaging method | Blood & Infection | 2024-04-08
PRN52-22 | L-threo-dihydroxyphenylserine (l-threo-DOPS; droxidopa) | for the treatment of neurogenic orthostatic hypotension (nOH) | Trauma | 2024-04-08
PRN5-24 | Tumour Treating Fields | for the treatment of newly diagnosed WHO grade 4 glioma (glioblastoma multiforme) | Cancer | 2024-06-05
PRN39-22 | Tocilizumab retreatment | for a new giant cell arteritis relapse (adults) | Internal Medicine | 2024-07-22
PRN62-23 | Stratified treatments | in multiple myeloma | Cancer | 2024-07-23
PRN50-23 | Pomalidomide (generic) combination therapies | as a treatment option in second or third line for relapsed multiple myeloma (MM) patients | Cancer | 2024-07-25
PRN43-24 | Pembrolizumab | in combination with lenvatinib for BRAF wild-type anaplastic thyroid cancer | Cancer | 2024-08-21
PRN30-23 | Chronic Kidney Disease-specific | digital rehabilitation and self-management solutions | Internal Medicine | 2024-08-21
PRN65-23 | Use of anakinra | in colchicine refractory idiopathic recurrent pericarditis | Internal Medicine | 2024-09-18
PRN69-23 | Renal Hypertension | for resistant hypertension | Internal Medicine | 2024-09-18
PRN8-24 | Vertebral Body Tethering (VBT) for scoliosis | for scoliosis | Trauma | 2024-10-16
PRN70-23 | Infliximab | for refractory or relapsing Cogan's syndrome (all ages) | Internal Medicine | 2025-02-19
PRN64-23 | Paclitaxel albumin (nab-paclitaxel) | for ovarian cancer in adult patients who have had a hypersensitivity reaction to paclitaxel | Cancer | 2025-02-19
PRN15-24 | Baricitinib | for treatment of VEXAS (Vacuoles, E1 enzyme, X-linked, Autoinflammatory, Somatic) | Blood & Infection | 2025-03-19
PRN16-24 | Tocilizumab | for treatment of VEXAS (Vacuoles, E1 enzyme, X-linked, Autoinflammatory, Somatic) | Blood & Infection | 2025-03-19
PRN17-24 | Anakinra | for treatment of VEXAS (Vacuoles, E1 enzyme, X-linked, Autoinflammatory, Somatic) | Blood & Infection | 2025-03-19
PRN18-24 | Azacitidine | for treatment of VEXAS (Vacuoles, E1 enzyme, X-linked, Autoinflammatory, Somatic) | Blood & Infection | 2025-03-19
PRN25-22 | Oral cladribine tablets (Mavenclad) | in people with relapsing remitting multiple sclerosis | Trauma | 2025-10-15
PRN19-24 | Reimbursement for the use of generic and second line drugs | for Pre Exposure Prophylaxis (PrEP) for the prevention of HIV | Blood & Infection | 2025-04-30
PRN26-24 | Ovarian cancer surveillance | for women carrying pathogenic germline variants in BRCA1 and BRCA2 who defer or decline risk-reducing surgery | Cancer | 2025-05-19
PRN34-23 | Omalizumab | for the treatment of severe chronic rhinosinusitis with nasal polyps | Blood & Infection | 2025-06-18
PRN42-23 | Bone morphegenic Protein | in treatment of congenital pseudarthrosis | Women & Children | 2025-06-18
PRN11-25 | Mesenchyme or stromal stem cell infusions CordSTROM | for children with recessive dystrophic epidermolysis bullosa | Internal Medicine | 2025-06-18
PRN13-25 | Histotripsy Treatment | in Primary and Secondary Liver Cancers (adults) | Cancer | 2025-06-18
PRN15-25 | Abatacept | for refractory birdshot retinochoroidopathy | Trauma | 2026-05-20
N/A | Oestrogen or testosterone | for patients aged 16-17 year-olds currently on GnRH analogues awaiting masculinising or feminising hormones | Gender | 2026-05-20
PRN23-25 | Balloon Pulmonary angioplasty | for chronic thromboembtic pulmonary hypertensions (Adults) | Blood & Infection | 2026-06-17
PRN25-26 | Uterus transplantation (UTx) | for Absolute Uterine Factor Infertility (AUFI) (all ages) | Women & Children | 2026-07-15