## Cover Sheet
Cover Sheet | SUMMARY SHEET
[11 empty] | IPOS Scores Audit - For Q1 17/18 |  | Quarter 2 2018/19 |  | Quarter 3 2018/19 |  | Quarter 4 2018/19
Provider Code | Cancer Tumour Site | Estimated number of new diagnosis of incurable disease | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis of incurable disease | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis for Period |  |  | Proportion of Deaths within 30 days of Chemotherapy Baseline | Proportion of Deaths within 30 days of Chemotherapy | Change from Expected Rate | IPOS SURVEY (STAFF) AREA | IPOS Scores Audit Taken from a random sample of 10 patients record average IPOS scores from at least 2 visits to supportive care team (1st and at least one follow up)
|  |  | Baseline | Q1 & Q3 | Q3 | Q4 | % | % |  |  | Quarter 1- 2018/19 |  | Quarter 2 - 2018/19 |  | Quarter 3 - 2018/19 |  | Quarter 4 - 2018/19
| Enter Site No.1 Name Cover Sheet | 0 | - | - | - | - | - | - | - |  | 1st | F/U (1) | 1st | F/U (1) | 1st | F/U (1) | 1st | F/U (1)
Provider Name | Enter Site No.2 Name Cover Sheet | 0 | - | - | - | - | - | - | - | Pain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enter Site No.3 Name Cover Sheet | 0 | - | - | - | - | - | - | - | Shortness of breath | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enter Site No.4 Name Cover Sheet | 0 | - | - | - | - | - | - | - | Weakness or lack of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Date | Enter Site No.5 name Cover Sheet | 0 | - | - | - | - | - | - | - | energy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enter Site No.6 name Cover Sheet | 0 | - | - | - | - | - | - | - | Nausea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | - | - | - | - | - | - | - | Vomiting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed By: | [9 empty] | Poor appetite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Constipation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Sore or dry mouth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Email: | [9 empty] | Drowsiness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Potential Value for CQUIN Scheme |  | 0 | [6 empty] | Poor mobility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Has s/he been feeling anxious or worried about his/her illness or treatment? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contact Number: | Quarter 1 |  | 0 | [6 empty] | Have any of his/her family or friends been anxious or worried about the patient? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quarter 2 |  | 0 | [6 empty] | Do you think s/he felt depressed? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quarter 3 |  | 0 | [6 empty] | Do you think s/he has felt at peace? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Authorised by: | Quarter 4 |  | 0 | [6 empty] | Has the patient been able to share how s/he is feeling with his/her family or friends as much as s/he wanted? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Adjustment | [8 empty] | Has the patient had as much information as s/he wanted? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | [6 empty] | Have any practical problems resulting from his/her illness been addressed? (such as financial or personal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Authoriser's Title:

## Guidance
This tool should be used to collect baseline data and return data relevant to each quarters payment trigger within the CA1 Enhanced Supportive Care (for Advanced Cancer Patients) CQUIN. The tool should be completed and returned at end of Q1, Q2 and Q4 to your local specialised Commissioning Team contact for CQUIN.
Please note - The CQUIN document and payment guide are included as tabs 11 and 12 and should be read and understood before completeing this tool.
Tab | Content | Guidance Notes
1 | Total Value of CQUIN | Use this tab to insert the estimated patient population for each of the cancer tumour site groups that the ESC approach is being targeted at, or ,if you are focussing on appropriate patients across your whole cancer population, an estimate of this figure.The total estimated population will drive the total £ value of the CQUIN (as explained in the payment guide included in tab 12)
2 | Baseline Data (1) | Use this tab to record the projects baseline line data for numbers of patients in each chosen cancer tumour site groups that are being offered referral to a supportive care team at point of diagnosis of incurable disease, or where you are offering ESC to appropriate patients across your cancer population, that baseline figure. The numerator - offered referral to the supportive care team data could be accessible through the national Electronic Palliative Care Co-ordination System (EPACCS) if this is being used or through other internal data systems if not. The denominator- Total diagnosis of incurable cancer should be registered through the SACT data-set - roughly as those patients receiving chemo with palliative intent and through other Trusts systems for patients receiving Radiotherapy for palliative intent or no active treatment. Improvement can be measured from this baseline data. Please also state the time period that the baseline data relates to.
3 | ESC principles - description and development of your ESC model | You can use this tab to assess and provide evidence of how your ESC service is meeting the 6 principles of ESC. This information can be updated quarterly if there are changes you want to update on. This information will allow you to assess progress against the 6 principles and provide your Trust and Commissioners with additional evidence of the benefit and impact of ESC. 1. Earlier involvement of supportive care services. 2. Supportive care teams that work together. 3. A more positive approach to supportive care. 4. Cutting edge and evidence-based practice in supportive and palliative care. 5. Technology to improve communication. 6. Best practice in chemotherapy care.
4 | Q1 CQUIN Payment Trigger | Use this Tab to record the outcome of the CQUIN rules that will trigger Q1 payment (refer to tab 12 and 13 for guidance)
5 | Q2 CQUIN Payment Trigger | Use this Tab to record the outcome of the CQUIN payment triggers for Q2 Payment (refer to tab 12 and 13 for guidance)
6 | Q3 CQUIN Payment Tigger | Use this Tab to record the outcome of the CQUIN payment triggers for Q3 Payment (refer to tab 12 and 13 for guidance)
7 | Q4 CQUIN Payment Tigger | Use this Tab to record the outcome of the CQUIN payment triggers for Q4 Payment (refer to tab 12 and 13 for guidance)
8 | Baseline IPOS Survey (if used) | IPOS survey data (or other similar recognised tool) should be collected at point of referral by palliative/supportive care team and then at review. This tab can be used to record the projects baseline data for patient experience / QOL. We are suggesting use of the IPOS (Staff) Tool. If another recognised tool is to be used then the relevant fields will need to be changed on this tab. Record the name of the cancer tumour site group at the top of each column - or use the first column of you are focussing ESC on appropriate patients across your cancer population. For the first quarter, select a random sample of 10 patients from the range of disease sites or your population cohort - as apprioriate, record IPOS scores for at least 2 visits to the supportive care team (1st and at least one follow-up) and record in this tool the average scores across the 10 patients for each visit.
8.1 | IPOS Data Sample Q2 (if used) | Use this tab to record data relating to Patient Experience/QOL scores for Q2
8.2 | IPOS Data Sample Q3 (if used) | Use this tab to record data relating to Patient Experience/QOL scores for Q3
8.3 | IPOS Data Sample Q4 (if used) | Use this tab to record data relating to Patient Experience/QOL scores for Q4
9 | Baseline Data (3) | Use this tab to record baseline data relating to rates of 30 day chemotherapy mortality. This data should be recorded within the SACT data submission.
9.1 | 17 - 18 Performance (2) | Use this tab to record full year data relating to 30 Day Chemotherapy Mortality
10 | Baseline Data (4) | Use this tab to record baseline data relating to numbers of emergency admissions to your Hospital Trust for the chosen tumour site groups, for a three year period.
10.1 | 17 18 Performance (3) | Use this tab to record full year data relating to emergency admissions
11 | Charts | Use this tab to insert any charts derived from the data
12 | CA1 CQUIN
13 | Payment Guide
nathanhall@nhs.net
Richard.Berman@christie.nhs.uk
Further Guidance on ESC:
https://www.england.nhs.uk/wp-content/uploads/2016/03/ca1-enhncd-supprtv-care-guid.pdf
https://www.england.nhs.uk/2016/03/richard-berman/

## 1. Total Value of CQUIN
Estimated Target Population
Basis for Estimate: [please describe here the basis for the estimated figures given below. If your ESC service is focussing on a whole cancer population rather than specific disease sites, describe this rather than listing the range of disease sites encompassed within this.]
Cancer Tumour Site | Estimated number of new diagnosis of incurable disease
Enter Site No.1 Name Cover Sheet
Enter Site No.2 Name Cover Sheet
Enter Site No.3 Name Cover Sheet
Enter Site No.4 Name Cover Sheet
Enter Site No.5 name Cover Sheet
Enter Site No.6 name Cover Sheet
TOTAL | 0
Agreed £value per targeted patient
Total Potential Value for CQUIN Scheme | 0

## 2. Baseline - Referal Offer
Baseline Data - % of patients being offered referral to a Supportive Care Team at point of diagnosis of incurable disease
Baseline Data relates to: [please confirm here the time-period for this baseline data]
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 7 only and change the title in line 6 column A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Cancer Tumour Site | Total number of new diagnosis of incurable disease | Total Number of Patients offered referral to a Supportive Care Team* at Point of Diagnosis of incurable disease | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis of incurable disease
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | -
*The Term Supportive Care Team includes a referral to a Palliative Care Team

## 3. ESC principles - progress
Principles of ESC - Baseline and progress This section collects information on a quarterly basis - some qualitative, to enable providers to describe progress with your ESC model towards meeting the 6 underpinning principles of ESC. This will not be used for direct comparative analysis with other models, but to enable fuller understanding of the evolution and progress of your specific model, benefits and it's potential impact across other parts of the system.
Baseline Data relates to: [please confirm here the time-period for this baseline data]
Principles | Aim | Components of the ESC principle | Q1 | Q2 | Q3 | Q4
1. Earlier involvement of supportive care servicesSupportive Care | From the point of recognition of incurable disease (whether local or metastatic) all patients should be screened for supportive care needs (NICE 2004). This should include prompt identification and management of physical and psychological symptoms. This has the potential to improve the patient experience and their ability to tolerate anti-cancer treatment | How are you are offering earlier involvement of supportive care services? (with reference to actions, or specific activities undertaken and the resulting change/improvement)
Number of patients diagnosed with incurable cancer in the quarter who have been offered ESC and demonstrate an upward trend
Have you identified a clinical lead for ESC? Yes/No From which professional group? Describe the impact of this on developing ESC locally If 'no' explain your rationale for not identiying a clinical lead.
Describe how your approach to identifying patients is proactive, and how this has impacted on ESC, patients and other services.
How are you poviding efficient referral pathways to allow prompt access to supportive care?
What changes have been made through your ESC service to enable it to be ‘available’ to provide advice to oncology, by phone and face to face?
Do your ESC patients having access to an advice line – for issues relating to pain / symptom control / complications of treatment?
Have you developed joint clinics? If yes, with whom and what is the impact? - for patients, ESC and other professions
Principle 2; Supportive care teams that work together | Aim: Cancer patients should have access to a comprehensive range of support services, which run alongside their anti-cancer treatments. These supportive care services should work together, ideally under one umbrella, and have recognition in their centres as a core part of the business – being regarded as the “4th pillar of cancer care | Describe the range of professionals involved with the ESC caseload across this quarter, and how you demonstrate a joined up approach, to your ESC patients
Describe your approach to ESC MDT - e.g. frequency of meeting, model, documentation.
Describe how you are working with your community palliative care services, and the impact on your service, their services and the ESC patients. E.g. - has this resulted in improvements in efficiency and referrals/access?
Number of patients referred to benefits advisor as a result of ESC, for whom this would not otherwise have taken place yet?
Is your ESC service involved with joint working on projects – research and audit – to enhance clinical outcomes and care
Does your ESC model provide of one-stop supportive care outpatient clinics – with multiple supportive care specialties available within the clinic to help patient complementary, OT, physiotherapy).
Number of patients referred to other palliative care services e.g. day therapy as a result of ESC, for whom this would not otherwise have taken place yet
Principle 3; A more positive approach to supportive care | Aim: Excellent supportive care should offer patients a positive experience, help them to maintain hope, and even have the potential to extend survival. This approach should be adopted throughout the continuum of cancer care. In particular, for patients in whom further chemotherapy is unlikely to offer any benefit, provision of ongoing high quality supportive care should be seen as a ‘real’ and robust alternative to continuation of anti-cancer treatment. | Describe how your ESC model demonstrates to patients that it is maintaining appropriate hope and presenting a positive approach to care.
How have you rebranded existing services to create ' ESC' and what is the title of your ESC service model?
Does your ESC model enable 'automatic' referral to supportive care teams at the point of diagnosis of incurable disease? If 'no' how are you progressing towards this? eg building rapport, relationships and regular review throughout treatment and beyond.
Where your ESC service is receiving additional referrals for access to ESC from non-palliative care professionals, ie individual consultants (or their teams) please record number of referrals recieved.
Principle 4; Cutting edge and evidence-based practice in supportive and palliative care. | Aim: Supportive care teams should commit to ensuring that the care they provide is cutting-edge, with awareness of the latest available pain and symptom control treatments used in different stages of cancer care. | Describe the involvement of your ESC model or patients in ESC related research
Describe how you tailor your treatments for managing pain and symptoms, for patients who are earlier in their cancer trajectory / on active cancer treatment
Are you more involved in managing the adverse effects of cancer treatments, as a result of ESC?
Are you referring for pain interventions more frequently as a result of ESC?
Describe how ESC has impacted on patients in your centre/Trust who are living with ‘chronic cancer’ .
Have you extended your ESC service more widely than just for patients with incurable cancer? (eg curable disease, non-cancer, survivorship)?
Describe any involvement of your ESC model or patients in ESC related research
Principle 5; Technology to improve communication | Aim: Incorporating technology to facilitate better communication between the hospital and community services, especially for patients with progressing cancer. | Describe how your ESC service is using technology to improve communication with other professionals. E.g. number of ESC patients added to the Electronic Palliative Care Coordination System.
Describe how your ESC service is using technology to improve communication with patients at home e.g. remote monitoring / electronic patient reporting systems.
Number of ESC patients completing an electronic Holistic Needs Assessment (eHNA)
Principle 6; Best practice in chemotherapy care. | Aim: Cancer patients should be offered appropriate treatment, delivered to a high standard. All chemotherapy treatment regimens and associated supportive care offered should be based on the results of national and international research and audit. | Does your ESC model support shared decision making between patients and oncologists regarding treatment options and continuation of treatment?”
How does your ESC model support patients to cope with the burden of treatment?
How does your ESC model support patients to self care?
Can you demonstrate an impact on decision making regarding appropriateness of treatment? Is there any evidence of an impact on 30 day chemotherapy mortality?

## 4. Q1
QUARTER 1 POSITION
Has Baseline Data been collected for each of the targeted Cancer Disease Sites or % cancer population where this is the focus of your ESC service, covering offer of referral rate to supportive care, 30 day Chemotherapy Mortality, Patient Experience and Emergency Admissions?
Yes/No | Yes
Comments:
Has a Clinical Lead for Enhanced Supportive Care been nominated and communicated to Richard.Berman@christie.nhs.uk
Yes/No | No
Comments:
20% Payment for Achieving: | 0

## 5. Q2
QUARTER 2 - % of patients being offered referral to a Supportive Care Team at point of diagnosis of incurable disease
Q1 & Q2 Activity - April - September 2018
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 7 only and change the title in line 6 column A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Q1 & Q2
Cancer Tumour Site | Total number of new diagnosis of incurable disease in Period | Total Number of Patients offered referral to a Supportive Care Team at Point of Diagnosis of incurable disease in Period | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis for Period | Total Number of Consultations - new and follow up (for Supportive Care) from this cohort
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | - | 0
Has a Clinical Lead for Enhanced Supportive Care engaged with national peer group of clinical leads?
Yes/No | Yes
Comments:
Has Improvement from baseline been demonstrated re % of patients offered referral to supportive care?
Yes/No | No
Comments:
20% Payment for Achieving: | 0

## 6. Q3
QUARTER 3 - % of patients being offered referral to a Supportive Care Team at point of diagnosis of incurable disease
October 2017 -December 2018
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 7 only and change the title in line 7 column A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Q3
Cancer Tumour Site | Total number of new diagnosis of incurable disease in Period | Total Number of Patients offered referral to a Supportive Care Team at Point of Diagnosis of incurable disease in Period | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis for Period | Total Number of Consultations - new and follow up (for Supportive Care) from this cohort
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | - | 0
Has Improvement from baseline been demonstrated re % of patients offered referral to supportive care?
Yes/No | Yes
Comments:
30% Payment for Achieving: | 0
Up to 60% of Total CQUIN Value (Based on above performance) It is suggested that if across the final 6 months of the first year that 80% of eligible patients*, for that period, have been offered referral to the Enhanced Supportive Care team, then that should be seen as good enough performance to generate the final 60% payment. If performance is below this level then we suggest payment is made in line with the performance achieved (e.g. the providers gets 70% of the final payment if they deliver 70% of eligible patients referred to the Enhanced Supportive Care Team.) However, the actual targets set also need to be cognisant of the need to stretch current baseline performance where an enhanced supportive care approach is already in place.

## 7. Q4
QUARTER 3&4 - % of patients being offered referral to a Supportive Care Team at point of diagnosis of incurable disease
January 2019 -March 2019
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 7 only and change the title in line 6 colunm A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Q4
Cancer Tumour Site | Total number of new diagnosis of incurable disease in Period | Total Number of Patients offered referral to a Supportive Care Team at Point of Diagnosis of incurable disease in Period | % of Patients in Disease Group offered referral to a supportive care team at point of diagnosis for Period | Total Number of Consultations - new and follow up (for Supportive Care) from this cohort
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | - | 0
`
Has Improvement from baseline been demonstrated re % of patients offered referral to supportive care?
Yes/No | Yes
Comments:
30% Payment for Achieving: | 0
Up to 60% of Total CQUIN Value (Based on above performance) It is suggested that if across the final 6 months of the first year that 80% of eligible patients*, for that period, have been offered referral to the Enhanced Supportive Care team, then that should be seen as good enough performance to generate the final 60% payment. If performance is below this level then we suggest payment is made in line with the performance achieved (e.g. the providers gets 70% of the final payment if they deliver 70% of eligible patients referred to the Enhanced Supportive Care Team.) However, the actual targets set also need to be cognisant of the need to stretch current baseline performance where an enhanced supportive care approach is already in place.

## 8. IPOS Data Baseline
Baseline Data (Q1) Patient Experience/QOL Scores Using IPOS Staff Tool
Data for Q1 18 -19
IPOS SURVEY (STAFF) AREA | IPOS Scores Audit - For Q1 18/19 from a random sample of 10 patients record average IPOS scores from at least 2 visits to supportive care team (1st and at least one follow up; ideally not consecutive visits)
Visits
| 1st | F/U (1) | F/U (2) | F/U (3) | F/U (4) | F/U (5)
Pain
Shortness of breath
Weakness or lack of
energy
Nausea
Vomiting
Poor appetite
Constipation
Sore or dry mouth
Drowsiness
Poor mobility
Has s/he been feeling anxious or worried about his/her illness or treatment?
Have any of his/her family or friends been anxious or worried about the patient?
Do you think s/he felt depressed?
Do you think s/he has felt at peace?
Has the patient been able to share how s/he is feeling with his/her family or friends as much as s/he wanted?
Has the patient had as much information as s/he wanted?
Have any practical problems resulting from his/her illness been addressed? (such as financial or personal)
comments

## 8.1. IPOS Data Q2
17 - 18 - Patient Experience/QOL Scores Using IPOS Staff Tool
Data for Q2 18 -19
IPOS SURVEY (STAFF) AREA | For Q2 18/19 from a random sample of 10 patients record average IPOS scores from at least 2 visits to supportive care team (1st and at least one follow up idealy not consecutive visits)
Visits
| 1st | F/U (1) | F/U (2) | F/U (3) | F/U (4) | F/U (5)
Pain
Shortness of breath
Weakness or lack of
energy
Nausea
Vomiting
Poor appetite
Constipation
Sore or dry mouth
Drowsiness
Poor mobility
Has s/he been feeling anxious or worried about his/her illness or treatment?
Have any of his/her family or friends been anxious or worried about the patient?
Do you think s/he felt depressed?
Do you think s/he has felt at peace?
Has the patient been able to share how s/he is feeling with his/her family or friends as much as s/he wanted?
Has the patient had as much information as s/he wanted?
Have any practical problems resulting from his/her illness been addressed? (such as financial or personal)
comments

## 8.2 IPOS Data Q3
17-18 - Patient Experience/QOL Scores Using IPOS Staff Tool
Data for Q3 18 - 19
IPOS SURVEY (STAFF) AREA | For Q3 18/19 from a random sample of 10 patients from each disease site record average IPOS scores from at least 2 visits to supportive care team (1st and at least one follow up; ideally not consecutive visits)
Visits
| 1st | F/U (1) | F/U (2) | F/U (3) | F/U (4) | F/U (5)
Pain
Shortness of breath
Weakness or lack of
energy
Nausea
Vomiting
Poor appetite
Constipation
Sore or dry mouth
Drowsiness
Poor mobility
Has s/he been feeling anxious or worried about his/her illness or treatment?
Have any of his/her family or friends been anxious or worried about the patient?
Do you think s/he felt depressed?
Do you think s/he has felt at peace?
Has the patient been able to share how s/he is feeling with his/her family or friends as much as s/he wanted?
Has the patient had as much information as s/he wanted?
Have any practical problems resulting from his/her illness been addressed? (such as financial or personal)
comments

## 8.3 IPOS Data Q4
17-18 - Patient Experience/QOL Scores Using IPOS Staff Tool
Data for Q4 18-19
IPOS SURVEY (STAFF) AREA | For Q4 18/19 from a random sample of 10 patients record average IPOS scores from at least 2 visits to supportive care team (1st and at least one follow up ; ideally not consecutive visits)
Visits
| 1st | F/U (1) | F/U (2) | F/U (3) | F/U (4) | F/U (5)
Pain
Shortness of breath
Weakness or lack of
energy
Nausea
Vomiting
Poor appetite
Constipation
Sore or dry mouth
Drowsiness
Poor mobility
Has s/he been feeling anxious or worried about his/her illness or treatment?
Have any of his/her family or friends been anxious or worried about the patient?
Do you think s/he felt depressed?
Do you think s/he has felt at peace?
Has the patient been able to share how s/he is feeling with his/her family or friends as much as s/he wanted?
Has the patient had as much information as s/he wanted?
Have any practical problems resulting from his/her illness been addressed? (such as financial or personal)
comments

## 9.Chemo mortality baseline
Baseline Data - 30 Day Chemotherapy Mortality
Baseline Data relates to: [please confirm here the time-period for this baseline data]
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 6 only and change the title in line 5 colunm A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Cancer Tumour Site | Total Number of Patients Receiving Chemotherapy Treatment within Baseline Period | Total Number of Deaths Occuring within 30 Days of Chemotherapy Treatment | Proportion of Deaths within 30 days of Chemotherapy %
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | -
comments

## 9.1. 30 Day Mort 18-19
18/19 ; 30 Day Chemotherapy Mortality
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 6 only and change the title in line 5 column A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Cancer Tumour Site | Total Number of Patients Receiving Chemotherapy Treatment within Period | Total Number of Deaths Occurring within 30 Days of Chemotherapy Treatment | Proportion of Deaths within 30 days of Chemotherapy %
Enter Site No.1 Name Cover Sheet |  |  | -
Enter Site No.2 Name Cover Sheet |  |  | -
Enter Site No.3 Name Cover Sheet |  |  | -
Enter Site No.4 Name Cover Sheet |  |  | -
Enter Site No.5 name Cover Sheet |  |  | -
Enter Site No.6 name Cover Sheet |  |  | -
TOTAL | 0 | 0 | -
comments

## 10. Baseline Em Admissions
Baseline Data - Emergency Hospital Admissions
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 6 only and change the title in line 4 column A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Cancer Tumour Site | Total Number of Emergency Non-Elective Admissions (Oncology) within this Cancer Centre
| 2016/17 | 2017/18 | 2018/19 | Average Growth across Period | Percentage Growth
Enter Site No.1 Name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
Enter Site No.2 Name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
Enter Site No.3 Name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
Enter Site No.4 Name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
Enter Site No.5 name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
Enter Site No.6 name Cover Sheet |  |  |  | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
TOTAL | 0 | 0 | 0 | 0 | - | #DIV/0! | #DIV/0! | #DIV/0!
comments

## 10.1 Em Admissions 1819
18/19 Performance - Emergency Hospital Admissions
Baseline Data relates to: [please confirm here the time-period for this baseline data]
If your ESC service is focussing on a whole cancer population rather than specific disease sites, please complete the table using line 7 only and change the title in line 5 row A to ' Cancer population' rather than listing each disease site encompassed by your population, individually
Cancer Tumour Site |  | Total Number of Emergency Non-Elective Admissions (Oncology) within this Cancer Centre
| Percentage of Average Growth across Period | Expected level of admissions for 18/19 (extrapolated from previous years growth rate of admissions) | 2018 -19 Actual | Change from Expected Rate
Enter Site No.1 Name Cover Sheet | - | - | 0 | -
Enter Site No.2 Name Cover Sheet | - | - | 0 | -
Enter Site No.3 Name Cover Sheet | - | - | 0 | -
Enter Site No.4 Name Cover Sheet | - | - | 0 | -
Enter Site No.5 name Cover Sheet | - | - | 0 | -
Enter Site No.6 name Cover Sheet | - | - | 0 | -
TOTAL | - | - | 0 | -
comments

## Hide Look up tables (hidden)
Yes | >75%
No | 50%-74%
<50%