## Title
Benefits Identification and Realisation Document
Date
Version 1.0
Purpose of the Document
This document can be used to measure demonstratable benefits, evidence that improvement has taken place over time, and that benefits can be sustained.
It can be used to compare your results with others to benchmark current performance and idenfitify areas to target improvement
The template provides examples for possible benefits, and your Implementation and Business Change manager can help you in defining additional ones if required.

## Benefit Report
BENEFIT PLANNING AND REALISATION
Strategic Alignment |  |  | Problem | [9 empty] | Benefits Mapping and profiling | [6 empty] | Success Criteria |  |  |  | Review Date | Review Date | Review Date
National Objective | Enabling women access to their Care records as involvement in care is expected to improve outcomes for mother and baby. Also will improve mothers experience |  | Name of Problem | Strategic Owner of problem | Operational owner of Problem | Problem statement | Issues/Barriers to success | AS IS Map Issues | Vision of the future | Change and Enablers | Action | Risks | Organisational objective | Benefits we want to achieve | Disbenefits we want to control | Capabilities and Outcomes | Work | Main Benefit Recipient | Category of Benefit | What are we going to measure | How are we going to measure | When are we going to measure | Baseline results
Trust objective/s |  | 1 | Cost of printing local educational materials |  |  | Cost of printing local educational materials are increasing |  |  | Saving the cost of educational leaflets, while inceasing access to educational material |  |  |  |  | Reduced cost of educational leaflets |  |  |  | Provider Organisation Women | Cash Releasing | Number of leaflets used Number of Leaflets available online Cost of leaflets | Leaflets provided at Booking Leaflets provided at each AN visit | Booking 16wk AN visit 24wk AN visit
|  | 2 | Reduce Carbon Footprint |  |  | The increasing paper printed, increases unwanted carbon footprint
|  | 3 | Cost of National educational leaflets |  |  | Cost of purchasing national educational materials are increasing | [7 empty] | Reduced cost of educational leaflets
|  | 4 | Cost of buying the Pregnancy hand held records |  |  | Cost of purchasing Maternity booklets (Handheld records) are increasing
|  | 5 | Cost of storing the preganancy hand held records |  |  | Cost of storing Paper-based records for 25 years, after the maternity episode has ended, has a high cost impact.
|  | 6 | Cost of scanning the paper-based records for archiving |  |  | The cost of scanning paper-based records for digital storage has increased the total cost of archiving records
|  | 7 | Cost of preparing a copy of the medical record on women's demand |  |  | Cost of preparing and providing a copy of the medical record has an impact on administrator time
|  | 8 | Cost in time taken to transcribe information between paper and electronic systems |  |  | Overworked clinical professionals haven't the time to do "admin work" to update paper-based records, or print copies for hand held records. | X number of systems are not integrated | [6 empty] | Reduced risk of error when transcribing details Reduced time taken to transcribe details | [5 empty] | Time taken to transcribe details Time taken to correct errors in transcription | Assess a sample group, by time and motion study | When women transfer care into the Trust At booking appointment
|  | 9 | Women engagment with their maternity record |  |  | Women do not understand and or not fully engaged with their maternity record. |  |  | Women will enter the details of their booking assessment, prior to their meeting with the midwife |  |  |  |  | Women's engagement, and reduced Midwife time at Booking.
|  | 10 | Cost in time taken to investigate "incidents" with a direct corralation to poor record keeping |  |  | Innaccurate or incorrect data collected is impacting on service user safety.
|  | 11 | Womens perception of Good pregancy outcome needs improving |  |  | Women carry the paper-based records around with them, causing inconvenience | [7 empty] | Reduction in complaints Increased completion of surveys Increased Preception of good Care recorded
Note on A1: A benefit is measurable improvement seen by the stakeholder as a benefit and contributing to the organisation's objective.
Note on E3: Accountable for 1. Resources 2. Political Backing 3. Driving 4. Receiving reports
Note on F3: Responsible for 1. Designing the change 2. Staff Moral 3. Making it happen 4. Reporting benefits
Note on G3: 1. What areas have problems. 2. Where are we not succeeding as well as we can. 3. What objectives are we not meeting
Note on H3: 1. What is happening in this area which means we are not succeeding? 2. What can we do better
Note on I3: 1. Risk Assess the process 2. Idenitify the bottlenecks 3. Process smoothing
Note on J3: 1. What will I see if I fix the problem 2. What KPIs will be improved 3. Whats the knock on effect
Note on K3: 1. What has to change in order to enable the vision. 2. What enablers need to be present for people to do things better 3. What will they do differently 4. TO BE process mapping
Note on L3: What will I have to do to make things happen 1. Human (process) 2. Technical 3. Physical 4. Governance 5. Cultural 6. Other
Note on M3: 1. What are the risks 2. What are the dependancies 3. External Context 4. Priorities 5. What are you uncertain about
Note on Q3: 1. What do we stop doing 2. What do we start doing 3. What do we do differently 4. Exploiting an enabler 5. Result of change
Note on R3: 1. Actions to be taken 2. Business Change (20% is technology, 80% is business change)
Note on S3: 1. Health Professional 2. Provider Organisation 3. Women 4. Other (define)
Note on T3: 1. Cash releasing (if money will be saved and released from a budget i.e. print costs) 2. Non-cash releasing (where the benefit is time saved and that persons time will be re-directed to other activities rather than reducing headcount) 3. Quality Benefit (where no monetary value can be attributed but there is a measurable improvement such as patient satisfaction) 4. Public Benefit (where we are saving time/cost for the public)
Note on U3: 1. Existing Key performance indicators
Note on V3: 1. Data collection, method 2. calculation