## DPIA Risk register
Privacy Impact Assessment - Risk Register | [5 empty] | Mandatory privacy risks to assess - if not applicable place N/A with relevant detail to justify why it's not relevant. Also add further risks identified.
Initiative name
Risk reference: A unique coding that allows the risk to be easily identified | Which elements of the initiative give rise to privacy risks? | What is/are the potential or actual privacy risk(s) | Risk Score |  |  | Proposed solution(s)/mitigating action(s) – systems and processes that are or will be in place and operating that mitigate this risk, including assurances | Result | Evaluation | Solution approved by | Action | Date for completion | Anticipated risk score |  |  | Responsibility | Current status/progress
|  |  | Likelihood | Impact | RAG status | [6 empty] | Likelihood | Impact | RAG status
1 | Transferring of data outside of the EEA | Non-compliance:- No adequacy arrangement results in serious non-compliance with the data protection legislation. This faces regulatory action and exposes the vulnerability of an organisation as it is a breach. If consequently there is any loss of personal data to non-trusted sources this is a further breach and risks privacy re onward sharing of personal data; reputational damage; loss of trust by data subjects. | 2 | 3 | AG | 1. The platform is only accessed by staff within the UK and the platform is locked down for access to specific IP addresses of known users. 2. All members of staff are informed via security operating procedures that they must conform with the requirements of the Data protection act and must not download data from the platform. 3. A platform configuration review confirms that no data is exposed to the platform and the platform is only accessible to a small number of known and approved endpoints. |  |  |  | No further action | N/A | 2 | 3 | AG | NHS Front Door Team | Complete
2 | Misuse of information by those with access | Non-compliance with the data protection legislation; vulnerability of organisation against breach and possible regulatory action; loss of personal data to non-trusted sources; privacy risk to onward sharing of personal data; reputational damage; loss of trust by data subjects. | 2 | 3 | AG | 1. The supplier is on contract with relevant security and data protection clauses contained within the agreements. 2. All users are required to sign security operating procedures that confirm their responsibilities to protect data. 3. The download funtionality of data from Palantir Foundry platform has been disabled and access to this is controlled by the NHS Front Door process which ensures appropriate governance in in place |  |  |  | Ongoing review of this by NHS Management Team |  | 1 | 5 | G | NHS Management | Ongoing
3 | Adequate data processing agreements with relevant data processors; | Non-compliance with the data protection legislation; vulnerability of organisation against breach and possible regulatory action; loss of personal data to non-trusted sources; privacy risk to onward sharing of personal data; reputational damage; loss of trust by data subjects. | 1 | 4 | G | 1. Data Processing Agreements are in place with all data suppliers 2. The contracts in place with suppliers are GDPR compliant, are G-Cloud and have appropriate protections built into it. |  |  |  | No further action | N/A | 1 | 4 | G | NHS Management | Complete
4 | Lack of technical or organisational measures implemented to ensure appropriate security of the personal data | Non-compliance with the data protection legislation; vulnerability of organisation against breach and possible regulatory action; loss of personal data to non-trusted sources; privacy risk to onward sharing of personal data; reputational damage; loss of trust by data subjects. | 1 | 5 | G |  |  |  |  | No further action |  | 1 | 5 | G | NHS Management | Complete
5 | Personal data not being encrypted both/either in transit or at rest | Non-compliance with the data protection legislation; vulnerability of organisation against breach and possible regulatory action; loss of personal data to non-trusted sources; privacy risk to onward sharing of personal data; reputational damage; loss of trust by data subjects. | 1 | 1 | G | 1. Data is encrypted in storage 2. All data to and from the platform is encrypted in transit using at least TLS1.2 |  |  |  | No further action | N/A | 1 | 1 | G | NHS Management | Complete
6 | Lack of testing which would assess and improve the effectiveness of such technical and organisational measures | Non-compliance with the data protection legislation; vulnerability of organisation against breach and possible regulatory action; loss of personal data to non-trusted sources; privacy risk to onward sharing of personal data; reputational damage; loss of trust by data subjects. | 2 | 2 | AG | 1. An AWS platform configuration review by AWS security team has been performed to ensure that first ingest of data is stored securely. 2. Full penetration test will also be undertaken. |  |  |  | Regularised PEN tests planned on an ongoing basis to assure security | Ongoing | 1 | 1 | G | NHS Management | Ongoing
7 | Risk of re-identification for analysts who have access to psuedonymised record level data | Due to the small numbers of Covid cases (especially during the early days) there is a possibility that data could be triangulated and individuals could be identified. This would impact on trust from data subjects | 3 | 2 | AG | 1. Access to NHS Data at pseudonymised record level remains in control of the NHS in line with contractual arrangements 2. Staff are trained and fully aware of their responsibilites when analysis data to only use the minimum required for their purpose and that it is a criminal offence under the DPA 2018 to knowingly re-identify an individual 3. Contracts of employment and other organisational policies provide further safeguards against data missuse |  |  |  | Ongoing review of this by NHS Data Management Team | Ongoing | 1 | 1 | G | NHS Management | Ongoing
Note on D5: 1 = Rare 2 = Unlikely 3 = Possible 4 = Likely 5 = Almost certain
Note on E5: 1 = Insignificant or minor 2 = Moderate 3 = Significant 4 = Very significant 5 = Major
Note on M5: 1 = Rare 2 = Unlikely 3 = Possible 4 = Likely 5 = Almost certain
Note on N5: 1 = Insignificant or minor 2 = Moderate 3 = Significant 4 = Very significant 5 = Major

## Types of privacy risk
Types of privacy risk
Risks to individuals
· Inadequate disclosure controls increase the likelihood of information being shared inappropriately.
· The context in which information is used or disclosed can change over time, leading to it being used for different purposes without people’s knowledge.
· New surveillance methods may be an unjustified intrusion on their privacy.
· Measures taken against individuals as a result of collecting information about them might be seen as intrusive.
· The sharing and merging of datasets can allow organisations to collect a much wider set of information than individuals might expect.
· Identifiers might be collected and linked which prevent people from using a service anonymously.
· Vulnerable people may be particularly concerned about the risks of identification or the disclosure of information.
· Collecting information and linking identifiers might mean that an organisation is no longer using information which is safely anonymised.
· Information which is collected and stored unnecessarily, or is not properly managed so that duplicate records are created, presents a greater security risk.
· If a retention period is not established information might be used for longer than necessary.
Compliance risk
· Non-compliance with the DPA.
· Non-compliance with the Privacy and Electronic Communications Regulations (PECR).
· Non-compliance with sector specific legislation or standards.
· Non-compliance with human rights legislation.
Associated organisation/corporate risk
· Non-compliance with the DPA or other legislation can lead to sanctions, fines and reputational damage.
· Problems which are only identified after the project has launched are more likely to require expensive fixes.
· The use of biometric information or potentially intrusive tracking technologies may cause increased concern and cause people to avoid engaging with the organisation.
· Information which is collected and stored unnecessarily, or is not properly managed so that duplicate records are created, is less useful to the business.
· Public distrust about how information is used can damage an organisation’s reputation and lead to loss of business.
· Data losses which damage individuals could lead to claims for compensation.

## Guidance for completion
Risk guidance
Guidance for completing a risk register
What is the actual risk ? (really consider and evaluate what the risk is).
Is the risk clear and concise and articulated with appropriate use of language, suitable for the public domain.
All risks need to proceed with the wording: There is a risk that ……… would lead to ………….
‘Risk owner’ and ‘Action owner’ should include full job title (not names).
Acronyms must be spelt out in the first instance.
Be careful and sensitive about the wording of the risk, as risk registers are subject to Freedom of Information (FOI) requests.
Don’t reference blame to other organisations in the risk register (the register may be made available in the public domain).
Does the risk belong to a business area within the NHS England or another NHS body, e.g. DH.
Risk assessment / scoring in line with the guidance (really ask yourself how likely the realisation of the risk is).
The risk register
Risk owner – the owner is responsible for the management and control of all aspects of the risk. Each national directorate has an assigned National Director who as Senior Responsible Owner (SRO) is the responsible risk owner for the strategic risks.
Risk description- a statement describing the cause, risk event and impact.
Mitigating actions - systems and processes that are in place and operating that mitigate this risk. This can include assurances: Internal assurance - internal evidence that this risk is being effectively managed (e.g. Board reporting, sub-committee and internal audit committee reviews), and external assurance - external evidence that this risk is being effectively managed (e.g. planned or received external audit reviews).
Action owners - all risks have an action owner to who has delegated responsibility for the on going control, monitoring and status reporting.
Completion date for actions - each mitigating action should have a completion date, for when the action will be completed.
Scoring the risks
NHS England risks should be scored between 1-5 for both likelihood and impact.
The table below provides descriptions of likelihood and impact scoring.
Score
Likelihood score | 1 | 2 | 3 | 4 | 5
Descriptor | Rare | Unlikely | Possible | Likely | Almost Certain
Frequency - how often might it happen? | This probably will never happen/recur | Do not expect it to happen/recur, but it is possible it may do so | Might happen or recur occasionally | Will probably happen/recur, but is not a persisting issue or circumstance | Almost certain to happen/recur; possibly frequently
Score
Impact score | 1 | 2 | 3 | 4 | 5
Descriptor | Very low | Low | Medium | High | Very high
Impact should it happen? | Unlikely to have any impact | May have an impact | Likely to have an impact | Highly probable it will have a significant impact | Will have a major impact
NHS England uses a RAG matrix rating system. RAG stands for red, amber, green. To achieve a RAG rating, each risk first needs a likelihood and impact score.
Each risk will be RAG rated by taking the likelihood and impact scores, and using the matrix below:
Using the risk “RAG” rating system for scoring risks means risks can be ranked so that the most severe are addressed first. Decisions can then be made as to what mitigating action can be taken to alleviate the risk.
A
A/R
R
R
R
A
A
A/R
R
R
A/G
A
A
A/R
A/R
Very High -5
High - 4
Medium - 3
G
A/G
A/G
A
A
G
G
G
G
G
1
Rare
2
Unlikely
3
Possible
4
Likely
5
Almost Certain
Likelihood
Low - 2
Very Low - 1
Impact

## RAG Lookup (hidden)
Risk Scoring
Impact | Likelihood | Concat | RAG
1 | 1 | 11 | G
1 | 2 | 12 | G
1 | 3 | 13 | G
1 | 4 | 14 | G
1 | 5 | 15 | G
2 | 1 | 21 | G
2 | 2 | 22 | AG
2 | 3 | 23 | AG
2 | 4 | 24 | A
2 | 5 | 25 | A
3 | 1 | 31 | AG
3 | 2 | 32 | A
3 | 3 | 33 | A
3 | 4 | 34 | AR
3 | 5 | 35 | AR
4 | 1 | 41 | A
4 | 2 | 42 | A
4 | 3 | 43 | AR
4 | 4 | 44 | R
4 | 5 | 45 | R
5 | 1 | 51 | A
5 | 2 | 52 | AR
5 | 3 | 53 | R
5 | 4 | 54 | R
5 | 5 | 55 | R