## Notes
NHS Improvement consolidation framework document
2018
This document is a guide to pathology consolidation project planning. The guide project plan has been been developed using pathology laboratory consolidation expertise and the review of case studies of pathology consolidation projects.
The project plan is a guide only: each consolidation project will have factors and details not included in this template guide. The timelines suggested are also a guide only and each project will have its own complexities and constraints that will alter the guide timelines.
The plan is split into two sections:
1. scenarios where the strategic outline case (SOC) results in the development of a joint venture, arm's-length hosted organisation or limited liability entity
2. scenarios where the SOC results in a decision to outsource pathology services. This framework will be included with the outsourcing toolkit.

## Project Framework (JV, ALO)
Pathology Consolidation Framework Plan (For JV and unit organisations) |  |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
Month
Activity | Responsibility | Sign Off | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Pre planning | bar: Month 1
Gain understanding of regulatory environment | bar: Month 1
Engage NHS Improvement | bar: Month 1
Define options evaluation criteria | bar: Month 1
SOC | bar: Month 2 to Month 7
Strategic case analysis | bar: Month 2
Macro environment analysis | bar: Month 2
Micro environment analysis | bar: Month 2
Need for change | bar: Month 2
SWOT analysis | bar: Month 2
Economic case analysis | bar: Month 2 to Month 6
Data collection of current services | bar: Month 2 to Month 3
Data standardisation process for baseline state | bar: Month 4 to Month 5
Develop scenarios for future operating model | bar: Month 5 to Month 6
Data collection of current finances | bar: Month 2 to Month 3
Standardisation of financial baseline | bar: Month 4 to Month 5
Identification of key service requirements | bar: Month 2
Analyse operational and financial baseline | bar: Month 6
Collate and analyse SWOT analysis | bar: Month 6
Financial case analysis | bar: Month 5 to Month 6
Financial analysis of future state against each option | bar: Month 5 to Month 6
Commercial case analysis | bar: Month 2 to Month 6
Identify possible commercial structures | bar: Month 2
Evaluate each commercial structure | bar: Month 3 to Month 4
Identify key commercial terms with initial considerations | bar: Month 5 to Month 6
Management case analysis | bar: Month 2 to Month 6
Identify management structure | bar: Month 2
Identify project resources required | bar: Month 3 to Month 4
Identify organisational structure | bar: Month 5
Identify reporting heirarchy | bar: Month 6
Identify project risks | bar: Month 2 to Month 6
Analyse options and evaluate | bar: Month 7
Decide option to proceed | bar: Month 7
OBC | bar: Month 8 to Month 13
Review and update strategic case from SOC | bar: Month 8
Detailed design of target operating model | bar: Month 8 to Month 13
Identify key assumptions | bar: Month 8
Establish service quality baseline | bar: Month 8
Identify TOM service configuration (hub and spoke specs) | bar: Month 8 to Month 9
Facility review and capacity modelling | bar: Month 10 to Month 11
Define logistics model | bar: Month 8 to Month 9
Define IT/LIMS system | bar: Month 8 to Month 9
Define workforce structure | bar: Month 11
Define organisational structure | bar: Month 11
Conduct detailed financial analysis against baseline | bar: Month 12 to Month 13
Governance design | bar: Month 8 to Month 13
Define operating arrangements | bar: Month 8 to Month 9
Define owner trust representation | bar: Month 8 to Month 9
Define executive and non-executive representation | bar: Month 8 to Month 9
Define appointment process | bar: Month 10
Define governance principles | bar: Month 10
Define heads of terms of reference | bar: Month 8 to Month 13
Transition planning | bar: Month 12 to Month 13
Construct transition project plan | bar: Month 12 to Month 13
Assess required transition and management personnel | bar: Month 12 to Month 13
Define staff engagement strategy | bar: Month 12 to Month 13
Define clinical engagement strategy | bar: Month 12 to Month 13
Define supplier and service user engagement strategy | bar: Month 12 to Month 13
Ascertain source of capital | bar: Month 12 to Month 13
Define procurement requirements | bar: Month 12 to Month 13
Define project phases | bar: Month 12 to Month 13
Define organisational structure for transition team | bar: Month 12 to Month 13
Identify key project risks | bar: Month 12 to Month 13
OBC approval | bar: Month 14 to Month 15
FBC | bar: Month 16 to Month 18
Continued engagement (staff, clinical, supplier, service users) | bar: Month 16 to Month 18
Workforce planning | bar: Month 16 to Month 18
Refinement of target operating model | bar: Month 16 to Month 18
Refinement of layout design | bar: Month 16 to Month 18
Refinement of transition plan | bar: Month 16 to Month 18
Detailed understanding of enabling works | bar: Month 16 to Month 18
Completion of commercial agreement and contracts | bar: Month 16 to Month 18
Implementation | bar: Month 19 to Month 36
Commercial structure and governance | bar: Month 19 to Month 21
Commercial structure established and contracts signed | bar: Month 19
Appointment of board members | bar: Month 19
Appointment of chair | bar: Month 20
Appointment of executive management | bar: Month 20
Governance structure established | bar: Month 21
Heads of terms of reference agreed | bar: Month 21
Clarification on route to access capital | bar: Month 21
Detailed implementation plan established | bar: Month 22 to Month 23
Onboarding of workstream leads | bar: Month 22 to Month 23
Procurement plan established | bar: Month 22 to Month 23
Building works design and commission | bar: Month 22 to Month 23
LIMs implementation planning | bar: Month 22 to Month 23
Logsitics implementation planning | bar: Month 22 to Month 23
LIMS system implementation | bar: Month 24 to Month 33
Procurement implementation | bar: Month 24 to Month 33
Staff engagement and TUPE transfer | bar: Month 24 to Month 29
Hub facility capacity implementation for microbiology | bar: Month 27 to Month 32
Transfer of ESL microbiology to hub | bar: Month 33
Hub facility capacity implementation for cell pathology | bar: Month 29 to Month 34
Transfer of ESL Cell Path to hub | bar: Month 35
Hub facility capacity implementation for blood sciences | bar: Month 30 to Month 35
Transfer of ESL blood sciences to hub | bar: Month 36