## Instructions
Use this Standards Gap Analysis Template (SGAT) to help your organisation plan and prioritise implementing the Healthcare costing standards for England.
The template asks a series of questions covering the costing process (CPs) standards. The questions are designed to take you through the implementation of the costing standards step by step, allowing you to identify the areas where your organisation will need to focus their efforts to ensure compliance with the costing standards.
If you have any questions about this template, please email them to costing@improvement.nhs.uk
Ambulance costing standards gap analysis template

## CP1
CP1: The role of the general ledger in costing |  |  |  | Y | Red
N
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
1 | Have you read the standard?
2 | Have you have read the relevant costing principle and reviewed the relevant spreadsheet in the technical document
3 | Are you able to obtain the general ledger (GL) output?
4 | Have you agreed with your senior manager whether to do in-month costing or year to date costing?
5 | Do you include all your organisation's income and expenditure in your general ledger output?
6 | Have you discussed the general ledger's layout and structure with the finance team?
7 | Is there a process in place for the finance team to tell you the GL has been closed for the period?
8 | Do you keep a record of all off ledger adjustments to use in reconciling the costing outputs to the audited accounts?
9 | Have you documented the process for extracting the general ledger?
10 | Does the finance team tell you when it has set up new cost centres or expense codes?
11 | Does the finance team rename, merge or use existing cost centres for something else?
12 | Do you have a process to identify and map to the cost ledger new GL cost centres and expense codes?
13 | Do you have a process in place to identify and address dump ledger codes?
14 | Do you have a rolling programme in place to meet with your finance colleagues to discuss the GL and it's role in costing?

## Sheet4 (hidden)
Yes
No

## CP2
|  |  |  | Y | Red
CP2: Clearly identifiable costs |  |  |  | N | Amber
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
15 | Have you read the standard?
16 | Have you have read the relevant costing principles and reviewed the relevant spreadsheets in the technical document
17 | Have you read and understood the cost classifications of patient facing and type 1 and type 2 support costs
18 | Are you netting income off costs in the allowable ways for the 3 items in listed in a to c?
19 | Are you netting income off costs in any other ways other than the 3 allowable ways listed in a to c?
20 | Have you identified the pay recharges in your general ledger and identified the appropriate treatment in the costing process?
21 | Have you identified the commercial activities costs and income in the general ledger and identified an appropriate treatment in the costing process?
22 | Have you identified commercial activities with income but where the associated costs are difficult to identify and made a sensible assumption on how to identify the costs based on discussions with the department?
23 | Have you identified where your organisation holds the costs but not the activity to report under cost group 'Costs and income reconciliation'
24 | Have you identified if your organisation is taking part in any national programmes and identified the costs related to the programme?
25 | Have you reviewed the costing diagram in the technical document?
26 | Have you read and understood the 3 elements of getting the right costs in the starting place with the right label?
27 | In conjunction with review number 14 do you have a plan in place for a rolling programme of deep dive analysis into the general ledger supported by finance colleagues?
28 | Do you have a plan in place to put the information obtained through the deep dive analysis into your costing system to inform the processing rules? Will you do that yourself or will it be your software supplier?
29 | Have you discussed with your software supplier their development plans to put the cost ledger account codes into the costing system?
30 | Have you discussed with your software supplier their development plans to introduce the linear mapping of GL to CL to resource to collection resource?
31 | If you use a lower level of resource that in the standard have you reviewed how you will include that in the mapping
32 | As an interim measure have you done the mapping required in your costing system to ensure that your costs are in the right starting position with the right label, that you are using the prescribed allocation method for the resource and you are mapped to the correct collection resource?
33 | Have you initiated your rolling programme of deep dive analysis?
34 | If your GL includes sub analysis codes do you know what costs are recorded there?
35 | Have you identified GL lines that will need disaggregating because they are mapped to different resources?
36 | Have you run your cost ledger through NHS Improvement's GL to CL mapping algorithm?
37 | Have you reviewed the lines that did not map across when you ran the algorithm with your finance colleagues to understand what costs sit in the GL lines?
38 | Based on the information obtained from your finance colleagues have you identified the correct lines in the CL to map those unmapped GL lines to so you'll know how to treat those lines in the costing process?
39 | Have you updated your costing system with the information you obtained from your deep dive analysis and use of the GL to CL algorithm?
40 | Have you identified your type 1 support costs?
41 | Have you reviewed the type 1 support costs allocation methods in CP2.2 and identified where you comply and where you do not?
42 | Have you identified the information you will need to obtain so you can comply with the prescribed allocation methods?
43 | Have you identified where your support type 1 costs are centrally held or devolved?
44 | Have you identified where you are using a type 2 support cost allocation method for a type 1 support cost?
45 | Does your costing system do reciprocal costing?
46 | Have you updated your costing system to use the prescribed allocation methods for allocating type 1 support costs?
47 | Have you identified your type 2 support costs and your patient facing costs?
48 | Have you read and understood how to treat type 1 support costs in type 2 support cost centres and in patient-facing cost centres?
49 | Do you have a process in place to identify negative costs in the cost ledger and to treat them appropriately?
50 | Do you have a rolling programme to review the expected costs in the costing outputs to ensure that expected costs are being allocated correctly in the costing process?
51 | Have you set up your costing system to meet the PLICS collection requirements?

## CP3
|  |  |  | Y | Red
CP3: Appropriate cost allocation methods |  |  |  | N | Amber
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
52 | Have you read the standard?
53 | Have you have read the relevant costing principle and reviewed the relevant spreadsheet in the technical document?
54 | Have you read and understood the definitions for resources and activities?
55 | Have you identified the activities your organisation performs from the prescribed list of activities?
56 | Have you identified the information sources for your activities?
57 | Do you have resources and activities in your costing system?
58 | Have you reviewed the patient facing allocation methods and identified where you are compliant or not?
59 | Have you identified what information you need to be compliant with the prescribed patient facing cost allocation methods?
60 | Have you updated the patient facing cost allocation methods in your costing system?
61 | Have you reviewed the type 2 support allocation methods and identified where you are compliant or not?
62 | Have you identified what information you need to be compliant with the prescribed type 2 support cost allocation methods?
63 | Have you updated the type 2 support cost allocation methods in your costing system?
64 | Where resources are allocated to a number of activities have you calculated the correct apportionment?
65 | Have you updated your costing system with the correct apportionment?
66 | Are you allocating costs equally to activities?
67 | Have you investigated if this is appropriate?
68 | Are you using a fixed cost instead of using it as a weighting in your costing?
69 | Have you investigated if this is appropriate?
70 | If you have a more sophisticated allocation method have you documented it in the integrated costing assurance log (ICAL)?
71 | Do you have a process in place to investigate any costs not driven to an activity, or any activities that have not received a cost and to correct this?
72 | Have you identified traceable costs you can use in the costing process?
73 | Have you investigated which departments have local databases that could provide you with additional information that can be used in costing?
74 | Have you identified where you need relative weight values?
75 | Have you worked with the departments to agree them?
76 | Have you included them in your costing system?
77 | Do you have a rolling programme in place to review?
78 | Have you set up the type 1 support costs relative weight value tables?
79 | Have you set up your costing system to meet the PLICS collection requirements?

## CP4
|  |  |  | Y | Red
CP4: Matching costed activities to incidents and patients |  |  |  | N | Amber
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
80 | Have you read the standard?
81 | Have you have read the relevant costing principle and reviewed the relevant spreadsheet in the technical document?
82 | Can your costing system match 2 ways?
83 | Can your costing system match costed activities to incidents and patients to get to patient unit costs?
84 | Are you able to obtain the incident ID in any or all of your auxiliary feeds?
85 | Have you updated your costing system with the prescribed matching rules?
86 | Can you match to incidents the two categories of activities?
87 | Have you identified which activities should not be matched and how these should be reported?
88 | Have you reviewed the cost allocation methods for matching activities where there isn't a patient level feed?
89 | Have you identified the information you will need to be compliant with these allocation methods?
90 | Have you updated your costing system with these allocation methods?
91 | Have you developed your list of 'unlikely matches'?
92 | Have you collected data on the proxy for the number of patients to allocate costs to patients in multiple patient incidents?
93 | Does your costing system produce a report showing which matching criteria has been applied?
94 | Do you have a rolling programme in place to review this report and take corrective action if needed?
95 | Do you have a plan in place to share with services and departments the impact unmatched activities due to poor data quality is having on costing?
96 | Have you set up your costing system to meet the PLICS collection requirements?

## CP5
|  |  |  | Y | Red
CP5: Reconciliation |  |  |  | N | Amber
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
97 | Have you read the standard?
98 | Have you have read the relevant costing principle and reviewed the relevant spreadsheet in the technical document?
94 | Does your costing system produce these reports?
95 | Do you have a rolling programme in place to review these reports and to take corrective action if required?
96 | Does your costing system report these costs and activities against these cost groups?
99 | Have you completed the log in ICAL Worksheet 1: Patient level activity feeds?
100 | Have you set up your costing system to meet the PLICS collection requirements?

## CP6
|  |  |  | Y | Red
CP6: Assurance of cost data |  |  |  | N | Amber
Review number | Review required | Review response (Y/N) | Nature of gap | Step(s) required to close gap | Reason step(s) required to close gap are needed (please provide appropriate evidence)
101 | Have you read the standard?
102 | Have you have read the relevant costing principle and reviewed the relevant spreadsheet in the technical document?
103 | Have you familiarised yourself with the assurance tools available to help you?
104 | Have you set up your costing assurance log?
105 | Have you completed your information gap analysis
106 | At the end of the costing process, have you completed your CAT?
107 | Have you reviewed and understood the transition path in the technical document for both the standards and the information requirements?
108 | Do you have a rolling programme in place to maintain good documentation and a clear audit trail of the costing process?
109 | Do you have a rolling programme in place to review the costing outputs with senior managers and clinicians?
110 | Does your organisation have a costing user group?
111 | Do you have in place a programme where you reivew and validate the costing outputs?
112 | Do you use the tools provided to validate your cost submissions?
113 | Do you have a rolling programme where you compare your cost data with your peers?