## Cover Sheet
NHS England Capital Business Case Process and Documents
2026-03-10
Digital Capital Business Case Checklist Workbook
This Business Case Checklist Workbook is a tool to aid development of HM Treasury Green Book compliant business cases
The BC Checklist Introduction tab provides a simple overview of this updated Business Case Checklist and new worksheets, which align to HM Treasury Green Book (2026) and NHS England and Department of Health and Social Care (DHSC) business case requirements and processes. NHS England and DHSC have developed a set of Fundamental Criteria requirements, which must be met before a business case is submitted into the NHS England and DHSC review and approval process. These criteria are included in the checklist.
For business cases requiring NHS England / DHSC approval, please submit a completed checklist alongside the business case to assist the review process.
Workbook Tab - colour guide
For completion - Mandatory worksheets to be completed and submitted as Appendix 1 with the business case
For advice - Introduction and explanation worksheets
For information - The BC Project Data Sheet and additional documentation regarding typical appendices and acronyms to aid completion of the business case

## BC Checklist Introduction
Business Case Checklist Introduction
2024-04-03
A. Workbook Overview
This Digital Capital Business Case Checklist Workbook (alongside the Capital Business Case Checklist) updates the February 2023 published version, and is a tool to aid business case development and review. This checklist covers the Strategic Outline Case, Outline Business Case and Full Business Case stages, with these business cases required for capital schemes that exceed NHS Trust and NHS Foundation Trust delegated limits. Delegated limits were updated in the November 2025 Addendum to the Capital Investment and Property Business Case Approval Guidance for NHS Trusts and Foundation Trusts. The requirements of this checklist should be considered for all capital investments, although there are Short Form Business Cases and Programme of Works templates that can be utilised for capital schemes valued less than £25m. This document can be used either as a live document that records the assurance and core project data for a scheme as it progresses through the business case stages, or as a standalone document that is used for a single business case stage. Tabs can be hidden if not required, although it is anticipated that all relevant mandatory tabs are completed for every business case submission.
B. Fundamental Criteria
NHS England and DHSC have developed a set of Fundamental Criteria against which to assess whether a business case is ready to enter the review and approval process. The Fundamental Criteria for each business case stage (SOC, OBC and FBC) are built into the detailed checklists. These Fundamental Criteria (FC) can be isolated within the Checklist through using the filter on Column G of each checklist. As part of an initial review of any business case submitted for evaluation and review prior to a decision relating to approval of the various stages of the business case process or final approval, that business case and its full complement of appendices is assessed against a number of key or Fundamental Criteria. During this triage, the robustness and completeness of the business case is checked in relation to the standard Fundamental Criteria requirements. These must be satisfied before the case can be considered to enter full national review. It is anticipated that this checklist and the Fundamental Criteria will be used for self-assessment by business case authors, as well as a guide for reviewers to HMT Green Book requirements.
Business Case Checklist Workbook
BC Checklist - Introduction
This worksheet containing a brief explanation of the various tabs in this workbook.
1a. SOC Fundamental Criteria and Checklist (please complete relevant tab and submit to NHSE with your Business Case)
This tab contains the Fundamental Criteria and business case requirements for a Strategic Outline Case (SOC). This can be used both as a self assessment tool for business case authors and as a supplement to the Fundamental Criteria and Detailed Review processes for business case reviewers. To enable quicker approvals, the business case must be submitted to NHSE with a completed self-assessment against the Fundamental Criteria.
1b. OBC Fundamental Criteria and Checklist (please complete relevant tab and submit to NHSE with your Business Case)
This tab contains the Fundamental Criteria and business case requirements for a Outline Business Case (OBC). This can be used both as a self assessment tool for business case authors and as a supplement to the Fundamental Criteria and Detailed Review processes for business case reviewers. To enable quicker approvals, the business case must be submitted to NHSE with a completed self-assessment against the Fundamental Criteria.
1c. FBC Fundamental Criteria and Checklist (please complete relevant tab and submit to NHSE with your Business Case)
This tab contains the Fundamental Criteria and business case requirements for a Full Business Case (FBC). This can be used both as a self assessment tool for business case authors and as a supplement to the Fundamental Criteria and Detailed Review processes for business case reviewers. To enable quicker approvals, the business case must be submitted to NHSE with a completed self-assessment against the Fundamental Criteria.
2. List of Appendices - Optional
This worksheet provides a long list of typical business case appendices. Mirroring the core Checklists for SOC, OBC and FBC, this appendices list identifies those that are relevant and important for Digital / Tech schemes.
3. Glossary of Business Case related Acronyms - Guidance only
Glossary of typical business case acronyms.

## 1a. SOC FC +Checklist
2a. Strategic Outline Case (SOC) Checklist | [19 empty] | Provider Self Assessment |  | Regional Fundamental Criteria Assessment |  | Additional Checklist Information
2026-03-10
5 Case Model Heading | Sub-Heading | Business Case Checklist Reference Number | Category | Discipline / subject matter covered Formal or possible associated input / interest | Fundamental Criteria | Commissioning | Design Review. Design Appraisal | Clinical | Finance | Estates | Estates Standard Review | Assurance | Strategy | Economics | Policy | Workforce | NHP (New Hospital Programme) | Digital BC | Item / Section See Note B. on Introduction about Fundamental Criteria (FC) Where confirmation is asked for in the requirement, evidence should be provided with that confirmation. Light blue cell shading identifies the current FC item in the various sections | Provider Self Assessment RAG Rating Yes = Green Partly = Amber No = Red Completed by Provider | Where is this covered in the Business Case? Document, Appendix, section and / or page | Regional Fundamental Critiera RAG Rating Yes = Green Partly = Amber No = Red Completed by Regional FCR Reviewer | Please highlight in this column any areas where the Fundamental Criteria have not been fully met. | General Notes and Guidance Any links and guidance provided in this checklist may change over time. The Trust / ICB must therefore always establish that the guidance used is current and appropriate.
Strategic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Strategic | Workshop | 1.1.1 | Workshop 1 Green Book | Assurance Digital | [14 empty] | Workshop 1 undertaken - Determining the Case for change. |  |  |  |  | Green Book and associated guidance documents. Mandated workshop requirement | bar: AS; DI
Strategic | Approval and Support | [17 empty] | Approval and Support | bar: FC to DI
Strategic | Approval and Support | 1.2.1 | Board approval | Assurance Digital | FC: FC; AS: AS; DI: DI | Trust Board Approval - Confirm the date when the business case was approved by the Trust Board. Submission Requirements - The Business Case should be submitted with completed self-assessed Fundamental Criteria Checklist, to ensure that core requirements are met. This will enable swifter approvals. Letters of Support - ICB and Trust - The Business Case should be submitted with a Letter of Support from both the ICB as strategic commissioner and the Trust. Guidance on Letters of Suppport content and template letters are set out in Annex 3 of the NHSE Capital investment and property business case approval guidance. The Letters of Support should include the following (template lettes are included in Annex 3) - ICB Letter - Support for the business case, public consultation requirements have been met, alignment with ICB strategic commissioning/clinical strategy, affordability. - Trust Letter - Trust Board approval, capital affordability, revenue affordability, accounting treatment, alignment with local estates, digital and workforce strategies, deliverability. Cabinet Office (CO) Commercial Controls - If any of the contracts within the scheme are expected exceed the Cabinet Office Controls threshold the Trust will need to ensure that this contract value is reported onto the Regional Commercial Pipeline for CO oversight, and that the "Business Case Six Test Checklist" is completed and accompanies the business case submission. Trusts that will require CO approval should refer to this within their business case and ensure there is sufficient time to secure CO approval within the programme plan. |  |  |  |  | Provide minutes of the Board / Governing Body meeting approving the business case. The Board/Governing Body has approved all parts of the business case, e.g. strategic fit and the financial/operational impact. If there is more than one SRO / approving body, then the senior or lead SRO should take responsibility for submitting the case. The significance of the SRO role at this stage is to show ownership, and to formally signify the start of the review / approval process.
Strategic | Approval and Support | 1.2.2 | HMT guidance followed | Assurance Digital | [14 empty] | Confirm that the HMT Green Book has been followed in developing the business case. | bar: AS; DI
Strategic | Approval and Support | 1.2.3 | Digital and Technology Assurance Questions | Assurance Digital | [14 empty] | Trusts should confirm that their Business Case is accompanied by a completed Digital and Technology Question Set. These have been published on the NHS Futures Sharepoint, with access provided by the Transformation Directorate team. Reference should be made to the Trust’s strategy for cloud data storage, and alignment with Government and NHS Public Cloud Hosting Policy. Trust should engaged with the Cloud Centre of Excellence and address any recommendations from that engagement as it is expected they meet the NHS Public Cloud Hosting policy. The assessment form for the EPR Technology & Digital Assessment may be found on the Frontline Digitisation Support Offer webpages on the NHS Futures Sharepoint or the related MS Teams Channel. | bar: FC
Strategic | Strategic and Policy Context |  |  |  | FC |  |  | CL | FI | ES | ESR | AS | ST |  | PO |  |  | DI | Strategic and Policy Context
Strategic | Strategic and Policy Context | 1.3.1 | Strategic Context | Clinical Finnce Estates Strategy Policy Digital | FC: FC; CL: CL; FI: FI; ES: ES; ST: ST; PO: PO; DI: DI | The context and case for change should be set out clearly, with local and national drivers for the change identified. The Trust should show how the proposals align to government and DHSC policy. This case for change should be evidence based and should articulate the proposed clinical model, underpinned by demand and capacity modelling. It should demonstrate: - the links to enabling strategies, e.g. workforce, patient experience and patient safety; - consideration of quality, workforce and financial / efficiency considerations; - stakeholder engagement, including with clinical leaders and trust staff to assess clinical oversight and involvement in the business case development; - alignment with both local and national service configuration, commissioning intentions and patient-centred design and build; - consistency with Trust digital strategy. A link or copy of the strategy should be appended or made available. - a clear commitment to IT systems interoperability should be made to the effect that 'any digital technology deployed, must be compliant with all relevant functional and interoperability standards. We need to be clear that the organisational overview sets out the relationship with key partners, in delivering care, patient flow etc, in addition to an overview of which trusts and hospitals are involved e.g. Acute, Community, Mental Health, Ambulance, how many beds, how many staff, how many in-patient episodes, and out-patient episodes. Also the latest CQC rating. The 'case for change' should also focus on the current gaps in local digital services as well as future gaps against business plans and strategy. Brief Reference to relevant national policy and strategy drivers e.g., national published documents such as the 'Ten-Year Health Plan: Fit for the Future' is advised. Clear case for change including presentation of the ICB roadmap and trust existing digital landscape, (with a graphical diagram or table) and indication of current digital maturity, and identifying gaps, problems, and opportunities, for improving productivity and reducing clinical risk against the national and ICB and local business strategy and published guidance i.e., the digital baseline. Inclusion of a good evidence base can help to support generalisations that are often made around patient experience, clinician’s needs that are not direct consequences of digitisation. The SOC may incorporate the outcomes of an initial Agile discovery and Alpha phase or pilot. For Agile Digital Projects an overall PBC should be considered. |  |  |  |  | For EPR Cases the strategy is to achieve a minimum Digital Maturity of HIMSS Level 5 / MDF with a view to be able to reach HIMSS 6 or 7 with future extension / optimisation of the solution The regional team should review and confirm the Digital Strategy / Management is robust and fits with Region and ICS digital strategy. Assurance is sought from Regional Digital leads that the case fits with regional convergence (Requirements and relevant standards may change over time)
Strategic | Strategic and Policy Context | 1.3.2 | Consultation | Commissioning Digital | FC: FC; CO: CO; DI: DI | Provider confirmation that the organisations consulted with global digital exemplars or very digitally mature trusts and accessed the digital blueprint library on the NHS Futures site.
Strategic | Strategic and Policy Context | 1.3.3 | Engagement and Integrated Working | Commissioning Design Review Design Appraisal Clinical Finance Estates Assurance Strategy Digital | CO: CO; DR DA: DR DA; CL: CL; ES: ES; AS: AS; ST: ST; DI: DI | The Trust should provide evidence of how the lead commissioning organisation has engaged with their patients and / or users, stakeholders, wider public / population and governors (as appropriate) in setting the clinical and service priorities that led to the scheme design and objectives. The case should provide evidence as to what extent the proposal will or has promoted integrated working between health, social care and public health. This should include alignment to the Integrated Care Addendum documentation, and should reflect on any post-project evaluations relating to the current service. In proposals that aim for ‘transformation change’, the nature of the change needs to be transparently explained, with objective evidence on which it is based and objective support for the assumptions made. A credible explanation of the change process is required, with detail as to how uncertainty will be handled. Annex A7 of the HMT Green Book needs to be understood and considered. For Digital Technology projects, Discovery and Alpha phases will precede the SOC and inform the direction of the project.
Strategic | Strategic and Policy Context | 1.3.4 | Patient Choice | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that the scheme will support greater patient choice on where and how to access care, and / or improved quality and safety of service provision |  |  |  |  | See Operational Guidance to the NHS: extending patient choice of provider.
Strategic | Strategic and Policy Context | 1.3.5 | Equality and Diversity | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that any equality and diversity impact has been assessed and actively addressed. |  |  |  |  | The proposal must pay due regard to the public-sector equality duty in line with the principles and requirements of the NHS Constitution and with current legislation and guidance.
Strategic | Strategic and Policy Context | 1.3.6 | Service Reconfiguration Tests | Clinical Finance Estates Strategy | CL: CL; FI: FI; ES: ES; ST: ST | If the scheme involves changes to services, confirm that the four key tests for service reconfiguration will be met. Evidence should be provided. Please refer to the Planning Assuring Delivering Service Change V6-1 for detailed guidance |  |  |  |  | The four key tests for service reconfiguration were set out in Planning Assuring Delivering Service Change V6-1 • Strong public and patient engagement. • Consistency with current and prospective need for patient choice. • Clear, clinical evidence base. • Support for proposals from clinical commissioners. NHS England introduced a new test applicable from 1 April 2017. This requires that in any proposal including plans to significantly reduce hospital bed numbers NHS E&I will expect commissioners to be able to evidence that they can meet one of the following three conditions: i. Demonstrate that sufficient alternative provision, such as increased GP or community services, is being put in place alongside or ahead of bed closures, and that the new workforce will be there to deliver it; and/or ii. Show that specific new treatments or therapies, such as new anti-coagulation drugs used to treat strokes, will reduce specific categories of admissions; or iii. Where a hospital has been using beds less efficiently than the national average, that it has a credible plan to improve performance without affecting patient care (for example in line with the Getting it Right First Time programme).
Strategic | Strategic and Policy Context | 1.3.7 | Social Value | Clinical Finance Estates Strategy Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; ST: ST; DI: DI | Describe the social value themes that have been under taken in the assessment, share your timed action plans and confirm that 10% minimum of scoring is weighted to social value.
Strategic | Rationale and Objectives |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC |  |  | NHP | DI | Rationale and Objectives
Strategic | Rationale and Objectives | 1.4.1 | SMART / Strategic Objectives | Digital | [13 empty] | DI | The SOC needs to identify the SMART (Specific, Measurable, Achievable, Relevant, and Timebound) spending objectives associated with the project, and set out reasonable spending objectives linked to benefits. These objectives will need to be linked with Critical Success Factors and the identified benefits. These objectives will also need to link to wider government strategic priorities, as set out in the case for change, as well as directly link to Fit for the Future: 10 Year Health Plan for England priorities. Clear Investment or Spending Objectives must be linked to key strategy or business gaps such as replacement of legacy, levelling up capability, compliance, improving productivity, clearly derived from the strategic context and case for change. It should be clear that the investment is about clinical service transformation outcomes, improvement, and risk reduction, not just the technology. It may be more appropriate to develop a programme business case to look at a range of digital projects and services, phased over time, that could achieve better transformation and outcomes, particularly at ICB level. | bar: FC
Strategic | Clinical Quality |  |  |  | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  |  | Clinical Quality
Strategic | Clinical Quality | 1.5.1 | Delivery | Commissioning Clinical Finance Estates Strategy Digital | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  | DI | The SOC should describe how the scheme will support the delivery of the organisation’s clinical strategy and aligned to commissioning intentions as supported by the Provider Estate / Digital Strategy, and provide confirmation of when the organisation's clinical strategy was completed and signed off.
Strategic | Risks, Constraints and Dependencies | [5 empty] | DR DA | CL | FI | ES | ESR | AS | ST |  |  |  |  | DI | Risks, Constraints and Dependencies
Strategic | Risks, Constraints and Dependencies | 1.6.1 | Constraints and Dependencies | Digital | [13 empty] | DI | Key constraints and dependencies should be identified, particularly those separate projects, e.g. infrastructure improvements on which the successful delivery of this project will depend. The constraints should relate to standards and conformance with technology code of practice and other GDS and Transformation Directorate guidance can be brought out. e.g. 'digital first' principles. |  |  |  |  | This is particularly important if there are any interdependencies, especially benefits, with other investments / procurements.
Strategic | Strategic and Policy Context | 1.6.2 | Carter Efficiency | Finance Estates | FI: FI; ES: ES; ESR: ESR |  |  |  | DI | The Trust should confirm that the project complies with relevant Carter efficiency recommendations in Lord Carter of Coles 2015 report - Operational productivity and performance in English NHS acute hospitals: Unwarranted variations, and identify the recommendations being delivered by the project. |  |  |  |  | The case should refer to Lord Carter of Coles 2015 report: Operational productivity and performance in English NHS acute hospitals: Unwarranted variations, and identify the recommendations being delivered by the project.
Strategic | Strategic and Policy Context | 1.6.3 | Integrated Care and Digital Convergence | Finance Estates | [13 empty] | DI | The Trust should provide details of the strategy for delivering integrated care and convergence of digital solutions across the ICS, within the case or supporting documentation. | bar: FI to ES
Strategic | Risks, Constraints and Dependencies | 1.6.4 | Digital Technology Capability | Digital | [13 empty] | DI | Provide a summary of the organisation's current Digital Technology capability. Confirm that this identifies the starting point for development of the Digital technology schemefor example. This should include the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise. |  |  |  |  | An annex may include, for example, the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise.
Strategic | Risks, Constraints and Dependencies | 1.6.5 | Gap in Digital Technology Provision | Digital | [13 empty] | DI | Confirm that the "gap" in Digital Technology provision, between the current position and the identified objectives supporting health service delivery, is known.
Strategic | Risks, Constraints and Dependencies | 1.6.6 | Government Standards | Digital | [13 empty] | DI | Confirm that the programme demonstrate awareness and compliance with the relevant government standards and policies for technology. Confirm how it ensures these will be met. Confirm the applicability of the Technology Code of Practice and Digital by Default Service standard . |  |  |  |  | The Technology Code of Practice and Digital by Default Service standard always apply.
Strategic | Risks, Constraints and Dependencies | 1.6.7 | Options Analysis | Digital | [13 empty] | DI | Ensure and confirm that the options analysis concerning the delivery approach for digital is supported by adequate analysis of user, as opposed to stakeholder, needs. |  |  |  |  | Services that are driven by policy without appropriate meeting of user needs are far less likely to deliver the claimed benefits due to low adoption rates.
Strategic | Risks, Constraints and Dependencies | 1.6.8 | MVP | Digital | [13 empty] | DI | Confirm that the digital programme has established the criteria to be met by the Minimum Viable Product (MVP)
Strategic | Risks, Constraints and Dependencies | 1.6.9 | Service Assessment Scope | Digital | [13 empty] | DI | Confirm that the digital programme or any component is within the scope of service assessments. If so, the case should confirm at what stage and what were the outcomes of that assessment. |  |  |  |  | Service assessments are mandatory at alpha, beta and live stages of programmes. Failure to pass can prevent the programme continuing to the next stage or even prevent live deployment.
Strategic | Risks, Constraints and Dependencies | 1.6.10 | Technical Decisions | Digital | [13 empty] | DI | Confirm that the options analyses consider technical decisions and justify the preferred digital option. Buy versus build, proprietary versus open source , co-location or in-house provision versus cloud hosting et |  |  |  |  | Buy versus build, proprietary versus open source , co-location or in-house provision versus cloud hosting etc.
Economic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Economic | Workshop | 2.1.1 | Workshop 2 Green Book | Assurance Economics | [14 empty] | Workshop 2 completed: Assessing the Options: longlist and preliminary short list (using the Options Framework filter |  |  |  |  | Green Book and associated guidance documents. Mandated workshop requirement | bar: AS; EC
Economic | Options Appraisal |  |  |  | FC | CO | DA | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | Options Appraisal
Economic | Options Appraisal | 2.2.1 | Options Framework / Long List | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | FC | CO |  | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | The business case must identify Critical Success Factors (CSFs), develop the long list using the Options Framework, and appraise options by filter against the spending objectives and CSFs. Place-based impacts should also be considered in this process. The longlist identification and appraisal should be well detailed in the SOC to evidence how the business case has a workable shortlist that excludes unrealistic options. Guidance for the Options Framework can be found in the Green Book and accompanying Guide to Developing the Project / Programme Business Case. The SOC should demonstrate that the Trust have identified potential ‘scopes’ for the coverage of the project, ranging from business as usual (BAU), through to the ‘do minimum’, and ‘do maximum’ and intermediate options. The Options Framework guidance can be found within the Guide to Developing the Project Business Case guidance, published alongside the Green Book. This Long List appraisal should be well detailed in the SOC to evidence how a Trust has developed a workable short list for OBC. Demonstration of a preferred way forward is required. High level options appraisal of the potential scope of solutions, in terms of organisations and departments covered, and functional capability provided along with consideration of options for the implementation approach. Diagrams or tables may be helpful in showing how the functionality and coverage of legacy systems compare with their replacement by or interfacing with new systems. For trusts where they are combining together in a joint procurement for a single solution or where there are several projects consisting, for example of a mix of clinical digital information solutions and infrastructure phased over time, an overarching PBC setting out the options for scope and functionality and optimal order of phasing of projects should be considered. |  |  |  |  | Options should be identified using a range of parameters. Suitable parameters may include scope, implementation approach, timing, scale. Use of a feasibility study is recommended. See Green Book
Economic | Options Appraisal | 2.2.2 | Options Framework / Short List | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | FC | CO |  | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | The SOC should identify a minimum of four shortlisted options for further appraisal. Only in exceptional circumstances, and with prior agreement with DHSC Economists, can business cases be submitted with a short list of less than four. The short list should include: - Business As Usual (BAU) – acts as a "Do Nothing" benchmark for Value for Money - ‘Do Minimum’ – a realistic way forward that also acts as a further benchmark for Value for Money. This option should set out the minimum capital investment required to deliver the core spending objective(s) underpinning the case for change. - A recommended Preferred Way Forward (PWF), that combines the PWF options from all filters, unless this is identical to the Do Minimum. - One or more other realistic options, that use 'carried forward' options from at least one filter to become a more- or less-ambitious PWF. The presentation of the shortlist options in the economic case should be easily relatable to the presentation of the shortlist options in the Capital Investment Appraisal (CIA) model. |  |  |  |  | A minimum of 4 options have been shortlisted and costed in the CIA model. In addition to the BAU, there should be at least 3 viable options, each of which deliver the SMART objectives If there are not 4 options, there is a clear rationale for this which is discussed with other keyholders ahead of the FC review meeting. If omitted this may lead to delays while the economic case is reworked before it can be progressed to detailed review stage. The BAU and do min options should be "true" BAU and do min options and in line with the investment objectives for the case. - “BAU” should reflect the continuation of current arrangements as if the intervention under consideration were not to happen. This serves as a benchmark to compare alternative interventions even where this is an unviable option - “Do min” refers to the minimum intervention required to deliver core objectives only. This must be a realistic and achievable do minimum based on the core functionality and essential requirements for the project. It meets the ‘core’ scope and essential business needs of the project.
Economic | Options Appraisal | 2.2.3 | DPIA | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST; EC: EC; PO: PO; DI DI: DI | As part of the workshops and evalaution of options for new projects, programmes, or other activity which involves a new use of Personal Data, the SRO should assess the risks of data management. A Data Protection Impact Assessment (DPIA) is a process used to identify and minimise data protection risks when processing personal data. A DPIA should be provided with the SOC.
Economic | Risk | [6 empty] | CL | FI | ES | ESR | AS |  | EC |  | WO | NHP | DI | Risk
Economic | Risk | 2.3.1 | Risks and Mitigations | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the risks and mitigations associated with the project options been identified |  |  |  |  | Risks, constraints and dependencies should be consistent with the strategic case – where they should have been described.
Economic | NPSV, Optimism Bias and Sensitivity Analysis |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | NPSV, Optimism Bias and Sensitivity Analysis
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.4.1 | CIA Shortlisted Options | Digital | [14 empty] | There should be an indicative cost, benefit and risk appraisal performed on the four options, demonstrating a Net Present Social Value (NPSV) and benefit cost ratio to justify the preferred way forward at an early stage, albeit it is accepted that this will need further development at OBC stage. Business cases are required to present Short List options using the Digital Capital Investment Appraisal (CIA) model at the earliest stage to ensure continuity in the development of the economic case from SOC through OBC to FBC. There must be a clear reconciliation between the costs and cash releasing benefits in the economic case (and the CIA) and those used in the financial case. | bar: FC; DI DI
Economic | Summary |  |  |  | DR DA: DR DA; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | Summary
Economic | Summary | 2.5.1 | Consistency Across Case and Annexes | Design Appraisal Finance Estates Economics | DR DA: DA; FI: FI; ES: ES; EC: EC | Confirm all supporting evidence (e.g., in Annexes) consistent with the results in the main text of the business case. Where annexes are relevant, they must be referenced within the business case.
Commercial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Commercial | Procurement Strategy |  |  |  | FC: FC; FI FI: FI; ES ES: ES; ES ESR: ESR; ES AS: AS; EC NHP: NHP; EC DI: DI | Procurement Strategy
Commercial | Procurement Strategy | 3.1.1 | Procurement Strategy | Finance Assurance Digital | FC: FC; FI FI: FI; ES AS: AS; EC DI: DI | A competitive procurement should be proposed, through either the Health Service Systems Framework or the London Procurement Partnership Clinical Digital Information Systems Framework. This is mandatory for centrally funded EPR initiatives, requiring Transformation Directorate endorsement to ensure standard terms and conditions to support maximum standards compliance, unless there is a very good case set out for doing otherwise. e.g. Where some digital services that are not on either of these frameworks. A direct award will only be considered in exceptional circumstances and must comply with Public Contract Regulations (PCR 2015), local SFIs and supported by appropriate legal advice. It will require a full cost risk benefits economic analysis at OBC and FBC. A statement should be included that 'any digital technology deployed, must be able to demonstrate 'compliance with all relevant functional and interoperability standards'. This requirement will be met by the use of HSSF and LPP CDIS for procurement of EPR solutions. Where appropriate set out 'set out how any new products or services, for service users or professionals developed as part of this project, will meet level AA of the Web Content Accessibility Guidelines (WCAG 2.1) and flag any gaps https://www.gov.uk/service-manual/helping-people-to-use-your-service/understanding-wcag. |  |  |  |  | Clear, realistic procurement key milestones and delivery dates should be set out. Supplementary questions could focus on managerial capacity to deliver to timeline. Caution should be exercised in relation to overly optimistic timelines which have no contingency for slippage. The experience of capital procurement processes generally is that it invariably takes longer than anticipated.
Commercial | Procurement Strategy | 3.1.2 | Fraud Risk | Finance Estates Digital | FI FI: FI; ES ES: ES; EC DI: DI | SROs and Board to confirm that counter fraud measures focus on clear governance, procedures and responsibilities to counter fraud, including staff training, preventing, detecting, reporting and investigations. There are clear rules and duties of due diligence which must be adhered to when awarding purchasing contracts or other decisions (such as the awarding of grants). For major new areas of spend, an initial assessment of how fraud may occur and the potential impacts this will have should be conducted referencing the Government Fraud Risk Assessment Standard. This must be informed by consultation with relevant counter fraud experts and stakeholders at the earliest point in the business case process. For all proposals, proportionate counter fraud measures should be built into the design as a constraint and therefore as a requirement of all viable options. The Professional standards and guidance for fraud risk assessment in government should be referred to for additional information. |  |  |  |  | The type of risk and where it resides will depend on a number of factors including the type of contract employed. The process and achievement of risk transfer must be described and confirmed as having been achieved where applicable.
Commercial | Personnel |  |  |  | DA DR DA: DR DA; ES ES: ES; ES ESR: ESR; ES AS: AS; EC WO: WO; EC NHP: NHP; EC DI: DI | Personnel
Commercial | Personnel | 3.2.1 | Personnel Implications | Workforce | [14 empty] | The SOC should state explicitly whether the scheme has any implications for personnel, including whether there would be expected to be any transfer of staff. The case should confirm if TUPE is anticipated to apply. |  |  |  |  | TUPE – Transfer of Undertaking, Protection of Employment Regulations 2006 (and as updated since). This protects the employment conditions of public sector staff transferring to the private sector. Also see NHS Standard Contract, Fair Deal for Staff Pensions, Draft Template Schedule 7 and Accompanying Guidance | bar: EC WO
Commercial | Net Zero Carbon |  |  |  | FC: FC; FI FI: FI; ES ES: ES; ES ESR: ESR; ES AS: AS; EC NHP: NHP; EC DI: DI | Net Zero Carbon
Commercial | Net Zero Carbon | 3.3.1 | Net Zero Carbon | Digital | [14 empty] | The case should set out any requirements or opportunities for digital investment to contribute to net zero carbon: * Carbon costs in the tech stack (hosting, networks, devicing) should be minimised (both operation and embodied). * Potential carbon benefits from digitisation should be identified e.g. increased productivity, decreased number of provider visits / length of stay, changes in travel patterns etc. * Climate change risks to the digital service should be considered via provider climate change risk assessments and supplier engagement |  |  |  |  | For further detail explore the Technology Code of Practice sustainability principle and it's assurance requirements around compliance to the HMG GGC ICT and Digital Services Strategy objectives. Tooling available on request: net carbon impact calculator, low CO2 digital service design checklist, digital service climate change risk assessment and mitigation planning tool | bar: EC DI
Financial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Financial | Overall Affordability |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Overall Affordability
Financial | Overall Affordability | 4.1.1 | Overall Affordability | Finance Digital | [14 empty] | Confirm the financial case includes an overview of: (i) The organisation's financial position (ii) The resources available for the project / programme (iii) Any capital and revenue constraints (iv) Statements in relation to content of Letters of Support from ICBs as strategic commissioners and from the Trust. | bar: FI; DI DI
Financial | Financial Model |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Financial Model
Financial | Financial Model | 4.2.1 | Financial Model | Finance Digital | [14 empty] | (i) Confirm a financial model been developed, with plans to keep it under continuous review and updated. (ii) Confirm the financial model includes the minimum requirements, including • Agreement and recording of underlying assumptions • Funding • Input schedules for costs, cash releasing benefits, risks and contingencies • A reconciliation of demand, capacity, workforce and financial assumptions • Projected financial statements - SOCI, SoFP, Statement of Cashflows (ii) Does the Long Term Financial Model cover an appropriate term (BAU, construction, steady state) | bar: FI; DI DI
Financial | Capital Affordability |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; NHP: NHP; DI DI: DI | Capital Affordability
Financial | Capital Affordability | 4.3.1 | Capital Affordability | Digital | FC: FC; FI: FI; DI DI: DI | The case must demonstrate that the costed proposals are affordable within either operational capital allocations or within national programme funding allocations. Risk, Contingency and Optimism Bias should be appropriately calculated for SOC stage and inflation assumptions clearly stated. The SOC should also include fully costed and completed Cost Forms for all short listed options The capital cost for the preferred option will need to reconcile fully across the fully completed Cost Forms, the Financial Case and the CIA. The case will need to set out the Sources and Applications of capital funding for delivery of this scheme, as well as the proposed profile of expenditure of these capital sources. If operational capital envelopes are used to support the scheme, the Sources and Applications presentation should align with the Letter of Support from the Trust (see above). Indicative costs should take account of associated infrastructure, and implementation with business change. High level estimated capital and revenue costs should be shown over an assumed contract period |  |  |  |  | To support the FCR the case should clearly demonstrate capital affordability. The capital spend profile and values should align with funding agreed and clearly demonstrate CDEL affordability within any funding award/allocation, e.g., national programme PDC funding allocations and/ or within system operational capital allocations as confirmed in the system letter of support. Any national programme funding assumptions in the financial case must be profiled, and the scheme is completed in line with the key dates set by the relevant programme as a condition of funding award. The financial case should include a capital source and application of funds table which demonstrates the profiled CDEL impact of the investment, which correctly takes into account any CDEL credits, i.e. disposals, grants or donations. The case should also correctly take account of any early funding drawn to date and spend incurred The assumptions and the affordability statements in the case should be supported by the system per the letter of support. The financial case should ensure any matched funding requirements (Capital and or revenue) are met and should clearly set out the assumptions made.
Financial | External Funding Sources |  |  |  | FI: FI; NHP: NHP; DI DI: DI | External Funding Sources
Financial | External Funding Sources | 4.4.1 | External Funding | Finance Digital | [14 empty] | Confirm that any elements to be funded from external sources been identified, with the profile of funding / spend by year. | bar: FI; DI DI
Financial | External Funding Sources | 4.4.2 | Borrowing | Finance Digital | [14 empty] | Where borrowing is assumed, the case should set out whether this is anticipated to be DHSC or commercial borrowing, as well as confirming whether the NHS organisation has the ability to borrow. Trusts should refer to the DHSC S42a guidance on financing outside of the DHSC group: https://www.gov.uk/government/publications/guidance-on-financing-available-to-nhs-trusts-and-foundation-trusts/secretary-of-states-guidance-under-section-42a-of-the-national-health-service-act-2006#financing-from-outside-the-dhsc-group The case should set out the value of the expected loan, the assumed term and interest. The repayments and affordability should be assessed and clearly stated. | bar: FI; DI DI
Financial | Revenue Affordability |  |  |  | FC: FC; FI: FI; WO: WO; NHP: NHP; DI DI: DI | Revenue Affordability
Financial | Revenue Affordability | 4.5.1 | Revenue Affordability | Workforce Digital | FC: FC; FI: FI; WO: WO; DI DI: DI | The SOC should include an incremental Statement of Comprehensive Income, Statement of Cashflows and Statement of Financial Position and Trust-wide Statement of Comprehensive Income including the impact of the proposed investment. Any short-term worsening of the revenue position will need to be mitigated as much as possible at the SOC stage with the organisation working with partners to describe the mitigations in more detail at the OBC stage. There should be clear alignment and a reconciliation included that details the alignment of the revenue assumptions in the CIA and Financial case (including cash releasing benefits) for the Preferred Way Forward. Indicative costs should take account of attributable costs of infrastructure, and implementation with business change. High level estimated revenue costs should be shown over an assumed contract period. |  |  |  |  | To support the FCR the case should clearly demonstrate revenue affordability. The Trust should provide a working file to support the calculation of the statements. Any revenue funding assumptions should align with approved national programme funding allocations and confirmed in writing. Where additional revenue is assumed from Commissioners / ICB this should be clearly set out in a letter of support. The financial case should ensure any matched funding requirements (Capital and / or Revenue) are met and should clearly set out the assumptions made.
Financial | Revenue Affordability | 4.5.2 | Efficiency Savings | Finance | [14 empty] | Confirm and detail any efficiency savings as a consequence of the scheme based on reasonable assumptions | bar: FI
Financial | Special Purpose Vehicles / Subsidiaries |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP | Special Purpose Vehicles / Subsidiaries
Financial | Special Purpose Vehicles / Subsidiaries | 4.6.1 | SPV / Subsidiary | Finance Estates | FI: FI; ES: ES; ESR: ESR | If the organisation is intending to create an SPV, Joint Venture or Subsidiary, or where the proposal includes materially changing a Subsidiary, the business case must follow the approval process described in NHSE guidance - Guidance for assuring and supporting complex change – subsidiaries guidance for trusts forming or changing a subsidiary - before NHS Trusts and Foundation Trusts can implement such plans. |  |  |  |  | Additional review requirements for NHS Trusts For all NHS Trust subsidiary proposals, the business case must demonstrate to the Secretary of State that the subsidiary is income generating. We will co-ordinate our review process (if triggered) with that for obtaining Secretary of State consent on a case-by-case basis, considering the inherent risks of each proposal. This includes determining whether we should complete our review before the trust obtains the required consent from Secretary of State. Trusts should inform NHS England of proposals at the earliest opportunity so that we can align the review processes.
Financial | Technical Checks |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Technical Checks
Financial | Technical Checks | 4.7.1 | Revenue / Capital Split | Finance Digital | [14 empty] | Confirm the split of costs between revenue and capital in-line with the current capitalisation policy. | bar: FI; DI DI
Financial | Technical Checks | 4.7.2 | Ownership of Capital Assets | Finance Digital | [14 empty] | Where the Business Case includes the purchase or creation of capital assets the SOC should be clear which organisation will own the assets and whose asset register they will sit on. | bar: FI; DI DI
Financial | Technical Checks | 4.7.3 | Recharges | Finance Digital | [14 empty] | The SOC should set out any re-charges to other organisations that result from this scheme, with the recovery of costs or income generated factored into the case. | bar: FI; DI DI
Financial | Technical Checks | 4.7.4 | Procurement Costs | Finance Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm the procurement costs have been clearly set out, including the basis for internal costs of the project team and the costs of advisers and technical support
Financial | Technical Checks | 4.7.5 | Leases | Finance Digital | FI: FI; ES: ES; DI DI: DI | Where leases are being entered into, confirm these have been correctly accounted for as finance or operating leases in accordance with the applicable accounting standards.
Commercial | Technical Checks | 4.7.6 | VAT Recovery | Finance Digital | ES: ES; ESR: ESR | Confirmation of VAT expectations, and the basis for any assumption around VAT Recovery. |  |  |  |  | This VAT recovery Service is provided free of charge to NHS Clients using the Procure Framework. If this is not used, justification should be provided.
Financial | Contingencies |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Contingencies
Financial | Contingencies | 4.8.1 | Contingency Plans | Finance Digital | FI: FI; ES: ES; DI DI: DI | Confirm contingency plans are described, e.g. for alternative sources of funding, if assumptions turn out to be wrong or insufficient. The SOC should set out any flexibility to fund any additional revenue requirements or to absorb any affordability gaps that emerge. The case should also set out any possible contingent liabilities.
Financial | Contingencies | 4.8.2 | Optimism Bias | Finance Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that optimism bias set at the correct level, in accordance with the HMT Green Book.
Management |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Management | Other | 5.1.1 | All Documents and Appendices Complete and Included | Assurance | [14 empty] | Confirm all relevant documents and appendices been completed, checked, signed off, listed in the business case and confirmed to be submitted with the Business Case when it is submitted for the review and approval process. Missing documents may cause delay or rejection in relation to the approval process. | bar: ESR AS
Management | Project Plan | [5 empty] | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO |  | NHP | DI | Project Plan
Management | Project Plan | 5.2.1 | Project / Delivery Plan | Clinical Finance Estates Strategy Economics Policy Digital |  |  |  | CL | FI | ES | ESR |  | ST | EC | PO |  |  | DI | The SOC should set out a high level project plan with delivery dates and milestones for the key activities that will be undertaken across the life of the project. |  |  |  |  | The project plan should cover key milestone dates including approvals, future contract management and operational plans. It could take the form of, or be accompanied by, a Management Control Plan.
Management | Project Plan | 5.2.2 | Workstream Interdependencies | Design Review Assurance |  |  | DR DA: DR; ESR: ESR; AS AS: AS |  |  |  | The case should confirm other work stream milestones and their interdependencies with the proposal. |  |  |  |  | Other work streams may include workforce, equipment, training, benefits delivery Clear delivery dates and detailed milestones should be provided.
Management | Project Plan | 5.2.3 | Gateway Reviews | Assurance | [14 empty] | If there has been a Gateway Review to date on the project or programme, the SOC should set out the outcomes of the review process and identify any actions taken to comply with the recommendations and/or requirements of the review. | bar: AS AS
Management | Project Plan | 5.2.4 | Post-Implementation and PPE | Design Appraisal Clinical Finance Estates Assurance Strategy Economics |  |  | DA | CL | FI | ES | ESR | AS | ST | EC |  |  |  |  | PPE is an important element of any scheme to ensure lessons are learned and improvements made across all aspects of Capital Projects. The trust is to confirm that PPE lessons from previous schemes have been implemented in this scheme and that records are being maintained to enable a full and complete PPE to be prepared and completed for this project. It should also be noted that NHSE have a mandatory requirement that detailed project outturn costs are provided promptly as part of the PPE process. Annex 2 of the Capital Guidance includes post-project evaluation templates that can be utilised by Trusts in undertaking this exercise: https://www.england.nhs.uk/wp-content/uploads/2023/02/B1376iii-annex-2-post-project-evaluation-templates.pdf
Management | Project Management |  |  |  | FC |  | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO |  | NHP | DI | Project Management
Management | Project Management | 5.3.1 | Project Management | Digital | FC | [12 empty] | DI | The Case should identify the SRO for the project and have identified specific resource to make up a project team. The structure of the programme team and governance arrangements should be identified. The experience of the SRO and programme team in delivering major schemes should be clearly set out to demonstrate the capacity and capability of the team to deliver the project, as well as the budget and resources required to deliver the project. A Risk Potential Assessment (RPA) to be completed and appended. Leadership and governance arrangements, at the SOC stage, should be set out in full, taking account of involvement of key external and internal roles required and named individuals in senior roles. Capability of Senior Digital Leadership has been proven / demonstrated e.g. with Qualifications, Seniority & Collective Board Ownership. The SOC should detail any plans for assurance been included, for Programme / Project Assurance Review, as determined by the SRO. This could include tailored Gateway Review or other Assurance Reviews or Health checks, and should reference any follow-on actions identified from early stage reviews. | bar: FI FI
Management | Project Management | 5.3.2 | Resources Plan | Digital | [13 empty] | DI | At SOC the Trust should develop a project plan of the resources required for activities, and any need for specific capabilities and competencies required to develop the business case, from SOC through to approved FBC, including: • Details of the deliverables or products to be produced; • Details of the activities required to deliver them and the activities required to validate the quality of the deliverables; • A description of the resources and time needed for all activities, and any need for people with specific capabilities and competencies; • An resource plan detailing whether these activities can be delivered by existing Trust resources or through specialist advisers. The Trust should consider specialist advisers to support the business case, and reference these in the commercial and financial cases at OBC. The requirement for special advisers usually falls into four key categories in the project plan: financial, legal, technical and programme / project management. Where possible existing framework routes to market (e.g. NHS SBS framework) should be used. It is important that the case includes an indicative estimate of resources to inform the financial model identifies whether the resource is either new or funded from existing BAU budgets and whether a resource needs to be backfilled adding additional cost. This will be developed with much more detail at OBC. Identify specialised support and expertise that will be used in developing the business case and confirm they are suitably experienced. | bar: FI FI
Management | Project Management | 5.3.3 | Executive Support and Sign Off | Design Review Design Appraisal Finance Estates Estates Std'd Rev Assurance Strategy Economics |  |  | DR DA |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | The SOC should set out the project structure to provide assurance that the project has sufficient backing by, and commitment from senior executives and user groups to underpin a successful project.
Management | Project Management | 5.3.4 | Project Management Methodology | Finance Estates Assurance Strategy Economics |  |  |  |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | Confirm that the project management methodology been defined |  |  |  |  | The recommended project methodology is PRINCE 2 - Projects IN Controlled Environments, which is the de facto standard in use within the public sector in the UK.
Management | Project Management | 5.3.5 | Better Business Case Training | Assurance | [13 empty] | DI | Confirm that the Business Case Development Lead (ie Project Manager), Finance Lead and Estates Lead (for estates schemes)within the project team completed the mandatory Better Business Case training now required when working on NHS capital schemes and projects. | bar: AS AS AS
Management | Project Management | 5.3.6 | Adequate Management Arrangements for External Engagement | Design Review Design Appraisal Assurance |  |  | DA DR DA: DR DR; AS AS AS: AS |  |  |  | Describe how executive clinical leaders, frontline clinical and non-clinical staff, and other stakeholders have been involved in shaping and influencing proposals, including eliciting and acting on patient feedback. Has the organisation met its duties under s242 of the NHS Act 2006 to involve and where necessary carry out a full public consultation with patients, the public and other stakeholders? The outcome of this involvement has been considered and where appropriate has informed the business case Describe the interface with community partners and development/understanding of patient pathways.
Management | Change Management | [5 empty] | DR DA | CL | FI | ES |  | AS | ST | EC | PO | WO |  | DI | Change Management
Management | Change Management | 5.4.1 | Plan for Change and Contract Management | Digital | [13 empty] | DI | The SOC management case should define a change management plan that describes how resource capability will be developed according to the degree and pace of change required, such as through learning and development or through the appointment of specialist advisers. The change management plan should identify changes required to systems, processes and other governance arrangements, such as the contract management of specialist advisers by the SRO. The aligning of capability to support the project may involve considerable internal change, and Trust should ensure that staff and their representatives are included in a process of dialogue. Key to see that there is a Senior Responsible Owner (SRO) and an initial governance structure including other key provider trust roles (e.g., Chief Clinical Information Officer, Chief Information Officer, Chief Nursing Information Officer, Clinical Safety Officer) as well as involvement from key external stakeholders, in ICB and Region. Set out proposed delivery team structure under SRO, including how you will access any specialist digital and technology roles needed for delivery. Set out an initial high-level timeline, with broad commitment to adequate resourcing for any implementation programme. Set out what workshops have been held and which stakeholders engaged. Have participating Trusts agreed to work together, confirming whether there has there been any engagement with a trust that has undertaken as similar project e.g., a GDE or FF and review of blueprints. Set out how end-users (service users and professionals) have been engaged, including how many, how often, and of what types; and what their needs are. Include summaries of insights / outputs from engagement with users. Set out what plans are in place for this engagement with end users to continue throughout delivery. | bar: FI FI
Management | Other | [14 empty] | WO |  |  | Other | bar: DA DR DA to AS EC PO
Management | Other | 5.5.1 | Business Continuity | Assurance Workforce | [11 empty] | WO |  |  | Describe arrangements for business continuity during the build period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. |  |  |  |  | Describe arrangements for business continuity during the build period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. | bar: AS AS AS

## 1b. OBC FC + Checklist
2b. Outline Business Case (OBC) Checklist | [19 empty] | Provider Self Assessment |  | Regional Fundamental Criteria Assessment |  | Additional Checklist Information
2026-03-10
5 Case Model Heading | Sub-Heading | Business Case Checklist Reference Number | Category | Discipline / subject matter covered Formal or possible associated input / interest | Fundamental Criteria | Commissioning | Design Review. Design Appraisal | Clinical | Finance | Estates | Estates Standard Review | Assurance | Strategy | Economics | Policy | Workforce | NHP (New Hospital Programme) | Digital BC | Item / Section See Note B. on Introduction about Fundamental Criteria (FC) Where confirmation is asked for in the requirement, evidence should be provided with that confirmation. Light blue cell shading identifies the current FC item in the various sections | Provider Self Assessment RAG Rating Yes = Green Partly = Amber No = Red Completed by Provider | Where is this covered in the Business Case? Document, Appendix, section and / or page | Regional Fundamental Critiera RAG Rating Yes = Green Partly = Amber No = Red Completed by Regional FCR Reviewer | Please highlight in this column any areas where the Fundamental Criteria have not been fully met. | General Notes and Guidance Any links and guidance provided in this checklist may change over time. The Trust / ICB must therefore always establish that the guidance used is current and appropriate.
Strategic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Strategic | Approval and Support |  |  |  | FC: FC; AS: AS; DI: DI | Approval and Support
Strategic | Approval and Support | 1.1.1 | Board approval | Assurance Digital | FC: FC; AS: AS; DI: DI | Trust Board Approval - Confirm the date when the business case was approved by the Trust Board. Submission Requirements - The Business Case should be submitted with completed self-assessed Fundamental Criteria Checklist, to ensure that core requirements are met. This will enable swifter approvals. Letters of Support - ICB and Trust - The Business Case should be submitted with a Letter of Support from both the ICB as strategic commissioner and the Trust. Guidance on Letters of Suppport content and template letters are set out in Annex 3 of the NHSE Capital investment and property business case approval guidance. The Letters of Support should include the following (template lettes are included in Annex 3) - ICB Letter - Support for the business case, public consultation requirements have been met, alignment with ICB strategic commissioning/clinical strategy, affordability. - Trust Letter - Trust Board approval, capital affordability, revenue affordability, accounting treatment, alignment with local estates, digital and workforce strategies, deliverability. Cabinet Office (CO) Commercial Controls - If any of the contracts within the scheme are expected exceed the Cabinet Office Controls threshold the Trust will need to ensure that this contract value is reported onto the Regional Commercial Pipeline for CO oversight, and that the "Business Case Six Test Checklist" is completed and accompanies the business case submission. Trusts that will require CO approval should refer to this within their business case and ensure there is sufficient time to secure CO approval within the programme plan. |  |  |  |  | Provide minutes of the Board / Governing Body meeting approving the business case. The Board/Governing Body has approved all parts of the business case, e.g. strategic fit and the financial/operational impact. If there is more than one SRO / approving body, then the senior or lead SRO should take responsibility for submitting the case. The significance of the SRO role at this stage is to show ownership, and to formally signify the start of the review / approval process.
Strategic | Approval and Support | 1.1.2 | HMT guidance followed | Assurance Digital | [14 empty] | Confirm that the HMT Green Book has been followed in developing the business case. | bar: AS; DI
Strategic | Approval and Support | 1.1.3 | Assurance | Assurance Digital | [14 empty] | The case should demonstrate that all approval conditions from the SOC have been met. A log of these should be included as an appendix to the main case. For Electronic Patient Record Business Cases, the EPR Investment Board provides a completed Conditions Log with the Letter of Approval and will provide a confirmation e-mail when all conditions have been closed, so the Trust can proceed to launch 'Invitation to Tender' post OBC approval. The Trust must demonstrate that any other 'open' conditions set for closure either prior to or as part of the next business case stage have been met. | bar: FC
Strategic | Approval and Support | 1.1.4 | Cabinet Office Controls | Assurance Digital | FC: FC; ES: ES; AS: AS; DI: DI | The Cabinet Office Local Spend Control process is a separate approval process, which assesses a set of commercial principles and aims to provide support to Trusts at the earliest planning stage, prior to launch of their procurement. A submission to the Atamis Portal, or as directed, should be made as early as possible, to get a CO decision. If following submission, the CO applies a 'control' status and wishes to approve at OBC stage, then the completed Cabinet Office documentation and associated artefacts should be submitted with the business case for Fundamental Criteria Review, so any amendments can be made during detailed business case review. This applies to Digital and non-Digital, based on supplier commercial spend. Unless agreed otherwise with Cabinet Office - at OBC, the Trust should expect to seek CO sign-off before entering standstill, once a preferred bidder has been selected. It is also possible at this stage that CO may confirm that the Trust will either need to seek approval when the FBC is complete, or will be authorised to self-certify, subject to conditions such as there being no material changes.
Strategic | Approval and Support | 1.1.5 | Digital and Technology Assurance Questions | Assurance Digital | [14 empty] | Trusts should confirm that their Business Case is accompanied by a completed Digital and Technology Question Set. These have been published on the NHS Futures Sharepoint, with access provided by the Transformation Directorate team. Reference should be made to the Trust’s strategy for cloud data storage, and alignment with Government and NHS Public Cloud Hosting Policy. Trust should engaged with the Cloud Centre of Excellence and address any recommendations from that engagement as it is expected they meet the NHS Public Cloud Hosting policy. The assessment form for the EPR Technology & Digital Assessment may be found on the Frontline Digitisation Support Offer webpages on the NHS Futures Sharepoint or the related MS Teams Channel. | bar: FC
Strategic | Strategic and Policy Context |  |  |  | FC |  |  | CL | FI | ES | ESR | AS | ST |  | PO |  |  | DI | Strategic and Policy Context
Strategic | Strategic and Policy Context | 1.2.1 | Strategic Context | Clinical Finnce Estates Strategy Policy Digital | FC: FC; CL: CL; FI: FI; ES: ES; ST: ST; PO: PO; DI: DI | The context and case for change should be set out clearly, with local and national drivers for the change identified. The Trust should show how the proposals align to government and DHSC policy. This case for change should be evidence based and should articulate the proposed clinical model, underpinned by demand and capacity modelling. It should demonstrate: - the links to enabling strategies, e.g. workforce, patient experience and patient safety; - consideration of quality, workforce and financial / efficiency considerations; - stakeholder engagement, including with clinical leaders and trust staff to assess clinical oversight and involvement in the business case development; - alignment with both local and national service configuration, commissioning intentions and patient-centred design and build; - consistency with Trust digital strategy. A link or copy of the strategy should be appended or made available. - a clear commitment to IT systems interoperability should be made to the effect that 'any digital technology deployed, must be compliant with all relevant functional and interoperability standards. We need to be clear that the organisational overview sets out the relationship with key partners, in delivering care, patient flow etc, in addition to an overview of which trusts and hospitals are involved e.g. Acute, Community, Mental Health, Ambulance, how many beds, how many staff, how many in-patient episodes, and out-patient episodes. Also the latest CQC rating. The 'case for change' should also focus on the current gaps in local digital services as well as future gaps against business plans and strategy. Brief Reference to relevant national policy and strategy drivers e.g., national published documents such as the 'Ten-Year Health Plan: Fit for the Future' is advised. Clear case for change including presentation of the ICB roadmap and trust existing digital landscape, (with a graphical diagram or table) and indication of current digital maturity, and identifying gaps, problems, and opportunities, for improving productivity and reducing clinical risk against the national and ICB and local business strategy and published guidance i.e., the digital baseline. Inclusion of a good evidence base can help to support generalisations that are often made around patient experience, clinician’s needs that are not direct consequences of digitisation. The OBC may incorporate the outcomes of an initial Agile discovery and Alpha phase or pilot. For Agile Digital Projects an overall PBC should be considered. |  |  |  |  | For EPR Cases the strategy is to achieve a minimum Digital Maturity of HIMSS Level 5 / MDF with a view to be able to reach HIMSS 6 or 7 with future extension / optimisation of the solution The regional team should review and confirm the Digital Strategy / Management is robust and fits with Region and ICS digital strategy. Assurance is sought from Regional Digital leads that the case fits with regional convergence (Requirements and relevant standards may change over time)
Strategic | Strategic and Policy Context | 1.2.2 | Consultation | Commissioning Digital | FC: FC; CO: CO; DI: DI | Provider confirmation that the organisations consulted with global digital exemplars or very digitally mature trusts and accessed the digital blueprint library on the NHS Futures site.
Strategic | Strategic and Policy Context | 1.2.3 | Engagement and Integrated Working | Commissioning Design Review Design Appraisal Clinical Finance Estates Assurance Strategy Digital | CO: CO; DR DA: DR DA; CL: CL; ES: ES; AS: AS; ST: ST; DI: DI | The Trust should provide evidence of how the lead commissioning organisation has engaged with their patients and / or users, stakeholders, wider public / population and governors (as appropriate) in setting the clinical and service priorities that led to the scheme design and objectives. The case should provide evidence as to what extent the proposal will or has promoted integrated working between health, social care and public health. This should include alignment to the Integrated Care Addendum documentation, and should reflect on any post-project evaluations relating to the current service. In proposals that aim for ‘transformation change’, the nature of the change needs to be transparently explained, with objective evidence on which it is based and objective support for the assumptions made. A credible explanation of the change process is required, with detail as to how uncertainty will be handled. Annex A7 of the HMT Green Book needs to be understood and considered. |  |  |  |  | For Digital Technology projects, Discovery and Alpha phases will precede the SOC and inform the direction of the project.
Strategic | Strategic and Policy Context | 1.2.4 | Patient Choice | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that the scheme is developing well and on target to support greater patient choice on where and how to access care, and / or improved quality and safety of service provision |  |  |  |  | See Operational Guidance to the NHS: extending patient choice of provider.
Strategic | Strategic and Policy Context | 1.2.5 | Equality and Diversity | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that any equality and diversity impact has been assessed and actively addressed, detailing whether an appropriate assessment of the impact of the proposed service change on relevant diverse groups has been undertaken and if there has been engagement with any groups that may be affected. THe OBC should detail what action will be taken to mitigate any adverse impacts. |  |  |  |  | The proposal must pay due regard to the public-sector equality duty in line with the principles and requirements of the NHS Constitution and with current legislation and guidance.
Strategic | Strategic and Policy Context | 1.2.6 | Organisational Change | Clinical Finance Strategy | CL: CL; FI: FI; ST: ST | If there have been any strategic or organisational changes following approval of a previous business case, ensure these been adequately explained and their effects on the investment described. Confirm the demand assumptions in support of the size and scope of the investment still valid. |  |  |  |  | Does the recommended solution still provide all of the required services – both current and future?
Strategic | Strategic and Policy Context | 1.2.7 | Social Value | Clinical Finance Estates Strategy Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; ST: ST; DI: DI | Decribe the social value themes that have been under taken in the assessment, share your timed action plans and confirm that 10% minimum of scoring is weighted to social value.
Strategic | Rationale and Objectives |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC |  |  | NHP | DI | Rationale and Objectives
Strategic | Rationale and Objectives | 1.3.1 | SMART / Strategic Objectives | Digital | [13 empty] | DI | The OBC needs to identify the SMART (Specific, Measurable, Achievable, Relevant and Timebound) spending objectives associated with the project, and set out reasonable spending objectives linked to benefits. These objectives will need to be linked with Critical Success Factors and the identified benefits. These objectives will also need to link to wider government strategic priorities, as set out in the case for change, as well as directly link to Fit for the Future: 10 Year Health Plan for England priorities. Clear Investment or Spending Objectives must be linked to key strategy or business gaps such as replacement of legacy, levelling up capability, compliance, improving productivity, clearly derived from the strategic context and case for change. It should be clear that the investment is about clinical service transformation outcomes, improvement, and risk reduction, not just the technology. It may be more appropriate to develop a programme business case to look at a range of digital projects and services, phased over time, that could achieve better transformation and outcomes, particularly at ICB level. The OBC should confirm if there have there been any changes to the original scope or objectives since SOC, and set out if these changes have any material impact on the delivery of the objectives. | bar: FC
Strategic | Clinical Quality |  |  |  | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  |  | Clinical Quality
Strategic | Clinical Quality | 1.4.1 | IT Integration | Clinical Digital | [13 empty] | DI | Demonstrate how the specification for the Digital / IT system will integrate with other systems for the purposes of patient quality and safety. Describe and present the findings and outcome of the risk assessment and the impact on quality, including risks identified and the mitigation plan. Present the added clinical benefits of the new system. Provide evidence of clinician engagement and involvement in the project governance process. | bar: CL
Strategic | Clinical Quality | 1.4.2 | Delivery | Commissioning Clinical Finance Estates Strategy Digital | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  | DI | Describe how the scheme will support the delivery of the organisation’s clinical strategy and aligned to commissioning intentions as supported by the Provider Digital and Estate Strategies. Confirm if and when was the organisations clinical strategy was completed and signed off. Confirm if and when the Provider Digital and Estate Strategies was completed and signed off.
Strategic | Risks, Constraints and Dependencies | [5 empty] | DR DA | CL | FI | ES | ESR | AS | ST |  |  |  |  | DI | Risks, Constraints and Dependencies
Strategic | Risks, Constraints and Dependencies | 1.5.1 | Constraints and Dependencies | Digital | [13 empty] | DI | Key constraints and dependencies should be identified, particularly those separate projects, e.g. infrastructure improvements on which the successful delivery of this project will depend. The constraints should relate to standards and conformance with technology code of practice and other GDS and Transformation Directorate guidance can be brought out. e.g. 'digital first' principles. |  |  |  |  | This is particularly important if there are any interdependencies, especially benefits, with other investments / procurements.
Strategic | Strategic and Policy Context | 1.5.2 | Carter Efficiency | Finance Estates | FI: FI; ES: ES; ESR: ESR |  |  |  | DI | The Trust should confirm that the project complies with relevant Carter efficiency recommendations in Lord Carter of Coles 2015 report - Operational productivity and performance in English NHS acute hospitals: Unwarranted variations, and identify the recommendations being delivered by the project. |  |  |  |  | The case should refer to Lord Carter of Coles 2015 report: Operational productivity and performance in English NHS acute hospitals: Unwarranted variations, and identify the recommendations being delivered by the project.
Strategic | Strategic and Policy Context | 1.5.3 | Integrated Care and Digital Convergence | Finance Estates | [13 empty] | DI | The Trust should provide details of the strategy for delivering integrated care and convergence of digital solutions across the ICS, within the case or supporting documentation. | bar: FI to ES
Strategic | Risks, Constraints and Dependencies | 1.5.4 | Digital Technology Capability | Digital | [13 empty] | DI | Provide a summary of the organisation's current Digital Technology capability. Confirm that this identifies the starting point for development of the Digital technology schemefor example. This should include the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise |  |  |  |  | An annex may include, for example, the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise.
Strategic | Risks, Constraints and Dependencies | 1.5.5 | Gap in Digital Technology Provision | Digital | [13 empty] | DI | Confirm that the "gap" in Digital Technology provision, between the current position and the identified objectives supporting health service delivery, is known.
Strategic | Risks, Constraints and Dependencies | 1.5.6 | Government Standards | Digital | [13 empty] | DI | Confirm that the programme demonstrate awareness and compliance with the relevant government standards and policies for technology. Confirm how it ensures these will be met. Confirm the applicability of the Technology Code of Practice and Digital by Default Service standard. |  |  |  |  | The Technology Code of Practice and Digital by Default Service standard always apply.
Strategic | Risks, Constraints and Dependencies | 1.5.7 | Options Analysis | Digital | [13 empty] | DI | Ensure and confirm that the options analysis concerning the delivery approach for digital is supported by adequate analysis of user, as opposed to stakeholder, needs. |  |  |  |  | Services that are driven by policy without appropriate meeting of user needs are far less likely to deliver the claimed benefits due to low adoption rates.
Strategic | Risks, Constraints and Dependencies | 1.5.8 | MVP | Digital | [13 empty] | DI | Confirm that the digital programme has established the criteria to be met by the Minimum Viable Product (MVP) |  |  |  |  | The MVP is the minimum IT support necessary to deliver a service. If the MVP is undefined then scope-creep and consequent negative impact on VFM in particular becomes more likely. A service that is unable to articulate MVP criteria is not likely to have completed sufficient analysis of user needs.
Strategic | Risks, Constraints and Dependencies | 1.5.9 | Service Assessment Scope | Digital | [13 empty] | DI | Confirm that the digital programme or any component is within the scope of service assessments. If so, the case should confirm at what stage and what were the outcomes of that assessment. |  |  |  |  | Service assessments are mandatory at alpha, beta and live stages of programmes. Failure to pass can prevent the programme continuing to the next stage or even prevent live deployment.
Strategic | Risks, Constraints and Dependencies | 1.5.10 | Technical Decisions | Digital | [13 empty] | DI | Confirm that the options analyses consider technical decisions and justify the preferred digital option. Buy versus build, proprietary versus open source , co-location or in-house provision versus cloud hosting et |  |  |  |  | Buy versus build, proprietary versus open source , co-location or in-house provision versus cloud hosting etc.
Economic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Economic | Workshop | 2.1.1 | Workshop 3 Green Book | Assurance Economics | [14 empty] | Workshop 3 completed: Assessing the Shortlisted Options |  |  |  |  | Green Book and associated guidance documents. Mandated workshop requirement | bar: AS; EC
Economic | Options Appraisal |  |  |  | FC | CO | DA | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | Options Appraisal
Economic | Options Appraisal | 2.2.1 | Options Framework | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | FC | CO |  | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | The OBC should identify a minimum of four shortlisted options for further appraisal. Only in exceptional circumstances, and with prior agreement with DHSC Economists, can business cases be submitted with a short list of less than four. The short list should include: - Business As Usual (BAU) – acts as a "Do Nothing" benchmark for Value for Money - ‘Do Minimum’ – a realistic way forward that also acts as a further benchmark for Value for Money. This option should set out the minimum capital investment required to deliver the core spending objective(s) underpinning the case for change. - A recommended Preferred Way Forward (PWF), that combines the PWF options from all filters, unless this is identical to the Do Minimum. - One or more other realistic options, that use 'carried forward' options from at least one filter to become a more- or less-ambitious PWF. The presentation of the shortlist options in the economic case should be easily relatable to the presentation of the shortlist options in the Capital Investment Appraisal (CIA) model. The OBC must demonstrate a full options appraisal which gives a clear indication of the processes the project has gone through to arrive at a preferred option. This should be in line with the HMT Green Book and supplementary guidance. |  |  |  |  | HMT Green Book Options Framework is to be followed - recommended If, unusually, there is more than one preferred option, this should be explained, and the criterion applied to all of them.
Economic | Options Appraisal | 2.2.2 | Preferred Option | Commissioning Design Appraisal Clinical Finance Estates Strategy Economics Policy Digital |  | CO | DA | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | Ensure that the preferred option has been described in sufficient detail to enable the assessment of costs, benefits and risks. Where appropriate, wider impacts should be assessed e.g. sustainability, competition, regulatory impact, place-based. The costs, benefits and risks must be granular enough to be able to demonstrate where they are coming from, 'capital costs' or 'cash releasing benefits' will not be sufficient to support the case.
Economic | Options Appraisal | 2.2.3 | DPIA | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST; EC: EC; PO: PO; DI DI: DI | As part of the workshops and evalaution of options for new projects, programmes, or other activity which involves a new use of Personal Data, the SRO should assess the risks of data management. A Data Protection Impact Assessment (DPIA) is a process used to identify and minimise data protection risks when processing personal data. A DPIA should be provided with the OBC.
Economic | Costs |  |  |  | FI: FI; ES: ES; EC: EC; DI DI: DI | Costs
Economic | Costs | 2.3.1 | All Costs Assessed | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that all relevant capital (build and lifecycle) costs, revenue costs (e.g. running costs, dual running costs, transitional costs) and opportunity costs been identified and properly assessed. |  |  |  |  | The costs should cover the whole life of the investment for all IT projects and for most build projects, where possible. They should take account of (if appropriate): lifecycle costs (building related and equipment/IT replacements), residual values, monitoring and evaluation costs, health organisational development costs, opportunity costs, second round effects, avoided costs and costs borne by others. Care should be taken not to double-count costs. See Green Book . Cost sources should be identified for all costs, including where these are estimates. Note that costs must be assessed on a ‘bottom-up’ basis: that is, the case must show the total costs of each option, not just costs incremental above existing levels of expenditure. Descriptions of how all costs have been quantified should be available along with supporting spreadsheets.
Economic | Costs | 2.3.2 | Key Cost Assumptions | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that all key assumptions underlying the costs been clearly explained and justified |  |  |  |  | For example, the assumptions about the life of an asset. Reference the source documents underpinning these assumptions.
Economic | Costs | 2.3.3 | Costs in Real Terms | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that costs are shown in real terms, at constant (uninflated) prices, with the base year clearly specified and the current year shown as Year 0. Confirm the correct discount rate been used. For some goods or services there may be a relative price effect i.e. the movement of a specific price index (e.g. construction) may differ significantly from the general inflation (such as the GDP deflator). Where there is historical evidence and an expectation this will continue in the future, different rates of inflation can be used to reflect the relative difference. Where prices or values are expected to grow in real terms, these assumptions must be based on objective evidence, for example, long term trends in relevant indices. These assumptions should be transparently set out in the business case and assumptions agreed with the approving authority. |  |  |  |  | See Green Book
Economic | Costs | 2.3.4 | Sunk Costs | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that sunk costs (costs that has already been incurred and that cannot be recovered), transfer payments, VAT, capital charges, depreciation and other non-resource costs been excluded from the economic appraisal of costs in the CIA model. |  |  |  |  | Sunk costs are those already incurred, e.g. project management. Transfer payments include redundancy payments, VAT and local authority rates. Only income from non-government (third party) organisations should be included.
Economic | Costs | 2.3.5 | Appraisal Period | Finance Estates Economics Estates | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that the appraisal period appropriate to the life of the asset generated by each option |  |  |  |  | A view from the technical advisor should give the economic life of the asset generated by each option and must be stated. Where the appraisal period is different for alternative options, discounted costs must be expressed as equivalent annual costs rather than net present costs (NPC).
Economic | Costs | 2.3.6 | Environmental Costs | Finance Estates Economics Estates | FI: FI; ES: ES; EC: EC; DI DI: DI | Providers should refer to Annex A1 within the Green Book in order to ensure that they are accounting for the environmental costs of interventions. Total energy use and total GHG emissions should be quantified and costed utilising the BEIS Green Book supplementary guidance: valuation of energy use and greenhouse gas emissions for appraisal guidance document that has been published. |  |  |  |  | A view from the technical advisor should give the economic life of the asset generated by each option and must be stated. Where the appraisal period is different for alternative options, discounted costs must be expressed as equivalent annual costs rather than net present costs (NPC).
Economic | Benefits |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; WO: WO; NHP: NHP; DI DI: DI | Benefits
Economic | Benefits | 2.4.1 | Credible Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that appropriate and credible benefits (cash releasing, non-cash releasing, societal and quality) have been identified. Any disbenefits of investment should also be identified. |  |  |  |  | The benefits should be identified through consultation with stakeholders, e.g. through a benefits workshop. These may include cash-releasing, non-cash releasing or non-quantifiable (qualitative) benefits. See Green Book Benefits should be consistent throughout the case, i.e., strategic, economic, financial and management.
Economic | Benefits | 2.4.2 | Key Assumptions | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that supporting the benefit profiling are sources of evidence, including detailed calculations and assumptions and applied confidence and attribution, to ensure no double counting of benefits. |  |  |  |  | For example the assumptions about why a benefit might vary from one option to another, or be treated as non-cash releasing rather than cash-releasing. Please reference the source documents underpinning these assumptions.
Economic | Benefits | 2.4.3 | Quantified Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that benefits have been quantified in line with HMT Green Book guidance. QALY benefits should be assessed on the basis that the current monetary "willing to pay" value for a QALY is £70,000. The case should also set out a costed profile of benefits. |  |  |  |  | Benefits should be monetised or measured to the extent that it proportionate or prudent to do so.
Economic | Benefits | 2.4.4 | Non-Quantifiable Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Where it is not possible to quantify a benefit, the OBC should explain why this is so and demonstrate that benefits have been separately qualitatively evaluated where possible. |  |  |  |  | The presumption should be not to define benefits which cannot be measured or for which there is no evidence base.
Economic | Benefits | 2.4.5 | Benefits Register | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm there a benefits register to support the benefits modelled in the economic analysis
Economic | Benefits | 2.4.6 | Quantified Benefits Discounted | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Clarify if quantified benefits been discounted over the period of appraisal? Confirm that benefits have not been double counted. |  |  |  |  | Discount rate should be 3.5% if benefits are valued in real terms or 1.5% if Quality-Adjusted Life Years have been used in valuing benefits. For projects with very long-term impacts, over thirty years, a declining schedule of discount rates should be used (see Green Book Annex 6).
Economic | Benefits | 2.4.7 | Constant Value Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm the values of benefits been stated in constant (uninflated) prices and consistent with the cost assessment |  |  |  |  | See Green Book
Economic | Risk | [6 empty] | CL | FI | ES | ESR | AS |  | EC |  | WO | NHP | DI | Risk
Economic | Risk | 2.5.1 | Risks and Lifecycle | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Have the risks associated with all shortlisted options been appropriately identified across the whole lifecycle of the project? A brief description of the risk mitigations should be provided for the preferred option only. |  |  |  |  | These risks should be set out in a risk register (see also Management case) Whole lifecycle refers to the life of the project. This is normally the construction period plus 60 years operational life for new build investments. Refurbishment schemes are shorter, typically 25-30 years, depending on the anticipated life of the anticipated buildings. IT projects tend to be evaluated over a short time period, 7-10 years or even less, with allowances to renegotiate or extend the current contract.
Economic | Risk | 2.5.2 | Quantified Costed Risks | Clinical Finance Estates Economics Digital | CL: CL; FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the risks have been quantified and costed at OBC stage. These should be presented in a matrix showing: 1. which party is responsible for managing risks 2. the probability of the risk 3. the impact of the risk 4. the expected cost of each risk (probability x impact) |  |  |  |  | A narrative should be provided explaining the methodology for the quantification of risks and how the probability has been derived
Economic | Risk | 2.5.3 | Risk Register | Clinical Finance Estates Economics Digital | CL: CL; FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the assumptions underlying the identification, timing and potential impact of the risks been explained? Is there a costed risk register to support this? |  |  |  |  | These should be covered in the risk register.
Economic | NPSV, Optimism Bias and Sensitivity Analysis |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | NPSV, Optimism Bias and Sensitivity Analysis
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.1 | CIA Model | Finance Economics Digital | FC: FC; FI: FI; EC: EC; DI DI: DI | The OBC will need to demonstrate use of the Digital Capital Investment Appraisal (CIA) Model for the economic modelling. We would expect that all schemes will use the CIA, and they will not be able to proceed without completing. The VFM analysis must quantify costs, risks, cash releasing benefits, non-cash releasing benefits and economic societal benefits. It must also evaluate un-monetisable benefits. There should be a clear and transparent reconciliation of numbers across the CIA Model and Economic Case, the fully completed Cost Forms (OB / FB forms) that identify cost of options, and the Capital Figures included in the Finance Case. There should also be clear alignment across revenue assumptions in the CIA and SOCI (including cash releasing benefits). |  |  |  |  | The CIA model is fully completed and all shortlisted options are fully presented within the model to reflect costs, risks, OB and benefits of each option. Trusts should include the fully costs and benefits of the options explicitly, i.e. not incrementally, to enable a comparison between the costs and benefits from SOC to OBC. The outputs from the CIA model are accurately reflected in the business case, i.e. overall economic appraisal including incremental analysis and presentation of the NPSV and BCR, information on costs, risks, and benefits. Explanations and workings to support the calculations of the costs, risks, OB and benefits are provided and clearly set out in the CIA and supporting documents. The appraisal period of the shortlisted options modelled in the CIA, especially the preferred option is consistent with the financial case, and all have been quantified over the lifespan of the proposal, including the BAU option. The costs presented in the economic case correctly exclude sunk costs, VAT, and capital charges (Depreciation and PDC dividend costs) and any other transfer payments. Only income from non-government (3rd party) organisations should be included. These should be identified when reconciling the costs presented in the economic and financial case. There should be a clear and transparent reconciliation of numbers across the CIA Model and Economic Case, the fully completed Cost Forms (OB / FB forms) and cost advisors report that identify cost of options, including any GMP, and the Capital Figures included in the Finance Case.
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.2 | Presentation of an Incremental VFM Analysis | Digital | [14 empty] | The OBC must present a value for money case for all options, which should demonstrate a quantified cost / benefit / risk analysis to determine the option that shows the best value for money. The Net Present Social Value and Benefit Cost Ratio must be presented for each of the short-listed options. Business cases are expected to follow the HMT Green Book and supplementary guidance. The value for money analysis is expected to be presented as incremental analysis, as requested by the Green Book, and all figures must align with the CIA model. | bar: FC; DI DI
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.3 | Optimism Bias and CIA | Finance Economics | [14 empty] | Confirm costs (e.g. Capital, lifecycle, operating costs) and benefits been adjusted for optimism bias in accordance with the guidance or using the methodology in the CIA. | bar: FI; EC
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.4 | Demand Capacity Modelling | Economics | [14 empty] | Investment proposals must provide evidence of triangulation of demand and capacity modelling, workforce strategy, service development and efficiency programme across the lifetime of the scheme. Ensure that the values used in the CIA for costs (capital and revenue), risks and benefits reflect this. | bar: EC
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.5 | Sensitivity Analysis | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Economic Sensitivity Analysis is used to ensure that the preferred option is suitably robust in the event of changes to costs / benefits / risks. It is an important evaluation tool to demonstrate the robustness of the options appraisal and selection of the preferred option, and as such it should be undertaken prior to OBC submission to ensure that the preferred option for tendering is the best option.
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.6 | Benchmarking analysis | Economics Finance Estates Digital | FI: FI; ES: ES; ESR: ESR; EC: EC | The project cost advisor must provide a project cost benchmark comparator analysis to demonstrate the VFM of the proposed project in relation to other comparable projects.
Economic | Summary |  |  |  | DR DA: DR DA; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | Summary
Economic | Summary | 2.7.1 | Consistent Preferred Option | Economics | [14 empty] | Confirm the preferred option consistent with the results of the cost, benefits and risk appraisals. | bar: EC
Economic | Summary | 2.7.2 | Unquantified Costs | Economics | [14 empty] | The OBC should set out if there any decisive unquantified costs, non-beneficial areas and / or benefits, and explain any assumptions. | bar: EC
Economic | Summary | 2.7.3 | Place Based Analysis | Economics | [14 empty] | Confirm if distributional and place-based analysis is needed to highlight who benefits. If this has been completed it should be confirmed that this is in accordance with the Green Book. | bar: EC
Economic | Summary | 2.7.4 | Consistency Across Case and Annexes | Design Appraisal Finance Estates Economics | DR DA: DA; FI: FI; ES: ES; EC: EC | Confirm all supporting evidence (e.g., in Annexes) consistent with the results in the main text of the business case. Where annexes are relevant, they must be referenced within the business case.
Economic | Digital |  |  |  | EC: EC; NHP: NHP; DI DI: DI | Digital
Economic | Digital | 2.8.1 | Tax / Subsidy Treatments | Economics Digital | [14 empty] | The OBC should confirm whether any tax / subsidy treatments are non-distorting between options. |  |  |  |  | Also check if there’s any possibility of state aid if there is distortion between options. See Green Book | bar: EC; DI DI
Economic | Digital | 2.8.2 | Discovery / Preliminary Works | Economics Digital | [14 empty] | Set out whether any discovery or preliminary works in relation to digital projects been carried out, and, if so, whether the relevant spend control approvals and conditions been attached to the case. |  |  |  |  | Discovery up to £750k can be approved without (prior to) a supporting business case but cabinet office can and do apply conditions to this spend. | bar: EC; DI DI
Commercial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Commercial | Workshop | 3.1.1 | Workshop 4 Green Book | Estates Assurance | [14 empty] | Workshop 4: Developing the Commercial Strategy and Deal |  |  |  |  | Green Book and associated guidance documents. Mandated workshop requirement | bar: ES; AS
Commercial | Commercial Feasibility |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Commercial Feasibility
Commercial | Commercial Feasibility | 3.2.1 | Commercial Feasibility Confirmation | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the organisation and relevant project advisers (e.g., lawyers) consider that the proposal is commercially feasible and deliverable. |  |  |  |  | This should be adequately provided or explained.
Commercial | Commercial Feasibility | 3.2.2 | Sufficient Time | Finance Estates Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that the proposal allows sufficient time and resources for the completion of all identified procurement tasks, e.g. completion of necessary procurement documents and supplier negotiations.
Commercial | Commercial Feasibility | 3.2.3 | Tender / GMP Adequate Time | Finance Estates Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Where a tender or target price date has been planned or is being been established, confirm that there is adequate time allowed for the approval process to be completed to allow the contract to be signed.
Commercial | Scope |  |  |  | FC: FC; CL: CL; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Scope
Commercial | Scope | 3.3.1 | Procurement Aims | Clinical Finance Estates Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; DI DI: DI | The business case must clearly describe the subject matter of the procurement. For example, has the business case clearly set out the buildings, land, equipment, technology, goods and/or related service streams to be included in the scheme? |  |  |  |  | The business case should be clear as to the output to be procured, including specification of required outputs and requirements to be met (essential outputs, phases, performance measures, quality attributes. The business areas, stakeholders and customers affected by the procurement should also be set out, along with any future possibilities (potential developments and further phases). The process should be properly classified for the purposes of the procurement rules. It should be clear that the organisation can afford to commission or run the clinical services that are already in the building.
Commercial | Scope | 3.3.2 | Procurement Strategy | Finance Assurance Digital | FC: FC; FI: FI; AS: AS; DI DI: DI | A competitive procurement must be undertaken, through an NHSE endorsed route to market (ie. for Clinical IT solutions this is currently the LPP CDHS Framework). This is essentially mandatory for centrally funded EPR initiatives, requiring Transformation Directorate endorsement to ensure adoption of standard terms and conditions to support maximum standards compliance, unless there is a very good justification for doing otherwise. Where a Trust wishes to deviate from this approach they must submit a "Exception Request" for programme consideration / approval. The Frontline Productivity programme will not provide central funding where a Trusts wishes to Direct Award and all procurement activities must comply with applicable procurement regulation (PCR 2015 / PA2023), local SFIs and supported by appropriate legal advice. It will require a full cost risk benefits economic analysis at OBC and FBC. Where appropriate set out 'set out how any new products or services for service users or professionals developed as part of this project will meet level AA of the Web Content Accessibility Guidelines (WCAG 2.1) and flag any gaps https://www.gov.uk/service-manual/helping-people-to-use-your-service/understanding-wcag. If for any reason, an NHSE endorsed route to maket is not followed, then applicable standards should be clearly specified in related procurement documentation. OBC requires a compliance statement included that sets out 'any digital technology deployed, must be compliance with all relevant functional and interoperability standards' with more detail of which ones are relevant, which may be referred to in an Appendix The complete, final version of the Output-based specification or Requirements Specification should be submitted with the OBC for approval. The Trust will need to comply with the requirements set out in the latest Commercial Checklist. |  |  |  |  | Clear, realistic procurement key milestones and delivery dates should be set out. Supplementary questions could focus on managerial capacity to deliver to timeline. Caution should be exercised in relation to overly optimistic timelines which have no contingency for slippage. The experience of capital procurement processes generally is that it invariably takes longer than anticipated.
Commercial | Scope | 3.3.3 | Specialist Equipment Procurement | Clinical Finance Estates Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; DI DI: DI | The OBC should set out the strategy for any specialised procurement, e.g. equipment, with a project plan identifying the timeframes and costs. |  |  |  |  | The equipment strategy should set out: • any existing equipment to be transferred; • new equipment being procured in advance of the scheme: and • equipment being procured as part of, or in parallel with the scheme. • specialist equipment The business case must confirm: • which organisation procures the equipment; • which organisation funds the equipment; • which organisation will own, operate and maintain/replace the equipment
Commercial | Scope | 3.3.4 | Compliance with Relevant Procurement Laws | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm that the procurement strategy complies with the relevant procurement law. Assurance of compliance with procurement legislation must be provided by legal advisors, confirm that it has been updated at FBC stage as appropriate. |  |  |  |  | For example, all procurement stages must be of at least the minimum duration required by law, which depend on the process followed. The content of any sign off from legal advisors will be assessed. It is unlikely to be an unconditional endorsement. The reviewer will assess the degree of scrutiny that has been applied to the process; if this is considered inadequate, then the legal assessor will comment accordingly.
Commercial | Scope | 3.3.5 | VFM Procurement | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm the procurement strategy been chosen because it can provide an outcome that delivers value for money. If not confirmation as to why is required. |  |  |  |  | Consideration should be given as to how to incentivise those involved with the scheme to provide value for money. This should be reflected in the chosen payment mechanism.
Commercial | Scope | 3.3.6 | Market Interest | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm an assessment of market interest has been included together with any market soundings to date. Any factors that may have a detrimental impact on market interest are discussed and mitigation strategies must be included.
Commercial | Procurement Process |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Procurement Process
Commercial | Procurement Process | 3.4.1 | Procurement Documentation | Digital | [14 empty] | A competitive procurement should be undertaken utilising mandated frameworks, with procurement related documentation to be submitted with the case. The ITT should be included, and will need to incorporate the following: - Required references to compliance with the Technology Code of Practice - Pass / Fail Evaluation Criteria against which the supplier tender submission will be assessed. - The Affordability Cap is clearly stated. The OBC should be accompanied by a completed Output based specification of requirements that reflects the business case scope and related costs and benefits. | bar: FC; DI DI
Commercial | Procurement Process | 3.4.2 | Price & Risk Transfer | Digital | [14 empty] | The OBC includes suitable evaluation and consideration of the price and risk transfer. This should take consideration of the size and scale of the project and identify: 1. which party is responsible for managing risks; this should reflect the party who is most able to manage the risk. 2. the probability of the risk 3. the impact of the risk 4. the expected cost of each risk (probability x impact) The pricing methodology allows for an appropriate risk transfer but is still acceptable to the market, this should have been informed by a level of market engagement. Consideration should have been given to fixed or maximum price, arrangements for gain / pain share (delay, design, latent defects etc), formation of JVs. The OBC should onfirm there is a CRMS in place aligns with the standards set out in DCB0129 and DCB0160, detailing the procedures necessary to ensure that all healthcare IT systems used in the delivery of care are safely developed, deployed, and operated. | bar: FC; DI DI
Commercial | Key Contractual Issues |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Key Contractual Issues
Commercial | Key Contractual Issues | 3.5.1 | Commercial Legal Issues Summary | Finance Estates Assurance Digital | FI: FI; ES: ES; AS: AS; DI DI: DI | Confirm there is a summary commentary on all key scheme specific commercial and legal issues and risks retained by the trust. This should include commentary on any proposed amendments to the contract. See also 3.4.1. Legal advice to be taken by the provider and supplied with the OBC in the event that there are any novel and contentious elements or significant risks to the proposed contract. For framework procurements, a legal report will not be required unless there are variations to the standard procurement or contract documentation that are being made. In these instances, it is expected that providers will commission legal advice to test the viability and risks of any variations or additional Z clauses. If the procurement is proposing a standard contract, the OBC should outline any alterations or derogations that have been signed off. The case should indicate what contract will be used, and suitable commentary provided. If the procurement is not using a standard contract, does the case indicate what contract will be used? Suitable commentary should be provided. |  |  |  |  | As appropriate for OBC / FBC stages of business case development.
Commercial | Key Contractual Issues | 3.5.2 | Milestones | Design Appraisal Finance Estates Digital | DR DA: DA; FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that there are clear and realistic contractual key milestones and provide a full project programme showing start and completion dates together with all relevant elements of a full project plan. |  |  |  |  | The following examples of different payment mechanisms may be helpful: • Fixed price • Reimbursement of costs plus agreed margin • Payment on the delivery of agreed outputs. Any available deductions should be clearly described e.g.: • Availability and performance deductions • Liquidated damages for delay Any incentive payments or gainshare arrangements should be clearly described.
Commercial | Key Contractual Issues | 3.5.3 | LADs and Delay Risk | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the risk of delay in completion, including inclusion of liquidated and ascertained damages (LADs) and / or the management of contractor performance, has been addressed.
Commercial | Key Contractual Issues | 3.5.4 | Project Bank Account | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | The case should confirm if use of a project bank account been considered, and whether it has been set up.
Commercial | Risk |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Risk
Commercial | Risk | 3.6.1 | Identified Risk Allocation | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the identified risk (see economic case) been appropriately allocated to the party best able to manage the risk between public and Contractor sectors. |  |  |  |  | The business case should include a risk allocation table. The governing principle is that risk should be allocated to the party best able to manage it, subject to relative cost. There should be a sound risk allocation matrix for the preferred option showing how risks are to be apportioned between the Trust and the contractor. Shared risks should be excluded. Ideally, a percentage allocation should be recorded between the categories of public and contractor. If this is not feasible, then a “tick” system can be used at OBC stage. Has account been taken of potential private sector risks, e.g. bankruptcy of service provider?
Commercial | Risk | 3.6.2 | Risk Allocation Matrix | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm a timetable is set out to revisit and evaluate the risk allocation matrix.
Commercial | Risk | 3.6.3 | Collateral Warranties | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm use of collateral warranties been considered. Provide the outcome and arrangements put in place.
Commercial | Risk | 3.6.4 | Fraud Risk | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | SROs and Board to confirm that counter fraud measures focus on clear governance, procedures and responsibilities to counter fraud, including staff training, preventing, detecting, reporting and investigations. There are clear rules and duties of due diligence which must be adhered to when awarding purchasing contracts or other decisions (such as the awarding of grants). For major new areas of spend, an initial assessment of how fraud may occur and the potential impacts this will have should be conducted referencing the Government Fraud Risk Assessment Standard. This must be informed by consultation with relevant counter fraud experts and stakeholders at the earliest point in the business case process. For all proposals, proportionate counter fraud measures should be built into the design as a constraint and therefore as a requirement of all viable options. The Professional standards and guidance for fraud risk assessment in government should be referred to for additional information. SROs are satisfied that sufficient counter fraud measures are in place where funds are paid to a third party. SRO to confirm this in writing to satisfy this requirement. SROs must demonstrate they are aware of fraud risks and how they plan to manage them. Examples could include completing Fraud Risk Assessments and Action Plans. |  |  |  |  | The type of risk and where it resides will depend on a number of factors including the type of contract employed. The process and achievement of risk transfer must be described and confirmed as having been achieved where applicable.
Commercial | Personnel |  |  |  | DR DA: DR DA; ES: ES; ESR: ESR; AS: AS; EC WO: WO; EC NHP: NHP; DI DI: DI | Personnel
Commercial | Personnel | 3.7.1 | Personnel Implications | Workforce | [14 empty] | The OBC should state explicitly whether the scheme has any implications for personnel, including whether there would be expected to be any transfer of staff. The case should confirm if TUPE is anticipated to apply. |  |  |  |  | TUPE – Transfer of Undertaking, Protection of Employment Regulations 2006 (and as updated since). This protects the employment conditions of public sector staff transferring to the private sector. Also see NHS Standard Contract, Fair Deal for Staff Pensions, Draft Template Schedule 7 and Accompanying Guidance | bar: EC WO
Commercial | Personnel | 3.7.2 | Retention of Employment | Workforce | [14 empty] | Confirm advice was sought where retention of employment (RoE) is proposed and is there confirmation that plans accord with current guidance and requirements on RoE as related to pensions, and that there are plans for consultation in accordance with the law / guidance. |  |  |  |  | TUPE protection does not include pensions, and DHSC developed RoE to cover these. Its use is now specifically restricted to soft facilities management in PFI schemes. If it applies, a copy of the legal advice received must be provided, as well as whether the health organisation’s HR director accepts or disagrees with it and why. | bar: EC WO
Commercial | Personnel | 3.7.3 | Sustainable Development | Design Review Design Appraisal Estates | DR DA: DR DA; ES: ES | Confirm external support, assurance, guidance for Sustainable Development has been sought and used.
Commercial | Net Zero Carbon |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Net Zero Carbon
Commercial | Net Zero Carbon | 3.8.1 | Net Zero Carbon | Digital | [14 empty] | The case should set out any requirements or opportunities for digital investment to contribute to net zero carbon. This should entail an assessment in principle against either the Technology Code of Practice sustainability principle assurance checklists or Greener Digital Tooling available on ther Future NHS Workspace: net CO2 impact calculator, low CO2 and climate resilient digital service design. Greener Digital Tooling - https://future.nhs.uk/connect.ti/DigitalNetZero/view?objectId=40994704 |  |  |  |  | For further detail explore the Technology Code of Practice sustainability principle and it's assurance requirements around compliance to the HMG GGC ICT and Digital Services Strategy objectives. Tooling available on request: net carbon impact calculator, low CO2 digital service design checklist, digital service climate change risk assessment and mitigation planning tool | bar: FC; DI DI
Commercial | Sustainability |  |  |  | DR DA: DR DA; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Sustainability
Commercial | Sustainability | 3.9.1 | Sustainability Considerations | Digital | [14 empty] | The case should demonstrate how the proposal delivers across key themes for sustainability such as Climate Change Adaptation for overheating and flooding. The proposal should also demonstrate how it aligns to government policies such as digital future proofing. These will need to be included as part of the procurement strategy above. If this is not demonstrated at OBC, approval conditions will be put in place alongside the checking off of procurement documentation (see above) to ensure that these considerations are built into the tender. The case should set out any requirements or opportunities towards sustainability relating to digital investment. | bar: DI DI
Financial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Financial | Overall Affordability |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Overall Affordability
Financial | Overall Affordability | 4.1.1 | Overall Affordability | Finance Digital | [14 empty] | Confirm the financial case includes an overview of: (i) The organisation's financial position (ii) The resources available for the project / programme (iii) Any capital and revenue constraints (iv) Statements in relation to content of Letters of Support from ICBs as strategic commissioners and from the Trust. | bar: FI; DI DI
Financial | Financial Model |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Financial Model
Financial | Financial Model | 4.2.1 | Financial Model | Finance Digital | [14 empty] | (i) Confirm a financial model been developed, with plans to keep it under continuous review and updated. (ii) Confirm the financial model includes the minimum requirements, including • Agreement and recording of underlying assumptions • Funding • Input schedules for costs, cash releasing benefits, risks and contingencies • A reconciliation of demand, capacity, workforce and financial assumptions • Projected financial statements - SOCI, SoFP, Statement of Cashflows (ii) Does the Long Term Financial Model cover an appropriate term (BAU, construction, steady state) | bar: FI; DI DI
Financial | Capital Affordability |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; NHP: NHP; DI DI: DI | Capital Affordability
Financial | Capital Affordability | 4.3.1 | Capital Affordability | Digital | FC: FC; FI: FI; DI DI: DI | The case must demonstrate that the costed proposals are affordable within either operational capital allocations or within national programme funding allocations. Risk, Contingency and Optimism Bias should be appropriately calculated for OBC stage and inflation assumptions clearly stated. The OBC should also include fully costed and completed Cost Forms for all short listed options The capital cost for the preferred option will need to reconcile fully across the fully completed Cost Forms, the Financial Case and the CIA. The case will need to set out the Sources and Applications of capital funding for delivery of this scheme, as well as the proposed profile of expenditure of these capital sources. If operational capital envelopes are used to support the scheme, the Sources and Applications presentation should align with the Letter of Support from the Trust (see above). Indicative costs should take account of associated infrastructure, and implementation with business change. High level estimated capital and revenue costs should be shown over an assumed contract period |  |  |  |  | To support the FCR the case should clearly demonstrate capital affordability. The capital spend profile and values should align with funding agreed and clearly demonstrate CDEL affordability within any funding award/allocation, e.g., national programme PDC funding allocations and/ or within system operational capital allocations as confirmed in the system letter of support. Any national programme funding assumptions in the financial case must be profiled, and the scheme is completed in line with the key dates set by the relevant programme as a condition of funding award. The financial case should include a capital source and application of funds table which demonstrates the profiled CDEL impact of the investment, which correctly takes into account any CDEL credits, i.e. disposals, grants or donations. The case should also correctly take account of any early funding drawn to date and spend incurred The assumptions and the affordability statements in the case should be supported by the system per the letter of support. The financial case should ensure any matched funding requirements (Capital and or revenue) are met and should clearly set out the assumptions made.
Financial | External Funding Sources |  |  |  | FI: FI; NHP: NHP; DI DI: DI | External Funding Sources
Financial | External Funding Sources | 4.4.1 | External Funding | Finance Digital | [14 empty] | Confirm that any elements to be funded from external sources been identified, with the profile of funding / spend by year. | bar: FI; DI DI
Financial | External Funding Sources | 4.4.2 | Borrowing | Finance Digital | [14 empty] | Where borrowing is assumed, the case should set out whether this is anticipated to be DHSC or commercial borrowing, as well as confirming whether the NHS organisation has the ability to borrow. Trusts should refer to the DHSC S42a guidance on financing outside of the DHSC group: https://www.gov.uk/government/publications/guidance-on-financing-available-to-nhs-trusts-and-foundation-trusts/secretary-of-states-guidance-under-section-42a-of-the-national-health-service-act-2006#financing-from-outside-the-dhsc-group The case should set out the value of the expected loan, the assumed term and interest. The repayments and affordability should be assessed and clearly stated. | bar: FI; DI DI
Financial | External Funding Sources | 4.4.3 | Grants and Donations | Finance Digital | FC: FC; FI: FI; DI DI: DI | If grants or donations have been assumed, the case must set out what has been secured and what is the plan to secure the remainder. In general, it is expected that 50% should be secured at OBC, but this will be discussed with NHSE and DHSC on a case by case basis to determine the most appropriate level to be secured based on the risk of those donations and the value of them required to support the scheme. Any conditions attached to donated income or grant funding should be clearly set out.
Financial | Revenue Affordability |  |  |  | FC: FC; FI: FI; WO: WO; NHP: NHP; DI DI: DI | Revenue Affordability
Financial | Revenue Affordability | 4.5.1 | Revenue Affordability | Workforce Digital | FC: FC; FI: FI; WO: WO; DI DI: DI | The OBC should include an incremental Statement of Comprehensive Income, Statement of Cashflows and Statement of Financial Position and Trust-wide Statement of Comprehensive Income including the impact of the proposed investment on the bottom line financial position of the trust. The financial statements should demonstrate the revenue impacts of the build and the delivery of future services. The OBC should include detail of CIPs and other initiatives on which affordability depends. Where there is an adverse impact upon the I&E positon (short term or longer term) this must be explained and the case sets out plans to mitigate these costs pressures and ensure the financial impact is affordable to the Provider and will be managed within the ICS financial envelope. There should be clear alignment and a reconciliation included that details the alignment of the revenue assumptions in the CIA and Financial case (including cash releasing benefits) for the Preferred Way Forward. The activity and growth assumptions in the OBC must also align with the letters of commissioner support. |  |  |  |  | To support the FCR the case should clearly demonstrate revenue affordability. The Trust should provide a working file to support the calculation of the statements. Any revenue funding assumptions should align with approved national programme funding allocations and confirmed in writing. Where additional revenue is assumed from Commissioners / ICB this should be clearly set out in a letter of support. The financial case should ensure any matched funding requirements (Capital and / or Revenue) are met and should clearly set out the assumptions made.
Financial | Revenue Affordability | 4.5.2 | Efficiency Savings | Finance | [14 empty] | Confirm and detail any efficiency savings as a consequence of the scheme based on reasonable assumptions | bar: FI
Financial | Special Purpose Vehicles / Subsidiaries |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP | Special Purpose Vehicles / Subsidiaries
Financial | Special Purpose Vehicles / Subsidiaries | 4.6.1 | SPV / Subsidiary | Finance Estates Digital | FI: FI; ES: ES; ESR: ESR | If the organisation is intending to create an SPV, Joint Venture or Subsidiary, or where the proposal includes materially changing a Subsidiary, the business case must follow the approval process described in NHSE guidance - Guidance for assuring and supporting complex change – subsidiaries guidance for trusts forming or changing a subsidiary - before NHS Trusts and Foundation Trusts can implement such plans. |  |  |  |  | Additional review requirements for NHS Trusts For all NHS Trust subsidiary proposals, the business case must demonstrate to the Secretary of State that the subsidiary is income generating. We will co-ordinate our review process (if triggered) with that for obtaining Secretary of State consent on a case-by-case basis, considering the inherent risks of each proposal. This includes determining whether we should complete our review before the trust obtains the required consent from Secretary of State. Trusts should inform NHS England of proposals at the earliest opportunity so that we can align the review processes.
Financial | Technical Checks |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Technical Checks
Financial | Technical Checks | 4.7.1 | Accounting Treatment | Finance Digital | FI: FI; ES: ES; DI DI: DI | If the proposed accounting treatment requires professional judgement, an external audit option should be provided with the OBC. This would include for example leases, design and build contracts, managed service/equipment arrangements, Energy Service Performance Contracts (ESPC), use of Special Purpose Vehicles (SPVs). This should include formal VAT advice required to evidence VAT treatment set out in the OBC.
Financial | Technical Checks | 4.7.2 | Revenue / Capital Split | Finance Digital | [14 empty] | Confirm the split of costs between revenue and capital in-line with the current capitalisation policy. | bar: FI; DI DI
Financial | Technical Checks | 4.7.3 | Ownership of Capital Assets | Finance Digital | [14 empty] | Where the Business Case includes the purchase or creation of capital assets is it clear which organisation will own the assets and whose asset register they will sit on | bar: FI; DI DI
Financial | Technical Checks | 4.7.4 | Recharges | Finance Digital | [14 empty] | The OBC should set out any re-charges to other organisations that result from this scheme, with the recovery of costs or income generated factored into the case. | bar: FI; DI DI
Financial | Technical Checks | 4.7.5 | Procurement Costs | Finance Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm the procurement costs have been clearly set out, including the basis for internal costs of the project team and the costs of advisers and technical support
Financial | Technical Checks | 4.7.6 | Leases | Finance Digital | FI: FI; ES: ES; DI DI: DI | Where leases are being entered into, confirm these have been correctly accounted for as finance or operating leases in accordance with the applicable accounting standards.
Financial | Technical Checks | 4.7.7 | Contract / Staff Costs Split | Finance Digital | [14 empty] | Confirm all contract resources have been split out from staff costs and shown as separate line items with correct treatment of VAT | bar: FI; DI DI
Financial | Technical Checks | 4.7.8 | Stamp Duty | Finance Digital | [14 empty] | Confirm the treatment of Stamp Duty, Corporation Tax or any other taxes compliant with relevant legislation | bar: FI; DI DI
Financial | Technical Checks | 4.7.9 | Indexation | Finance Digital | [14 empty] | Confirm the indexation assumption accurate and appropriate | bar: FI; DI DI
Financial | Technical Checks | 4.7.10 | Financial Analysis | Finance Digital | [14 empty] | Confirm the financial analysis has been updated to take account of any changes in costs, and to show the effect of the proposed contractual payments | bar: FI; DI DI
Financial | Contingencies |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Contingencies
Financial | Contingencies | 4.8.1 | Contingencies / Other Funding Sources | Finance Digital | [14 empty] | The OBC should consider what (if any) other sources of finance there might be available to the Trust, and how this affects the affordability position. | bar: FI; DI DI
Financial | Contingencies | 4.8.2 | Contingency Plans | Finance Digital | FI: FI; ES: ES; DI DI: DI | Confirm contingency plans are described, e.g. for alternative sources of funding, if assumptions turn out to be wrong or insufficient. The OBC should set out any flexibility to fund any additional revenue requirements or to absorb any affordability gaps that emerge. If so, the OBC should confirm complaince to HMT guidance on contingent liabilities as described within Managing Public Money.
Financial | Contingencies | 4.8.3 | Financial Appraisal | Finance Digital | [14 empty] | Confirm the assumptions underlying the financial appraisal (including cost of risk mitigation) have been analysed for their robustness. | bar: FI; DI DI
Financial | Contingencies | 4.8.4 | Sensitivity Analysis | Finance Digital | [14 empty] | Confirm that a sensitivity analysis has been carried out on the relevant variables in the affordability analysis | bar: FI; DI DI
Financial | Costs |  |  |  | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Costs
Financial | Costs | 4.9.1 | Costed Equipment Schedule | Finance Digital | FI: FI; ES: ES; ESR: ESR | Confirm that a costed equipment schedule been provided |  |  |  |  | Information must be consistent with costs provided in the business case and Cost (OB) Forms
Management |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Management | Other | 5.1.1 | All Documents and Appendices Complete and Included | Assurance | [14 empty] | Confirm all relevant documents and appendices been completed, checked, signed off, listed in the business case and confirmed to be submitted with the Business Case when it is submitted for the review and approval process. Missing documents may cause delay or rejection in relation to the approval process. | bar: ESR AS
Management | Project Plan |  |  |  | FC: FC; FI FI: FI; ES ES: ES; ESR ESR: ESR; ESR DI: DI | Costs
Management | Project Plan | 5.2.1 | Contract Management Plan | Estates Assurance Strategy | FC: FC; ES ES: ES; ESR ESR: ESR; ESR AS: AS; ESR ST: ST | The OBC should set out the project plan, including the key delivery milestones and activities. This plan should be realistic, outline resources required for activities and any need for specific capabilities and competencies required to manage the design, build and operational phases of the scheme, and include sufficient time for business case review and approval, procurement and negotiation, and construction of the facility, as well as ensuring there is sufficient time allowed for all approvals (NHSE + DHSC, HMT, CO, BSA, etc). Use of any specialist advisers should be detailed. The OBC should also set out the delivery methodologies to be used (e.g. Agile, Waterfall, mix) and outline the resource and contingency plans. Dependencies (e.g. regulatory approvals, linked projects, funding stages) should be identified and mapped accordingly (e.g. in the RAID log and or within the Project Gantt chart). Any key assumptions should also be detailed.
Management | Project Plan | 5.2.2 | Workstream Interdependencies | Design Review Assurance | DR DA: DR; ESR ESR: ESR; ESR AS: AS | The case should confirm other work stream milestones and their interdependencies with the proposal. |  |  |  |  | Other work streams may include workforce, equipment, training, benefits delivery Clear delivery dates and detailed milestones should be provided.
Management | Project Management |  |  |  | FC |  | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO |  | NHP | DI | Project Management
Management | Project Management | 5.3.1 | Project Management | Digital | FC | [12 empty] | DI | The Case should identify the SRO for the project and have identified specific resource to make up a project team. The structure of the programme team and governance arrangements should be identified, with reporting lines and escalation processes should be clearly outlined. The Terms of Reference for governance boards and sub-groups should be provided. The experience of the SRO and programme team in delivering major schemes should be clearly set out to demonstrate the capacity and capability of the team to deliver the project, as well as the budget and resources required to deliver the project to completion. The Trust should provide an Integrated Assurance and Approvals Plan (IAAP) as part of the OBC. | bar: DR FI
Management | Project Management | 5.3.2 | Resources Plan | Clinical Finance Estates Strategy Economics Policy Digital |  |  |  | CL | FI | ES | ESR |  | ST | EC | PO |  |  | DI | At OBC the Trust should outline their full project plan of the resources required for activities, and any need for specific capabilities and competencies required to manage and deliver the procurement, and contract management post-FBC. The Trust should detail specialist advisers in place to support the scheme, and reference these in the commercial and financial cases at OBC. The requirement for special advisers usually falls into four key categories in the project plan: financial, legal, technical and programme / project management. Where possible existing framework routes to market (e.g. NHS SBS framework) should be used.
Management | Project Management | 5.3.3 | Project Management Budget | Finance Estates Assurance Strategy Economics |  |  |  |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | A breakdown of the budget should be provided. The budget should incorporate appropriate contingencies (and provide a rationale for these), and be consistent with the financial case.
Management | Project Management | 5.3.4 | Executive Support and Sign Off | Design Review Design Appraisal Finance Estates Assurance Strategy Economics |  |  | DR DA |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | The OBC should set out the project structure to provide assurance that the project has sufficient backing by, and commitment from senior executives and user groups to underpin a successful project.
Management | Project Management | 5.3.5 | Project Management Methodology | Finance Estates Assurance Strategy Economics |  |  |  |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | Confirm that the project management methodology been defined |  |  |  |  | The recommended project methodology is PRINCE 2 - Projects IN Controlled Environments, which is the de facto standard in use within the public sector in the UK.
Management | Project Management | 5.3.6 | Skilled Resource | Assurance | [14 empty] | Confirm there is sufficient and adequately skilled resource available to successfully manage the procurement, implementation and operational stages. |  |  |  |  | The skills set of the team and any skills gaps are identified. Plans are set out on how skill gaps are to be filled, including any plans to use advisers. Who will be responsible for contract management? How does their work fit into the overall project management structure? The role of advisers is set out, including the terms on which they have been appointed, confirmation of the breadth of their appointment, and arrangements to manage their fees; | bar: AS AS
Management | Project Management | 5.3.7 | Better Business Case Training | Assurance | [13 empty] | DI | Confirm that the Business Case Development Lead (ie Project Manager), Finance Lead and Estates Lead (for estates schemes)within the project team completed the mandatory Better Business Case training now required when working on NHS capital schemes and projects. | bar: AS AS
Management | Project Management | 5.3.8 | Confirmation of Management Training | Assurance | [14 empty] | Demonstrate that there are plans and adequate management arrangements put in place to resource and manage the bids, preferred bidder appointment and contract in accordance with NHSE and HM Treasury requirements for such projects (Better Business Case training). | bar: AS AS
Management | Project Management | 5.3.9 | Adequate Management Arrangements for External Engagement | Design Review Design Appraisal Assurance |  |  | DR DR DA: DR DR; AS AS: AS |  |  |  | Describe how executive clinical leaders, frontline clinical and non-clinical staff, and other stakeholders have been involved in shaping and influencing proposals, including eliciting and acting on patient feedback. The OBC should confirm that the organisation met its duties under s242 of the NHS Act 2006 to involve and where necessary carry out a full public consultation with patients, the public and other stakeholders. Describe the interface with community partners and development / understanding of patient pathways.
Management | Project Governance Reporting and Monitoring | [16 empty] | DI | Project Governance Reporting and Monitoring | bar: DR DR DA to AS PO
Management | Project Governance Reporting and Monitoring | 5.4.1 | Reporting Structures | Assurance Digital | [13 empty] | DI | Confirm the reporting structure and monitoring arrangements have been set out. |  |  |  |  | This should identify who is involved in reporting and monitoring, when and how this takes place and the anticipated cost. | bar: AS AS
Management | Project Governance Reporting and Monitoring | 5.4.2 | Project Board | Assurance Digital | [13 empty] | DI | Confirm the plan include full details of the membership and terms of reference of the project board and sub-groups in the project management structure. |  |  |  |  | The case should include an organogram or other representation of the project structure and governance (including links to the organisation’s Board). | bar: AS AS
Management | Project Governance Reporting and Monitoring | 5.4.3 | Routes of Escalation | Assurance Digital | [13 empty] | DI | Confirm the governance structure that is operating in support of scheme development and delivery and the routes of escalation across that structure to resolve issues. This should include the authority and delegated limits for decision making roles. | bar: AS AS
Management | Benefits Management | [5 empty] | DR FI: FI; DR ES: ES; AS AS: AS; AS EC: EC |  |  | DI | Benefits Management
Management | Benefits Management | 5.5.1 | Benefits Management | Estates Assurance Economics Digital | FC |  | DR ES: ES; AS AS: AS; AS EC: EC |  |  | DI | The OBC should set out the project's benefits management approach. It should outline the benefit realisation plans, including the monitoring and evaluation of benefits post-completion of the project. A benefits register, which captures all benefits, should be appended for central oversight.
Management | Benefits Management | 5.5.2 | Benefits Realisation | Finance Assurance Economics |  |  | DR FI: FI; AS AS: AS; AS EC: EC |  |  |  | Confirm that there is a benefits realisation table and plan. |  |  |  |  | At OBC stage the benefits strategy should be outlined. At FBC stage a detailed plan should be included. These should cover all benefits, CRB and non-CRB, and should reconcile with the economic benefits identified and valued in the economic case. The benefits should be quantified and measurable. There should be a clear plan to ensure monitoring and evaluation of the quantified benefits. This needs to include a time frame, accountable owner and ensure that the criteria for measurement have been identified.
Management | Change Management | [5 empty] | DR DA | CL | FI | ES |  | AS | ST | EC | PO | WO |  | DI | Change Management
Management | Change Management | 5.6.1 | Contract Management Plan | Estates Assurance Strategy |  |  | DR ES: ES; ESR ESR: ESR; AS AS: AS; AS ST: ST |  |  |  | Confirm that there is a robust contract management plan.
Management | Change Management | 5.6.2 | Plan for Change and Contract Management | Clinical Finance Estates Strategy Economics Policy Digital |  |  |  | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | The OBC management case should detail a change management plan that describes how resource capability will be developed according to the degree and pace of change required, such as through learning and development or through the appointment of specialist advisers. The change management plan should identify changes required to systems, processes and other governance arrangements, such as the contract management of specialist advisers by the SRO. The aligning of capability to support the project may involve considerable internal change, and the Trust should ensure that staff and their representatives are included in a process of dialogue.
Management | Change Management | 5.6.3 | Impact of Preferred Option Considered | Design Review Design Appraisal Estates Assurance Workforce |  |  | DR DR DA: DR DA; DR ES: ES; AS AS: AS | WO |  |  | Confirm that the organisational and cultural impact of the preferred option has been considered. Confirm the necessary measures been put in place to manage the organisational and cultural changes arising from the impact of the scheme. |  |  |  |  | For example, the identified impact of deployment should be consistent with wider organisational strategies e.g. human resources, estates or clinical services.
Management | Change Management | 5.6.4 | User Support Proposals | Assurance | [14 empty] | Confirm the business case demonstrates that users fully support the project and are committed to it. Confirm the business case includes detailed plans for user involvement in the planning and implementation of the project. | bar: AS AS
Management | Risk Management |  |  |  | FC |  | DR CL: CL; DR FI: FI; DR ES: ES; AS AS: AS |  |  | DI | Risk Management
Management | Risk Management | 5.7.1 | Risk Register | Estates Assurance Digital | FC |  | DR ES: ES; ESR ESR: ESR; AS AS: AS |  |  | DI | The OBC should include a detailed and costed risk register with clear owners for the management and mitigation of each risk.
Management | Risk Management | 5.7.2 | Risk Management / Orange Book | Estates Assurance Digital | [14 empty] | The OBC should confirm compliance with the HMT Orange Book, specifically regarding Risk Management, application of the Risk Management Framework and Risk Assurances Processes.
Management | Risk Management | 5.7.3 | Risk Management Plan | Clinical Finance Estates |  |  | DR CL: CL; DR FI: FI; DR ES: ES; ESR ESR: ESR |  |  |  | Confirm that a risk management plan been provided in which risks are appropriately identified, mitigated and managed. |  |  |  |  | Contingency plans should be set out, and risks are allocated to the most appropriate party. Potential cost overruns are provided for in the affordability analysis.
Management | Other | [14 empty] | WO |  |  | Other | bar: DR DR DA to AS PO
Management | Other | 5.8.1 | Business Continuity | Assurance Workforce | [11 empty] | WO |  |  | Describe arrangements for business continuity during the implementation period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. |  |  |  |  | Describe arrangements for business continuity during the build period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. | bar: AS AS
Management | Assurance | [14 empty] | WO |  |  | Assurance | bar: DR DR DA to AS PO
Management | Assurance | 5.9.1 | Gateway Reviews | Assurance | FC | [13 empty] | The OBC should record arrangements for Gateway reviews and organisational Health Checks (if applicable). The project's Integrated Assurance and Approvals plan should be appended, along with the Risk Potential Assessment (RPA). The OBC should also detail the actions taken, or to be taken, to comply with the recommendations of Gateway assurance reviews which have already taken place. | bar: AS AS
Management | Assurance | 5.9.2 | Post-Implementation and PPE | Design Appraisal Clinical Finance Estates Assurance Strategy Economics |  |  | DA | CL | FI | ES | ESR | AS | ST | EC |  |  |  |  | PPE is an important element of any scheme to ensure lessons are learned and improvements made across all aspects of Capital Projects. The trust is to confirm that PPE lessons from previous schemes have been implemented in this scheme and that records are being maintained to enable a full and complete PPE to be prepared and completed for this project. It should also be noted that NHSE have a mandatory requirement that detailed project outturn costs are provided promptly as part of the PPE process. Annex 2 of the Capital Guidance includes post-project evaluation templates that can be utilised by Trusts in undertaking this exercise: https://www.england.nhs.uk/wp-content/uploads/2023/02/B1376iii-annex-2-post-project-evaluation-templates.pdf |  |  |  |  | Is there a clear definition of the scope of the post project evaluation, approaches to be adopted (e.g. the Magenta Book), timescales and specific milestones reviews? Plans should be consistent with the benefits identified in the economic case and in line with overall objectives. What is the resource for this? Are costs for PPE included in the project cost? Participation in wider aggregate research may also be appropriate and beneficial. N.B. A Stage 5 In-Use Design Quality Indicator (DQI) assessment is classified as an element of PPE. The DQI PPE supports the benefits realisation PPE requirement of the Capital Investment Manual and HM Government mandatory BIM (Building Information Modelling) “Soft-landings” process for 2016 (Government Soft Landings). NHS England PAU also has designed templates to aid with this process. These can be provided upon request.
Management | Assurance | 5.9.3 | External Design Evaluation Support | Design Review Design Appraisal Estates |  |  | DA | CL | FI | ES | ESR | AS | ST | EC |  |  |  |  | Where applicable, the business case should provide evidence that specialist and relevant external design advice has been sought on design, build, health and safety, fire code, estate issues and information technology together with RPA in radiological areas. Provide a statement that this evaluation support has been signed off. This is also directly linked to the consideration and approval of any derogations proposed on this project
Management | Assurance | 5.9.4 | PAM | Digital |  |  | DA | CL | FI | ES | ESR | AS | ST | EC |  |  |  |  | Confirmation that the Trust has completed the Mandated NHS Premises Assurance Model (PAM) Standard Assessment Questionnaire for the health organisation and confirmation that this has been approved by the health organisation’s Board or Governing Body.
Management | Digital | [14 empty] | WO |  | DI | Digital
Management | Digital | 5.10.1 | Training | Workforce Digital | [11 empty] | WO |  | DI | Detail the outline training programme for all relevant staff, both users and project team members. |  |  |  |  | Detail should be provided about whether the organisation has a training infrastructure already, how will training be developed, and who will develop it.
Management | Digital | 5.10.2 | Delivery Plan | Digital | [13 empty] | DI | The OBC should include a detailed delivery plan that incorporates the full implementation and transition into live running / BAU.
Management | Digital | 5.10.3 | Delivery Plan | Digital | [13 empty] | DI | The case should document the evidence that security and confidentiality have been addressed in accordance with information governance principles.

## 1c. FBC FC +Checklist
2c. Full Business Case (FBC) Checklist | [19 empty] | Provider Self Assessment |  | Regional Fundamental Criteria Assessment |  | Additional Checklist Information
2026-03-10
5 Case Model Heading | Sub-Heading | Business Case Checklist Reference Number | Category | Discipline / subject matter covered Formal or possible associated input / interest | Fundamental Criteria | Commissioning | Design Review. Design Appraisal | Clinical | Finance | Estates | Estates Standard Review | Assurance | Strategy | Economics | Policy | Workforce | NHP (New Hospital Programme) | Digital BC | Item / Section See Note B. on Introduction about Fundamental Criteria (FC) Where confirmation is asked for in the requirement, evidence should be provided with that confirmation. Light blue cell shading identifies the current FC item in the various sections | Provider Self Assessment RAG Rating Yes = Green Partly = Amber No = Red Completed by Provider | Where is this covered in the Business Case? Document, Appendix, section and / or page | Regional Fundamental Critiera RAG Rating Yes = Green Partly = Amber No = Red Completed by Regional FCR Reviewer | Please highlight in this column any areas where the Fundamental Criteria have not been fully met. | General Notes and Guidance Any links and guidance provided in this checklist may change over time. The Trust / ICB must therefore always establish that the guidance used is current and appropriate.
Strategic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Strategic | Approval and Support |  |  |  | FC: FC; AS: AS; DI: DI | Approval and Support
Strategic | Approval and Support | 1.1.1 | Board approval | Assurance Digital | FC: FC; AS: AS; DI: DI | Trust Board Approval - Confirm the date when the business case was approved by the Trust Board. Submission Requirements - The Business Case should be submitted with completed self-assessed Fundamental Criteria Checklist, to ensure that core requirements are met. This will enable swifter approvals. Letters of Support - ICB and Trust - The Business Case should be submitted with a Letter of Support from both the ICB as strategic commissioner and the Trust. Guidance on Letters of Suppport content and template letters are set out in Annex 3 of the NHSE Capital investment and property business case approval guidance. The Letters of Support should include the following (template lettes are included in Annex 3) - ICB Letter - Support for the business case, public consultation requirements have been met, alignment with ICB strategic commissioning/clinical strategy, affordability. - Trust Letter - Trust Board approval, capital affordability, revenue affordability, accounting treatment, alignment with local estates, digital and workforce strategies, deliverability. Cabinet Office (CO) Commercial Controls - If any of the contracts within the scheme are expected exceed the Cabinet Office Controls threshold the Trust will need to ensure that this contract value is reported onto the Regional Commercial Pipeline for CO oversight, and that the "Business Case Six Test Checklist" is completed and accompanies the business case submission. Trusts that will require CO approval should refer to this within their business case and ensure there is sufficient time to secure CO approval within the programme plan. |  |  |  |  | Provide minutes of the Board / Governing Body meeting approving the business case. The Board/Governing Body has approved all parts of the business case, e.g. strategic fit and the financial/operational impact. If there is more than one SRO / approving body, then the senior or lead SRO should take responsibility for submitting the case. The significance of the SRO role at this stage is to show ownership, and to formally signify the start of the review / approval process.
Strategic | Approval and Support | 1.1.2 | HMT guidance followed | Assurance Digital | [14 empty] | Confirm that the HMT Green Book has been followed in developing the business case. | bar: AS; DI
Strategic | Approval and Support | 1.1.3 | Previous Approvals | Assurance | FC: FC; AS: AS; DI: DI | The case should demonstrate that all approval conditions from the OBC have been met. A log of these should be included as an appendix to the main case. For Electronic Patient Record Business Cases, the EPR Investment Board provides a completed Conditions Log with the Letter of Approval and will provide a confirmation e-mail when all conditions have been closed, so the Trust can enter contract post-FBC approval. The Trust must demonstrate that any other 'open' conditions set for closure either prior to or as part of the next business case stage have been met.
Strategic | Approval and Support | 1.1.4 | Cabinet Office Controls | Assurance Estates | FC: FC; ES: ES; AS: AS; DI: DI | The Cabinet Office Local Spend Control process is a separate approval process, which assesses a set of commercial principles and aims to provide support to Trusts at the earliest planning stage, prior to launch of their procurement. A submission to the Atamis Portal, or as directed, should be made as early as possible, to get a CO decision. If following submission, the CO applies a 'control' status and wishes to approve at OBC stage, then the completed Cabinet Office documentation and associated artefacts should be submitted with the business case for Fundamental Criteria Review, so any amendments can be made during detailed business case review. This applies to Digital and non-Digital, based on supplier commercial spend. Unless agreed otherwise with Cabinet Office - at FBC, the Trust should expect to seek approval when the FBC is complete. It may have been agreed at OBC that the Trust is authorised to self-certify, but unless this has been confirmed, the Trust should plan for CO approval.
Strategic | Approval and Support | 1.1.5 | Cabinet Office Controls | Assurance Estates | FC: FC; ES: ES; AS: AS; DI: DI | Trusts should confirm that their Business Case is accompanied by a completed Digital and Technology Question Set. These have been published on the NHS Futures Sharepoint, with access provided by the Transformation Directorate team. Reference should be made to the Trust’s strategy for cloud data storage, and alignment with Government and NHS Public Cloud Hosting Policy. Trust should engaged with the Cloud Centre of Excellence and address any recommendations from that engagement as it is expected they meet the NHS Public Cloud Hosting policy. The assessment form for the EPR Technology & Digital Assessment may be found on the Frontline Digitisation Support Offer webpages on the NHS Futures Sharepoint or the related MS Teams Channel.
Strategic | Strategic and Policy Context |  |  |  | FC |  |  | CL | FI | ES | ESR | AS | ST |  | PO |  |  | DI | Strategic and Policy Context
Strategic | Strategic and Policy Context | 1.2.1 | Strategic Context | Clinical Finnce Estates Strategy Policy Digital | FC: FC; CL: CL; FI: FI; ES: ES; ST: ST; PO: PO; DI: DI | The context and case for change should be set out clearly, with local and national drivers for the change identified. The Trust should show how the proposals align to government and DHSC policy. This case for change should be evidence based and should articulate the proposed clinical model, underpinned by demand and capacity modelling. It should demonstrate: - the links to enabling strategies, e.g. workforce, patient experience and patient safety; - consideration of quality, workforce and financial / efficiency considerations; - stakeholder engagement, including with clinical leaders and trust staff to assess clinical oversight and involvement in the business case development; - alignment with both local and national service configuration, commissioning intentions and patient-centred design and build; - consistency with Trust digital strategy. A link or copy of the strategy should be appended or made available. - a clear commitment to IT systems interoperability should be made to the effect that 'any digital technology deployed, must be compliant with all relevant functional and interoperability standards. We need to be clear that the organisational overview sets out the relationship with key partners, in delivering care, patient flow etc, in addition to an overview of which trusts and hospitals are involved e.g. Acute, Community, Mental Health, Ambulance, how many beds, how many staff, how many in-patient episodes, and out-patient episodes. Also the latest CQC rating. The 'case for change' should also focus on the current gaps in local digital services as well as future gaps against business plans and strategy. Brief Reference to relevant national policy and strategy drivers e.g., national published documents such as the 'Ten-Year Health Plan: Fit for the Future' is advised. Clear case for change including presentation of the ICB roadmap and trust existing digital landscape, (with a graphical diagram or table) and indication of current digital maturity, and identifying gaps, problems, and opportunities, for improving productivity and reducing clinical risk against the national and ICB and local business strategy and published guidance i.e., the digital baseline. Inclusion of a good evidence base can help to support generalisations that are often made around patient experience, clinician’s needs that are not direct consequences of digitisation. The FBC may incorporate the outcomes of an initial Agile discovery and Alpha phase or pilot. For Agile Digital Projects an overall PBC should be considered. |  |  |  |  | For EPR Cases the strategy is to achieve a minimum Digital Maturity of HIMSS Level 5 / MDF with a view to be able to reach HIMSS 6 or 7 with future extension / optimisation of the solution The regional team should review and confirm the Digital Strategy / Management is robust and fits with Region and ICS digital strategy. Assurance is sought from Regional Digital leads that the case fits with regional convergence (Requirements and relevant standards may change over time)
Strategic | Strategic and Policy Context | 1.2.2 | Engagement and Integrated Working | Commissioning Design Review Design Appraisal Clinical Finance Estates Assurance Strategy Digital | CO: CO; DR DA: DR DA; CL: CL; ES: ES; AS: AS; ST: ST; DI: DI | The Trust should provide evidence of how the lead commissioning organisation has engaged with their patients and / or users, stakeholders, wider public / population and governors (as appropriate) in setting the clinical and service priorities that led to the scheme design and objectives. The case should provide evidence as to what extent the proposal will or has promoted integrated working between health, social care and public health, and should reflect on any post-project evaluations relating to the current service. In proposals that aim for ‘transformation change’, the nature of the change needs to be transparently explained, with objective evidence on which it is based and objective support for the assumptions made. A credible explanation of the change process is required, with detail as to how uncertainty will be handled. Annex A7 of the HMT Green Book needs to be understood and considered. |  |  |  |  | For Digital Technology projects, Discovery and Alpha phases will precede the SOC and inform the direction of the project.
Strategic | Strategic and Policy Context | 1.2.3 | Patient Choice | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that the scheme as now developed will provide greater patient choice on where and how to access care, and / or improved quality and safety of service provision |  |  |  |  | See Operational Guidance to the NHS: extending patient choice of provider.
Strategic | Strategic and Policy Context | 1.2.4 | Equality and Diversity | Clinical Estates Strategy | CL: CL; ES: ES; ST: ST | Confirm that any equality and diversity impact has been assessed and actively addressed, and that this is submitted as an appendix. |  |  |  |  | The proposal must pay due regard to the public-sector equality duty in line with the principles and requirements of the NHS Constitution and with current legislation and guidance.
Strategic | Strategic and Policy Context | 1.2.5 | Organisational Change | Clinical Finance Strategy | CL: CL; FI: FI; ST: ST | If there have been any strategic or organisational changes following approval of a previous business case, ensure these been adequately explained and their effects on the investment described. Confirm the demand assumptions in support of the size and scope of the investment still valid. |  |  |  |  | Does the recommended solution still provide all of the required services – both current and future?
Strategic | Strategic and Policy Context | 1.2.6 | Social Value | Clinical Finance Estates Strategy Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; ST: ST; DI: DI | Decribe the social value themes that have been under taken in the assessment, share your timed action plans and confirm that 10% minimum of scoring is weighted to social value.
Strategic | Rationale and Objectives |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC |  |  | NHP | DI | Rationale and Objectives
Strategic | Rationale and Objectives | 1.3.1 | SMART / Strategic Objectives | Digital | [13 empty] | DI | The FBC needs to identify the SMART (Specific, Measurable, Achievable, Relevant and Timebound) spending objectives associated with the project, and set out reasonable spending objectives linked to benefits. These objectives will need to be linked with Critical Success Factors and the identified benefits. These objectives will also need to link to wider government strategic priorities, as set out in the case for change, as well as directly link to Fit for the Future: 10 Year Health Plan for England priorities. Clear Investment or Spending Objectives must be linked to key strategy or business gaps such as replacement of legacy, levelling up capability, compliance, improving productivity, clearly derived from the strategic context and case for change. It should be clear that the investment is about clinical service transformation outcomes, improvement, and risk reduction, not just the technology. It may be more appropriate to develop a programme business case to look at a range of digital projects and services, phased over time, that could achieve better transformation and outcomes, particularly at ICS level. The FBC should confirm if there have there been any changes to the original scope or objectives since SOC, and set out if these changes have any material impact on the delivery of the objectives. | bar: FC
Strategic | Clinical Quality |  |  |  | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  |  | Clinical Quality
Strategic | Clinical Quality | 1.4.1 | IT Integration | Clinical Digital | [13 empty] | DI | Demonstrate how the specification for the Digital / IT system will integrate with other systems for the purposes of patient quality and safety. Describe and present the findings and outcome of the risk assessment and the impact on quality, including risks identified and the mitigation plan. Present the added clinical benefits of the new system. Provide evidence of clinician engagement and involvement in the project governance process. | bar: CL
Strategic | Clinical Quality | 1.4.2 | Delivery | Commissioning Clinical Finance Estates Strategy Digital | CO: CO; CL: CL; FI: FI; ES: ES; ST: ST |  |  |  | DI | Describe how the scheme will support the delivery of the organisation’s clinical strategy and aligned to commissioning intentions as supported by the Provider Digital and Estate Strategies. Confirm if and when was the organisations clinical strategy was completed and signed off. Confirm if and when the Provider Digital and Estate Strategies was completed and signed off.
Strategic | Risks, Constraints and Dependencies | [5 empty] | DR DA | CL | FI | ES | ESR | AS | ST |  |  |  |  | DI | Risks, Constraints and Dependencies
Strategic | Risks, Constraints and Dependencies | 1.5.1 | Constraints and Dependencies | Digital | [13 empty] | DI | Key constraints and dependencies should be identified, particularly those separate projects, e.g. infrastructure improvements on which the successful delivery of this project will depend. The constraints should relate to standards and conformance with technology code of practice and other GDS and Transformation Directorate guidance can be brought out. e.g. 'digital first' principles.
Strategic | Strategic and Policy Context | 1.5.2 | Carter Efficiency | Finance Estates | FI: FI; ES: ES; ESR: ESR |  |  |  | DI | The Trust should confirm that the project complies with relevant Carter efficiency recommendations |  |  |  |  | The case should refer to Lord Carter of Coles 2015 report: Operational productivity and performance in English NHS acute hospitals: Unwarranted variations, and identify the recommendations being delivered by the project.
Strategic | Strategic and Policy Context | 1.5.3 | Integrated Care and Digital Convergence | Finance Estates | [13 empty] | DI | The Trust should provide details of the strategy for delivering integrated care and convergence of digital solutions across the ICS, within the case or supporting documentation. | bar: FI to ES
Strategic | Risks, Constraints and Dependencies | 1.5.4 | Digital Technology Capability | Digital | [13 empty] | DI | Provide a summary of the organisation's current Digital Technology capability. Confirm that this identifies the starting point for development of the Digital technology schemefor example. This should include the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise |  |  |  |  | An annex may include, for example, the configuration of current systems, the existing level of integration, the extent of paper-based systems, and the level of Digital Technology (information processing) expertise.
Strategic | Risks, Constraints and Dependencies | 1.5.5 | Gap' in Digital Technology Provision | Digital | [13 empty] | DI | Confirm that the "gap" in Digital Technology provision, between the current position and the identified objectives supporting health service delivery, is known.
Strategic | Risks, Constraints and Dependencies | 1.5.6 | Government Standards | Digital | [13 empty] | DI | Confirm that the programme demonstrate awareness and compliance with the relevant government standards and policies for technology. Confirm how it ensures these will be met. Confirm the applicability of the Technology Code of Practice and Digital by Default Service standard. |  |  |  |  | The Technology Code of Practice and Digital by Default Service standard always apply.
Strategic | Risks, Constraints and Dependencies | 1.5.7 | Service Assessment Scope | Digital | [13 empty] | DI | Confirm that the digital programme or any component is within the scope of service assessments. If so, the case should confirm at what stage and what were the outcomes of that assessment. |  |  |  |  | Service assessments are mandatory at alpha, beta and live stages of programmes. Failure to pass can prevent the programme continuing to the next stage or even prevent live deployment.
Economic |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Economic | Reconciliation | 2.1.1 | Reconciliation | Finance Assurance Economics | FC: FC; FI: FI; AS: AS; EC: EC | There should be a clear and transparent reconciliation of numbers across the CIA Model and Economic Case that identify the costs of each option. There should also be clear alignment across capital costs and revenue assumptions in the CIA and financial case (including cash releasing benefits) for the BAU and Preferred Way Forward - this is also referenced in the Finance Case FCRs.
Economic | Options Appraisal |  |  |  | FC | CO | DA | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | Options Appraisal
Economic | Options Appraisal | 2.2.1 | Options Framework | Commissioning Clinical Finance Estates Strategy Economics Policy Digital | FC | CO |  | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | It is not expected that the Trust fully re-evaluates the other options for consideration between OBC and FBC. If new options become apparent in the development of the FBC that may alter the scope from OBC to FBC, this should be compared to the previous preferred option, with incremental VFM analysis shown to demonstrate the option that has the highest VFM. The options appraisal should continue to demonstrate the relative value for money of the options taken into the Short List at SOC and OBC, including: - Business As Usual (BAU) – acts as a "Do Nothing" benchmark for Value for Money - ‘Do Minimum’ – a realistic way forward that also acts as a further benchmark for Value for Money. This option should set out the minimum capital investment required to deliver the core spending objective(s) underpinning the case for change. - A recommended Preferred Option, that combines the preferred way forward from all filters, unless this is identical to the Do Minimum. - One or more other realistic options, that use 'carried forward' options from at least one filter to become a more- or less-ambitious PWF. |  |  |  |  | HMT Green Book Options Framework is to be followed - recommended If, unusually, there is more than one preferred option, this should be explained, and the criterion applied to all of them.
Economic | Options Appraisal | 2.2.2 | Preferred Option | Commissioning Design Appraisal Clinical Finance Estates Strategy Economics Policy Digital |  | CO | DA | CL | FI | ES |  |  | ST | EC | PO |  |  | DI | Ensure that the Preferred Option has been described in sufficient detail to enable the assessment of costs, benefits and risks. Where appropriate, wider impacts should be assessed e.g. sustainability, competition, regulatory impact, place-based. The costs, benefits and risks must be granular enough to be able to demonstrate where they are coming from, 'capital costs' or 'cash releasing benefits' will not be sufficient to support the case.
Economic | Costs |  |  |  | FI: FI; ES: ES; EC: EC; DI DI: DI | Costs
Economic | Costs | 2.3.1 | All Costs Assessed | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that all relevant capital (build and lifecycle) costs, revenue costs (e.g. running costs, dual running costs, transitional costs) and opportunity costs been identified and properly assessed. |  |  |  |  | The costs should cover the whole life of the investment for all IT projects and for most build projects, where possible. They should take account of (if appropriate): lifecycle costs (building related and equipment/IT replacements), residual values, monitoring and evaluation costs, health organisational development costs, opportunity costs, second round effects, avoided costs and costs borne by others. Care should be taken not to double-count costs. See Green Book . Cost sources should be identified for all costs, including where these are estimates. Note that costs must be assessed on a ‘bottom-up’ basis: that is, the case must show the total costs of each option, not just costs incremental above existing levels of expenditure. Descriptions of how all costs have been quantified should be available along with supporting spreadsheets.
Economic | Costs | 2.3.2 | Key Cost Assumptions | Finance Estates Economics Digital | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that all key assumptions underlying the costs been clearly explained and justified |  |  |  |  | For example, the assumptions about the life of an asset. Reference the source documents underpinning these assumptions.
Economic | Costs | 2.3.3 | Costs in Real Terms | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that costs are shown in real terms, at constant (uninflated) prices, with the base year clearly specified and the current year shown as Year 0. Confirm the correct discount rate been used. For some goods or services there may be a relative price effect i.e. the movement of a specific price index (e.g. construction) may differ significantly from the general inflation (such as the GDP deflator). Where there is historical evidence and an expectation this will continue in the future, different rates of inflation can be used to reflect the relative difference. Where prices or values are expected to grow in real terms, these assumptions must be based on objective evidence, for example, long term trends in relevant indices. These assumptions should be transparently set out in the business case and assumptions agreed with the approving authority. |  |  |  |  | See Green Book
Economic | Costs | 2.3.4 | Sunk Costs | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that sunk costs (costs that has already been incurred and that cannot be recovered), transfer payments, VAT, capital charges, depreciation and other non-resource costs been excluded from the economic appraisal of costs in the CIA / NHS Digital Financial Model |  |  |  |  | Sunk costs are those already incurred, e.g. project management. Transfer payments include redundancy payments, VAT and local authority rates. Only income from non-government (third party) organisations should be included.
Economic | Costs | 2.3.5 | Appraisal Period | Finance Estates Economics Estates | FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm that the appraisal period appropriate to the life of the asset generated by each option |  |  |  |  | A view from the technical advisor should give the economic life of the asset generated by each option and must be stated. Where the appraisal period is different for alternative options, discounted costs must be expressed as equivalent annual costs rather than net present costs (NPC).
Economic | Costs | 2.3.6 | Environmental Costs | Finance Estates Economics Estates | FI: FI; ES: ES; EC: EC; DI DI: DI | Providers should refer to Annex A1 within the Green Book in order to ensure that they are accounting for the environmental costs of interventions. Total energy use and total GHG emissions should be quantified and costed utilising the BEIS Green Book supplementary guidance: valuation of energy use and greenhouse gas emissions for appraisal guidance document that has been published. |  |  |  |  | A view from the technical advisor should give the economic life of the asset generated by each option and must be stated. Where the appraisal period is different for alternative options, discounted costs must be expressed as equivalent annual costs rather than net present costs (NPC).
Economic | Benefits |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; WO: WO; NHP: NHP; DI DI: DI | Benefits
Economic | Benefits | 2.4.1 | Credible Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that appropriate and credible benefits (cash releasing, non-cash releasing, societal and quality) have been identified. Any disbenefits of investment should also be identified. |  |  |  |  | The benefits should be identified through consultation with stakeholders, e.g. through a benefits workshop. These may include cash-releasing, non-cash releasing or non-quantifiable (qualitative) benefits. See Green Book Benefits should be consistent throughout the case, i.e., strategic, economic, financial and management.
Economic | Benefits | 2.4.2 | Key Assumptions | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that supporting the benefit profiling are sources of evidence, including detailed calculations and assumptions and applied confidence and attribution, to ensure no double counting of benefits. |  |  |  |  | For example the assumptions about why a benefit might vary from one option to another, or be treated as non-cash releasing rather than cash-releasing. Please reference the source documents underpinning these assumptions.
Economic | Benefits | 2.4.3 | Quantified Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm that benefits have been quantified in line with HMT Green Book guidance. QALY benefits should be assessed on the basis that the current monetary "willing to pay" value for a QALY is £70,000. The case should also set out a costed profile of benefits. |  |  |  |  | Benefits should be monetised or measured to the extent that it proportionate or prudent to do so.
Economic | Benefits | 2.4.4 | Non-Quantifiable Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Where it is not possible to quantify a benefit, the FBC should explain why this is so and demonstrate that benefits have been separately qualitatively evaluated where possible. |  |  |  |  | The presumption should be not to define benefits which cannot be measured or for which there is no evidence base.
Economic | Benefits | 2.4.5 | Benefits Register | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm there a benefits register to support the benefits modelled in the economic analysis.
Economic | Benefits | 2.4.6 | Quantified Benefits Discounted | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Clarify if quantified benefits been discounted over the period of appraisal? Confirm that benefits have not been double counted. |  |  |  |  | Discount rate should be 3.5% if benefits are valued in real terms or 1.5% if Quality-Adjusted Life Years have been used in valuing benefits. For projects with very long-term impacts, over thirty years, a declining schedule of discount rates should be used (see Green Book Annex 6).
Economic | Benefits | 2.4.7 | Constant Value Benefits | Finance Economics Digital | FI: FI; EC: EC; DI DI: DI | Confirm the values of benefits been stated in constant (uninflated) prices and consistent with the cost assessment. |  |  |  |  | See Green Book
Economic | Risk | [6 empty] | CL | FI | ES | ESR | AS |  | EC |  | WO | NHP | DI | Risk
Economic | Risk | 2.5.1 | Risks and Lifecycle | Clinical Finance Estates Economics Digital | CL: CL; FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the risks associated with the options been appropriately identified across the whole lifecycle of the project. |  |  |  |  | These risks should be set out in a risk register (see also Management case) Whole lifecycle refers to the life of the project. This is normally the construction period plus 60 years operational life for new build investments. Refurbishment schemes are shorter, typically 25-30 years, depending on the anticipated life of the anticipated buildings. IT projects tend to be evaluated over a short time period, 7-10 years or even less, with allowances to renegotiate or extend the current contract.
Economic | Risk | 2.5.2 | Quantified Costed Risks | Clinical Finance Estates Economics Digital | CL: CL; FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the risks been fully quantified and costed at FBC stage. These should be presented in a matrix showing: 1. which party is responsible for managing risks 2. the probability of the risk 3. the impact of the risk 4. the expected cost of each risk (probability x impact) |  |  |  |  | A narrative should be provided explaining the methodology for the quantification of risks and how the probability has been derived
Economic | Risk | 2.5.3 | Risk Register | Clinical Finance Estates Economics Digital | CL: CL; FI: FI; ES: ES; EC: EC; DI DI: DI | Confirm the assumptions underlying the identification, timing and potential impact of the risks been explained and that there is a costed risk register to support this. |  |  |  |  | These should be covered in the risk register.
Economic | NPSV, Optimism Bias and Sensitivity Analysis |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | NPSV, Optimism Bias and Sensitivity Analysis
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.1 | CIA Model | Finance Economics Digital | FC: FC; FI: FI; EC: EC; DI DI: DI | The FBC will need to demonstrate use of the Digital Capital Investment Appraisal (CIA) Model for the economic modelling. We would expect that all schemes will use the CIA, and they will not be able to proceed without completing. The VFM analysis must quantify costs, risks, cash releasing benefits, non-cash releasing benefits and economic societal benefits. It must also evaluate un-monetisable benefits. There should be a clear and transparent reconciliation of numbers across the CIA Model and Economic Case, and the Capital Figures included in the Finance Case. There should also be clear alignment across revenue assumptions in the CIA and SOCI (including cash releasing benefits). |  |  |  |  | The CIA model is fully completed and all shortlisted options are fully presented within the model to reflect costs, risks, OB and benefits of each option. Trusts should include the fully costs and benefits of the options explicitly, i.e. not incrementally, to enable a comparison between the costs and benefits from OBC to FBC. The outputs from the CIA model are accurately reflected in the business case, i.e. overall economic appraisal including incremental analysis and presentation of the NPSV and BCR, information on costs, risks, and benefits. Explanations and workings to support the calculations of the costs, risks, OB and benefits are provided and clearly set out in the CIA and supporting documents. The appraisal period of the shortlisted options modelled in the CIA, especially the preferred option is consistent with the financial case, and all have been quantified over the lifespan of the proposal, including the BAU option. The costs presented in the economic case correctly exclude sunk costs, VAT, and capital charges (Depreciation and PDC dividend costs) and any other transfer payments. Only income from non-government (3rd party) organisations should be included. These should be identified when reconciling the costs presented in the economic and financial case. There should be a clear and transparent reconciliation of numbers across the CIA Model and Economic Case, the fully completed Cost Forms (OB / FB forms) and cost advisors report that identify cost of options, including any GMP, and the Capital Figures included in the Finance Case.
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.2 | Presentation of an Incremental VFM Analysis | Finance Estates Economics Digital | FC: FC; FI: FI; ES: ES; EC: EC; DI DI: DI | The FBC must present a value for money case for all options, which should demonstrate a quantified cost / benefit / risk analysis to determine the option that shows the best value for money. The Net Present Social Value and Benefit Cost Ratio must be presented for each of the short-listed options. Business cases are expected to follow the HMT Green Book and supplementary guidance. The value for money analysis is expected to be presented as incremental analysis, as requested by the Green Book, and all figures must align with the CIA model.
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.3 | Bid Evaluation | Digital | [14 empty] | The FBC should include an assessment of bids from service providers as part of the commercial case. In order to ensure that the different solutions being offered are appropriately evaluated economically, the FBC should introduce both the preferred and second choice providers into the CIA so that a direct comparison of costs, risks and benefits can be identified in the model. This is required due to the significantly different solutions offered by providers, with this additional analysis at FBC stage to provide additional confirmation that the preferred bidder is delivering the best value for money solution. The cost, risk benefit analysis should be applied to supplier options, where possible as the offerings may carry differing levels of functionality and risk such as additional volume related charges etc. The cost, benefit and risk analysis should be applied to supplier options, where possible. Offerings may carry differing levels of functionality and risk such as additional volume related charges etc. Appraisal should also be considered separately for the required contract length and when there are assumptions that extension provisions may be invoked | bar: FC; DI DI
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.4 | Optimism Bias and CIA | Finance Economics | [14 empty] | Confirm costs (e.g. Capital, lifecycle, operating costs) and benefits been adjusted for optimism bias in accordance with the guidance or using the methodology in the CIA. | bar: FI; EC
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.5 | Optimism Bias and CIA | Economics | [14 empty] | Does the FBC include a residual level of Optimism net of mitigations based on the lower bound percentages for this project type as recommended in the Green Book guidance. |  |  |  |  | Green Book - https://www.gov.uk/government/publications/green-book-review-2025-findings-and-actions/green-book-review-2025-findings-and-actions | bar: EC
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.6 | Demand Capacity Modelling | Economics | [14 empty] | Investment proposals must provide evidence of triangulation of demand and capacity modelling, workforce strategy, service development and efficiency programme across the lifetime of the scheme. The values used in the CIA for costs (capital and revenue), risks and benefits will need to reflect this. | bar: EC
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.7 | Sensitivity Analysis | Finance Estates Economics Digital | FC: FC; FI: FI; ES: ES; EC: EC; DI DI: DI | Economic Sensitivity Analysis is used to ensure that the preferred option is suitably robust in the event of changes to costs / benefits / risks. It is an important evaluation tool to demonstrate the robustness of the options appraisal and confirmation of the preferred option, and as such it should be further refined at FBC to show the continued strength of the preferred option.
Economic | NPSV, Optimism Bias and Sensitivity Analysis | 2.6.8 | Benchmarking analysis | Economics Finance Estates | FI: FI; ES: ES; ESR: ESR; EC: EC | The project cost advisor must provide a project cost benchmark comparator analysis to demonstrate the VFM of the proposed project in relation to other comparable projects.
Economic | Summary |  |  |  | DR DA: DR DA; FI: FI; ES: ES; ESR: ESR; AS: AS; EC: EC; NHP: NHP; DI DI: DI | Summary
Economic | Summary | 2.7.1 | OBC Option Appraisal | Design Appraisal Finance Estates Economics | DR DA: DA; FI: FI; ES: ES; EC: EC | Provide a summary of the OBC option appraisal, showing the long and short list, the result of the economic appraisal (including benefits and risks) and the sensitivity analysis. If the assumptions, scope or costs have changed since the OBC, does the FBC demonstrate either that the original preferred option remains valid, or that a new preferred option can be demonstrated to be so on NPSV grounds. If significant changes have occurred between OBC and FBC, it may be that new options need to be considered. |  |  |  |  | At FBC stage, the OBC economic appraisal should be reviewed to ensure it is consistent with the FBC. The economic appraisal undertaken at OBC needs to be retaken at FBC stage if: • There has been a significant change in the scope of the preferred option, and/or; • Capital costs have increased by more than 5% or revenue costs have increased by more than 10%. • For example, a halving of the BCR, or 20% reduction in benefits would warrant a reappraisal of benefits to ensure that the preferred option is still the best value for money,
Economic | Summary | 2.7.2 | Consistent Preferred Option | Economics | [14 empty] | Confirm the preferred option consistent with the results of the cost, benefits and risk appraisals. | bar: EC
Economic | Summary | 2.7.3 | Unquantified Costs | Economics | [14 empty] | The FBC should set out if there any decisive unquantified costs, non-beneficial areas and / or benefits, and explain any assumptions. | bar: EC
Economic | Summary | 2.7.4 | Place Based Analysis | Economics | [14 empty] | Confirm if distributional and place-based analysis is needed to highlight who benefits. If this has been completed it should be confirmed that this is in accordance with the Green Book. | bar: EC
Economic | Summary | 2.7.5 | Articulated Conclusion | Finance Estates Economics | FI: FI; ES: ES; EC: EC | The FBC should set out a clearly articulated conclusion that draws together the outcomes from the economic appraisal and sensitivity analysis; the unquantified factors; distributional analysis, to demonstrate the choice of preferred option. Where appropriate this conclusion should also reference the 'Levelling Up Agenda' referred to in the latest version of the Green Book.
Economic | Summary | 2.7.6 | Consistency Across Case and Annexes | Design Appraisal Finance Estates Economics | DR DA: DA; FI: FI; ES: ES; EC: EC | Confirm all supporting evidence (e.g. in Annexes) consistent with the results in the main text of the business case. Where annexes are relevant, they must be referenced within the business case.
Economic | Digital |  |  |  | EC: EC; NHP: NHP; DI DI: DI | Digital
Economic | Digital | 2.8.1 | Tax / Subsidy Treatments | Economics Digital | [14 empty] | Set out whether any discovery or preliminary works in relation to digital projects been carried out, and, if so, whether the relevant spend control approvals and conditions been attached to the case. |  |  |  |  | Also check if there’s any possibility of state aid if there is distortion between options. See Green Book | bar: EC; DI DI
Commercial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Commercial | Commercial Feasibility |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Commercial Feasibility
Commercial | Commercial Feasibility | 3.1.1 | Commercial Feasibility Confirmation | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the organisation and relevant project advisers (e.g., lawyers) consider that the proposal is commercially feasible and deliverable. |  |  |  |  | This should be adequately provided or explained.
Commercial | Commercial Feasibility | 3.1.2 | Sufficient Time | Finance Estates Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that the proposal allows sufficient time and resources for the completion of all identified procurement tasks, e.g. completion of necessary procurement documents and supplier negotiations.
Commercial | Commercial Feasibility | 3.1.3 | Tender / GMP Adequate Time | Finance Estates Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Where a tender or target price date has been planned or is being been established, confirm that there is adequate time allowed for the approval process to be completed to allow the contract to be signed. Also, confirm the tender or target price expiry date and confirm if there is scope for it to be extended. Where multiple phases or multiple projects come under this proposal, explain and confirm the arrangements relating to those issues. Also confirm that legal advice has been sought and fully confirms those arrangements.
Commercial | Scope |  |  |  | CL: CL; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Scope
Commercial | Scope | 3.2.1 | Procurement Aims | Clinical Finance Estates Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; DI DI: DI | The business case must clearly describe the subject matter of the procurement. For example, the business case should clearly set out the buildings, land, equipment, technology, goods and/or related service streams to be included in the scheme. |  |  |  |  | The business case should be clear as to the output to be procured, including specification of required outputs and requirements to be met (essential outputs, phases, performance measures, quality attributes. The business areas, stakeholders and customers affected by the procurement should also be set out, along with any future possibilities (potential developments and further phases). The process should be properly classified for the purposes of the procurement rules. It should be clear that the organisation can afford to commission or run the clinical services that are already in the building.
Commercial | Scope | 3.2.2 | Specialist Equipment Procurement | Clinical Finance Estates Digital | CL: CL; FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that the business case includes a strategy for any specialised procurement, e.g. equipment, with a project plan identifying the timeframes and costs. |  |  |  |  | The equipment strategy should set out: • any existing equipment to be transferred; • new equipment being procured in advance of the scheme: and • equipment being procured as part of, or in parallel with the scheme. • specialist equipment The business case must confirm: • which organisation procures the equipment; • which organisation funds the equipment; • which organisation will own, operate and maintain/replace the equipment
Commercial | Procurement Strategy | 3.2.3 | Compliance with Relevant Procurement Laws | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm that the procurement strategy complies with the relevant procurement law. Assurance of compliance with procurement legislation must be provided by legal advisors, confirm that it has been updated at FBC stage as appropriate. |  |  |  |  | For example, all procurement stages must be of at least the minimum duration required by law, which depend on the process followed. The content of any sign off from legal advisors will be assessed. It is unlikely to be an unconditional endorsement. The reviewer will assess the degree of scrutiny that has been applied to the process; if this is considered inadequate, then the legal assessor will comment accordingly.
Commercial | Procurement Strategy | 3.2.4 | Changes to Procurement Strategy | Finance Estates Assurance | FI: FI; ES: ES; ESR: ESR; AS: AS | Confirm that no material changes have been made to the procurement strategy since OBC. If there have been material changes, they must be detailed and adequately justified.
Commercial | Procurement Strategy | 3.2.5 | Changes to Procurement Strategy | Finance Estates Assurance | FI: FI; ES: ES; ESR: ESR; AS: AS | Where very significant material changes are to be made to the procurement strategy or contract terms to those planned at OBC, these must be agreed with NHSE and DHSC before submission of the FBC for approval. |  |  |  |  | If significant late changes are to be made, for example decisions to not use a framework for eventual construction as identified at OBC, the changes should be discussed with NHSE before submission of the FBC to avoid delay in the assurance and approval process and potential abortive work.
Commercial | Procurement Process |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Procurement Process
Commercial | Procurement Process | 3.3.1 | Terms of the Contract, including Price & Risk Transfer | Digital | [14 empty] | The final version of the agreed contract must be provided to the programme commercial team in an unredacted and searchable format. Where a change to an existing contract is proposed e.g. where trusts are merging and looking to have a common digital solution, then copies of the previous contract and CCNs should be provided. The FBC will need to confirm that short-listing of supplier responses were carried out in the appropriate way and in accordance with procurement regulations (ie the Public Contracts Regulations 2015 and subsequent legislation, and the Procurement Act 2023). It is expected that all contracts negotiated will include the appropriate level of cost certainty for an FBC for the Trust and the system. This is required in order to demonstrate that the project remains affordable with regards capital / revenue expenditure. There is a requirement for legal advice to be taken by the provider and submitted with the FBC assessing / confirming i) adherence with the relevent procurement regulations and ii) appropriateness of the proposed terms and conditions for a contract of value / complexity. The Trust will need to comply with the requirements set out in the latest Commercial Checklist | bar: FC; DI DI
Commercial | Procurement Process | 3.3.2 | Price of Contract | Digital | [14 empty] | Under the commercial case it is important that the supplier resources essential for the delivery of the solution into live use and the ongoing delivery of live service as well as the ongoing transition and transformation are factored in. This will include any third party arrangements which may be through the main supplier. Provide a cost breakdown that covers deployment, live ongoing service, exit and transition costs etc. | bar: FC; DI DI
Commercial | Procurement Process | 3.3.3 | Final Contract | Digital | [14 empty] | The contract should reflect an appropriate risk transfer and the strategy set out in the OBC. The FBC should demonstrate that the Trust and the supplier are ready to sign a contract and for the work to commence. In some instances, there may be some additional work on the final terms (other than price) being completed alongside FBC review and approval. In these instances, the Trust can receive approval for their FBC if outstanding terms will not have a material impact, but they will receive an approval condition to ensure that sign off of the final contractual terms takes place prior to contract signature. Copies of key contract schedules should be submitted with the FBC prior to approval. Ensure that there are no dilutions or easements relating to the need for compliance with standards set under the framework or specified at procurement. Clearly describe the mechanism for agreeing CCNs and any dispute resolution Need a compliance statement included that sets out 'any digital technology deployed, must be compliance with all relevant functional and interoperability standards' with more detail of which ones are relevant, which may be referred to in an Appendix. If the compliant EPR frameworks are used, compliance with standards will have been confirmed by suppliers, however if this procurement route is not followed, then applicable standards should be clearly specified. Compliance with the Technology Code of Practice should be stated. The FBC must set out the contract management arrangements during the implementation and live service phases of the programme. This would include Trust monitoring / management of supplier performance against the contracted SLAs / KPIs, and how the Trust will be engaging with the supplier and what the escalation mechanisms are. Set out an exit plan / timeline as part of the overall delivery plan, to avoid long-term vendor lock-in. The compliant EPR frameworks include Exit schedules that should cover related transition arrangements at contract expiry. Trusts need to check that appropriate provisions have been incorporated into the final contract that facilitate timely agreement of an exit plan. The FBC should set out the contingency plan in case of supplier failure and ensure there is a risk included in the risk register related to this. The contract should include terms covering BCDR, noting that the compliant frameworks include contractual schedules relating to this. The FBC should outline the Clinical Risk Management Plan (CRMP) to define how the EPR / System will be implemented. | bar: FC; DI DI
Commercial | Procurement Process | 3.3.4 | Bid Evaluation | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | The FBC should include an assessment of bids from service providers. This should describe each bid and the Best and Final Offers (BAFO), and the basis of the preferred bidder selection. |  |  |  |  | The FBC must demonstrate that the appropriate procurement procedures have been followed.
Commercial | Procurement Process | 3.3.5 | Evaluation Process Summary | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm an adequate summary of the evaluation process and outcome been included. Confirm that it identifies and clearly defines all the pros and cons of each shortlisted bid including the preferred bid. Confirm that the selection of the supplier has been carried out fairly and in accordance with the Public Contracts Regulations 2015 and subsequent legislation. Confirm and provide a clear recommendation for the preferred bidder from the procurement. |  |  |  |  | The FBC must demonstrate that the appropriate procurement procedures have been followed.
Commercial | Procurement Process | 3.3.6 | Higher Cost Supplier | Finance Estates Assurance | FI: FI; ES: ES; AS: AS | Confirm and provide a statement of any additional benefits offered by any higher cost supplier. |  |  |  |  | This is to confirm that the bid with optimal value for money has been selected.
Commercial | Key Contractual Issues |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Key Contractual Issues
Commercial | Key Contractual Issues | 3.4.1 | Commercial Legal Issues Summary | Finance Estates Assurance Digital | FI: FI; ES: ES; AS: AS; DI DI: DI | Confirm there is a summary commentary on all key scheme specific commercial and legal issues and risks retained by the trust. This should include commentary on any proposed amendments to the contract. See also 3.4.1. Legal advice to be taken by the provider and supplied with the FBC in the event that there are any novel and contentious elements or significant risks to the proposed contract. For framework procurements, a legal report will not be required unless there are variations to the standard procurement or contract documentation that are being made. In these instances, it is expected that providers will commission legal advice to test the viability and risks of any variations or additional Z clauses. If the procurement is proposing a standard contract, the FBC should outline any alterations or derogations that have been signed off. The case should indicate what contract will be used, and suitable commentary provided. If the procurement is not using a standard contract, does the case indicate what contract will be used? Suitable commentary should be provided. |  |  |  |  | As appropriate for OBC / FBC stages of business case development.
Commercial | Key Contractual Issues | 3.4.2 | Milestones | Design Appraisal Finance Estates Digital | DR DA: DA; FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that there are clear and realistic contractual key milestones and provide a full project programme showing start and completion dates together with all relevant elements of a full project plan. |  |  |  |  | The following examples of different payment mechanisms may be helpful: • Fixed price • Reimbursement of costs plus agreed margin • Payment on the delivery of agreed outputs. Any available deductions should be clearly described e.g.: • Availability and performance deductions • Liquidated damages for delay Any incentive payments or gainshare arrangements should be clearly described.
Commercial | Key Contractual Issues | 3.4.3 | LADs and Delay Risk | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the risk of delay in completion, including inclusion of liquidated and ascertained damages (LADs) and / or the management of contractor performance, has been addressed.
Commercial | Key Contractual Issues | 3.4.4 | Project Bank Account | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | The case should confirm if use of a project bank account been considered, and whether it has been set up.
Commercial | Key Contractual Issues | 3.4.5 | Payment Mechanism | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that any payment mechanism related to the project or scheme been clearly set out and that it is appropriate. |  |  |  |  | The payment mechanism should be appropriate to the type of scheme. The following examples drawn from PFI-type schemes may be helpful to other types as well. The payment mechanism for the: • pre-delivery phase could be fixed price/costs or payment on the delivery of agreed outputs • operational phase could be availability payment, performance payment, transaction/volume payment, incentive payment, cost of change or third-party revenues • extension phase (if any) could be technological obsolescence or contract currencies.
Commercial | Risk |  |  |  | FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Risk
Commercial | Risk | 3.5.1 | Identified Risk Allocation | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm that the identified risk (see economic case) been appropriately allocated to the party best able to manage the risk between public and Contractor sectors. |  |  |  |  | The business case should include a risk allocation table. The governing principle is that risk should be allocated to the party best able to manage it, subject to relative cost. There should be a sound risk allocation matrix for the preferred option showing how risks are to be apportioned between the Trust and the contractor. Shared risks should be excluded. Ideally, a percentage allocation should be recorded between the categories of public and contractor. If this is not feasible, then a “tick” system can be used at OBC stage. Has account been taken of potential private sector risks, e.g. bankruptcy of service provider?
Commercial | Risk | 3.5.2 | Collateral Warranties | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm use of collateral warranties been considered. Provide the outcome and arrangements put in place.
Commercial | Risk | 3.5.3 | Risk Transfer Mechanism | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | Confirm the mechanism for effecting risk transfer is described and that the risks identified as transferable to the suppliers been reflected in the contract in a way that is enforceable. |  |  |  |  | The type of risk and where it resides will depend on a number of factors including the type of contract employed. The process and achievement of risk transfer must be described and confirmed as having been achieved where applicable.
Commercial | Risk | 3.5.4 | Fraud Risk | Finance Estates Digital | FI: FI; ES: ES; DI DI: DI | SROs and Board to confirm that counter fraud measures focus on clear governance, procedures and responsibilities to counter fraud, including staff training, preventing, detecting, reporting and investigations. There are clear rules and duties of due diligence which must be adhered to when awarding purchasing contracts or other decisions (such as the awarding of grants). For major new areas of spend, an initial assessment of how fraud may occur and the potential impacts this will have should be conducted referencing the Government Fraud Risk Assessment Standard. This must be informed by consultation with relevant counter fraud experts and stakeholders at the earliest point in the business case process. For all proposals, proportionate counter fraud measures should be built into the design as a constraint and therefore as a requirement of all viable options. The Professional standards and guidance for fraud risk assessment in government should be referred to for additional information. SROs are satisfied that sufficient counter fraud measures are in place where funds are paid to a third party. SRO to confirm this in writing to satisfy this requirement. SROs must demonstrate they are aware of fraud risks and how they plan to manage them. Examples could include completing Fraud Risk Assessments and Action Plans. |  |  |  |  | The type of risk and where it resides will depend on a number of factors including the type of contract employed. The process and achievement of risk transfer must be described and confirmed as having been achieved where applicable.
Commercial | Personnel |  |  |  | DR DA: DR DA; ES: ES; ESR: ESR; AS: AS; EC WO: WO; EC NHP: NHP; DI DI: DI | Personnel
Commercial | Personnel | 3.6.1 | Personnel Implications | Workforce | [14 empty] | The FBC should state explicitly whether the scheme has any implications for personnel, including whether there would be expected to be any transfer of staff. The case should confirm if TUPE is to apply and whether the organisation has complied with all provisions and understands any associated costs. |  |  |  |  | TUPE – Transfer of Undertaking, Protection of Employment Regulations 2006 (and as updated since). This protects the employment conditions of public sector staff transferring to the private sector. Also see NHS Standard Contract, Fair Deal for Staff Pensions, Draft Template Schedule 7 and Accompanying Guidance | bar: EC WO
Commercial | Personnel | 3.6.2 | Retention of Employment | Workforce | [14 empty] | Confirm advice was sought where retention of employment (RoE) is proposed and is there confirmation that plans accord with current guidance and requirements on RoE as related to pensions, and that there are plans for consultation in accordance with the law / guidance. |  |  |  |  | TUPE protection does not include pensions, and DHSC developed RoE to cover these. Its use is now specifically restricted to soft facilities management in PFI schemes. If it applies, a copy of the legal advice received must be provided, as well as whether the health organisation’s HR director accepts or disagrees with it and why. | bar: EC WO
Commercial | Personnel | 3.6.3 | Sustainable Development | Design Review Design Appraisal | DR DA: DR DA; ES: ES | Confirm external support, assurance, guidance for Sustainable Development has been sought and used.
Commercial | Net Zero Carbon |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Net Zero Carbon
Commercial | Net Zero Carbon | 3.7.1 | Net Zero Carbon | Digital | [14 empty] | The contract should ensure that the delivery of any requirements and opportunities identified is clearly set out This should entail an assessment in principle against either the Technology Code of Practice sustainability principle assurance checklists or Greener Digital Tooling available on ther Future NHS Workspace: net CO2 impact calculator, low CO2 and climate resilient digital service design. Greener Digital Tooling - https://future.nhs.uk/connect.ti/DigitalNetZero/view?objectId=40994704 |  |  |  |  | For further detail explore the Technology Code of Practice sustainability principle and it's assurance requirements around compliance to the HMG GGC ICT and Digital Services Strategy objectives. Greener Digital Tooling is available on their Future NHS Workspace; net carbon impact calculator, low CO2 digital service design checklist, digital service climate change risk assessment and mitigation planning tool Greener Digital Tooling - https://future.nhs.uk/connect.ti/DigitalNetZero/view?objectId=40994704 | bar: FC; DI DI
Commercial | Sustainability |  |  |  | DR DA: DR DA; ES: ES; ESR: ESR; AS: AS; EC NHP: NHP; DI DI: DI | Sustainability
Commercial | Sustainability | 3.8.1 | Sustainability Considerations | Digital | [14 empty] | The FBC should identify how sustainability considerations were built into the design process, and will be achieved through the scheme. The contract should ensure that the delivery of any requirements and opportunities identified is clearly set out. | bar: DI DI
Financial |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Financial | Overall Affordability |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Overall Affordability
Financial | Overall Affordability | 4.1.1 | Overall Affordability | Finance Digital | [14 empty] | Confirm the financial case includes an overview of: (i) The organisation's financial position (ii) The resources available for the project / programme (iii) Any capital and revenue constraints (iv) Statements in relation to content of Letters of Support from ICBs as strategic commissioners and from the Trust. | bar: FI; DI DI
Financial | Financial Model |  |  |  | FI: FI; AS: AS; NHP: NHP; DI DI: DI | Financial Model
Financial | Financial Model | 4.2.1 | Financial Model | Finance Digital | [14 empty] | (i) Confirm a financial model been developed, with plans to keep it under continuous review and updated. (ii) Confirm the financial model includes the minimum requirements, including • Agreement and recording of underlying assumptions • Funding • Input schedules for costs, cash releasing benefits, risks and contingencies • A reconciliation of demand, capacity, workforce and financial assumptions • Projected financial statements - SOCI, SoFP, Statement of Cashflows (ii) Does the Long Term Financial Model cover an appropriate term (BAU, construction, steady state) | bar: FI; DI DI
Financial | Capital Affordability |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; AS: AS; NHP: NHP; DI DI: DI | Capital Affordability
Financial | Capital Affordability | 4.3.1 | Capital Affordability | Digital | FC: FC; FI: FI; DI DI: DI | The case must demonstrate that the costed proposals are affordable within either operational capital allocations or within national programme funding allocations. Risk, Contingency and Optimism Bias should be appropriately calculated for FBC stage and inflation assumptions clearly stated. The FBC should also include fully costed and completed Cost Forms for all short listed options The capital cost for the preferred option will need to reconcile fully across the fully completed Cost Forms, the Financial Case and the CIA. The case will need to set out the Sources and Applications of capital funding for delivery of this scheme, as well as the proposed profile of expenditure of these capital sources. If operational capital envelopes are used to support the scheme, the Sources and Applications presentation should align with the Letter of Support from the Trust (see above). The FBC should identify and confirm if there are any other sources of funding that could be exercised in the event of cost overrun for the project. The capital costs over the whole contract life including handover and transition should be included, as well as the cost of long-term archiving within the 'System of Record' as per Transformation Directorate guidance. A letter of funding confirmation for Capital and CDEL will be required, from the ICS CEO / CFO. Confirmation of any contingency capital and revenue support will be needed. The Trust will also need to confirm the matched funding as part of securing central funding and any other conditions relating to central funding. Trust must provide written confirmation of local capital and revenue funding sources from DoF, ICB and Region, in line with guidance and as required by the funding programme |  |  |  |  | To support the FCR the case should clearly demonstrate capital affordability. The capital spend profile and values should align with funding agreed and clearly demonstrate CDEL affordability within any funding award/allocation, e.g., national programme PDC funding allocations and/ or within system operational capital allocations as confirmed in the system letter of support. Any national programme funding assumptions in the financial case must be profiled, and the scheme is completed in line with the key dates set by the relevant programme as a condition of funding award. The financial case should include a capital source and application of funds table which demonstrates the profiled CDEL impact of the investment, which correctly takes into account any CDEL credits, i.e. disposals, grants or donations. The case should also correctly take account of any early funding drawn to date and spend incurred The assumptions and the affordability statements in the case should be supported by the system per the letter of support. The financial case should ensure any matched funding requirements (Capital and or revenue) are met and should clearly set out the assumptions made.
Financial | External Funding Sources |  |  |  | FI: FI; NHP: NHP; DI DI: DI | External Funding Sources
Financial | External Funding Sources | 4.4.1 | External Funding | Finance Digital | [14 empty] | Confirm that any elements to be funded from external sources been identified, with the profile of funding / spend by year. | bar: FI; DI DI
Financial | External Funding Sources | 4.4.2 | Borrowing | Finance Digital | [14 empty] | Where borrowing is assumed, the case should set out whether this is anticipated to be DHSC or commercial borrowing, as well as confirming whether the NHS organisation has the ability to borrow. Trusts should refer to the DHSC S42a guidance on financing outside of the DHSC group: https://www.gov.uk/government/publications/guidance-on-financing-available-to-nhs-trusts-and-foundation-trusts/secretary-of-states-guidance-under-section-42a-of-the-national-health-service-act-2006#financing-from-outside-the-dhsc-group The case should set out the value of the expected loan, the assumed term and interest. The repayments and affordability should be assessed and clearly stated. | bar: FI; DI DI
Financial | External Funding Sources | 4.4.3 | Grants and Donations | Finance Digital | FC: FC; FI: FI; DI DI: DI | If grants or donations have been assumed, the case must set out what has been secured and what is the plan to secure the remainder. In general, it is expected that 80% should be secured at FBC, but this will be discussed with NHSE and DHSC on a case by case basis to determine the most appropriate level to be secured based on the risk of those donations and the value of them required to support the scheme. Any conditions attached to donated income or grant funding should be clearly set out.
Financial | Revenue Affordability |  |  |  | FC: FC; FI: FI; WO: WO; NHP: NHP; DI DI: DI | Revenue Affordability
Financial | Revenue Affordability | 4.5.1 | Revenue Affordability | Workforce Digital | FC: FC; FI: FI; WO: WO; DI DI: DI | The FBC should include an incremental Statement of Comprehensive Income, Statement of Cashflows and Statement of Financial Position and Trust-wide Statement of Comprehensive Income including the impact of the proposed investment. The financial statements should demonstrate the revenue impacts of the build and the delivery of future services. The FBC should include detail of CIPs and other initiatives on which affordability depends. Where there is an adverse impact upon the I&E positon (Short term or longer term) this must be explained and the case sets out plans to mitigate these costs pressures and ensure the financial impact is affordable to the Provider and will be managed within the ICS financial envelope. There should be clear alignment and a reconciliation included that details the alignment of the revenue assumptions in the CIA and Financial case (including cash releasing benefits) for the Preferred Way Forward. The activity and growth assumptions in the FBC must also align with the letters of commissioner support. |  |  |  |  | To support the FCR the case should clearly demonstrate revenue affordability. The Trust should provide a working file to support the calculation of the statements. Any revenue funding assumptions should align with approved national programme funding allocations and confirmed in writing. Where additional revenue is assumed from Commissioners / ICB this should be clearly set out in a letter of support. The financial case should ensure any matched funding requirements (Capital and / or Revenue) are met and should clearly set out the assumptions made.
Financial | Revenue Affordability | 4.5.2 | Efficiency Savings | Finance | [14 empty] | Confirm and detail any efficiency savings as a consequence of the scheme based on reasonable assumptions | bar: FI
Financial | Financial Statements |  |  |  | FI: FI; NHP: NHP | Financial Statements
Financial | Financial Statements | 4.6.1 | Accounting Treatment | Finance | [14 empty] | Where assumed accounting treatment is open to interpretation, provide written confirmation from the Director of Finance, the procuring organisation’s external auditor and the organisation’s financial adviser stating that (in their opinion) the assumed treatment is correct. | bar: FI
Financial | Special Purpose Vehicles |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP | Special Purpose Vehicles
Financial | Special Purpose Vehicles / Subsidiaries | 4.7.1 | SPV / Subsidiary | Finance Digital | FI: FI; ES: ES; ESR: ESR | If the organisation is intending to create an SPV, Joint Venture or Subsidiary, or where the proposal includes materially changing a Subsidiary, the business case must follow the approval process described in NHSE guidance - Guidance for assuring and supporting complex change – subsidiaries guidance for trusts forming or changing a subsidiary - before NHS Trusts and Foundation Trusts can implement such plans. This JV needs to be in approved and in place ahead of FBC submission or have a clear plan to secure this in parallel with FBC approval to demonstrate that the vehicle is in place to contract. |  |  |  |  | Additional review requirements for NHS Trusts For all NHS Trust subsidiary proposals, the business case must demonstrate to the Secretary of State that the subsidiary is income generating. We will co-ordinate our review process (if triggered) with that for obtaining Secretary of State consent on a case-by-case basis, considering the inherent risks of each proposal. This includes determining whether we should complete our review before the trust obtains the required consent from Secretary of State. Trusts should inform NHS England of proposals at the earliest opportunity so that we can align the review processes.
Financial | Technical Checks |  |  |  | FC: FC; FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Technical Checks
Financial | Technical Checks | 4.8.1 | Accounting Treatment | Finance Digital | FC: FC; FI: FI; ES: ES; DI DI: DI | If the proposed accounting treatment requires professional judgement, an external audit option should be provided at FBC to confirm the arrangement. This would include for example leases, design and build contracts, managed service/equipment arrangements, Energy Service Performance Contracts (ESPC), use of Special Purpose Vehicles (SPVs). This should include formal VAT advice required to evidence VAT treatment set out in the FBC. |  |  |  |  | This section should provide details of the intended accountancy treatment for the potential deal and confirm on whose Statement of Financial Position, formerly known as the balance sheet (public, private or both sectors), the assets underpinning the deal will sit. Where the scheme is novel, contentious or repercussive, or the accounting treatment is unclear, the organisation should obtain written agreement from its external auditors on the proposed accounting treatment.
Financial | Technical Checks | 4.8.2 | Revenue / Capital Split | Finance Digital | [14 empty] | Confirm the split of costs between revenue and capital in-line with the current capitalisation policy. | bar: FI; DI DI
Financial | Technical Checks | 4.8.3 | Ownership of Capital Assets | Finance Digital | [14 empty] | Where the Business Case includes the purchase or creation of capital assets is it clear which organisation will own the assets and whose asset register they will sit on | bar: FI; DI DI
Financial | Technical Checks | 4.8.4 | Recharges | Finance Digital | [14 empty] | The FBC should set out any re-charges to other organisations that result from this scheme, with the recovery of costs or income generated factored into the case. | bar: FI; DI DI
Financial | Technical Checks | 4.8.5 | Procurement Costs | Finance Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm the procurement costs have been clearly set out, including the basis for internal costs of the project team and the costs of advisers and technical support
Financial | Technical Checks | 4.8.6 | Leases | Finance Digital | FI: FI; ES: ES; DI DI: DI | Where leases are being entered into, confirm these have been correctly accounted for as finance or operating leases in accordance with the applicable accounting standards.
Financial | Technical Checks | 4.8.7 | Contract / Staff Costs Split | Finance Digital | [14 empty] | Confirm all contract resources have been split out from staff costs and shown as separate line items with correct treatment of VAT | bar: FI; DI DI
Financial | Technical Checks | 4.8.8 | Stamp Duty | Finance Digital | [14 empty] | Confirm the treatment of Stamp Duty, Corporation Tax or any other taxes compliant with relevant legislation | bar: FI; DI DI
Financial | Technical Checks | 4.8.9 | Indexation | Finance Digital | [14 empty] | Confirm the indexation assumption accurate and appropriate | bar: FI; DI DI
Financial | Technical Checks | 4.8.10 | Financial Analysis | Finance Digital | [14 empty] | Confirm the financial analysis has been updated to take account of any changes in costs, and to show the effect of the proposed contractual payments | bar: FI; DI DI
Financial | Contingencies |  |  |  | FI: FI; ES: ES; ESR: ESR; NHP: NHP; DI DI: DI | Contingencies
Financial | Contingencies | 4.9.1 | Contingencies / Other Funding Sources | Finance Digital | [14 empty] | The FBC should identify and confirm if there are any other sources of funding that could be exercised in the event of cost overrun for the project. | bar: FI; DI DI
Financial | Contingencies | 4.9.2 | Contingency Plans | Finance Digital | FI: FI; ES: ES; DI DI: DI | Confirm contingency plans are described, e.g. for alternative sources of funding, if assumptions turn out to be wrong or insufficient. The FBC should set out any flexibility to fund any additional revenue requirements or to absorb any affordability gaps that emerge. If so, the FBC should confirm complaince to HMT guidance on contingent liabilities as described within Managing Public Money.
Financial | Contingencies | 4.9.3 | Financial Appraisal | Finance Digital | [14 empty] | Confirm the assumptions underlying the financial appraisal (including cost of risk mitigation) have been analysed for their robustness. | bar: FI; DI DI
Financial | Contingencies | 4.9.4 | Sensitivity Analysis | Finance Digital | [14 empty] | Confirm that a sensitivity analysis has been carried out on the relevant variables in the affordability analysis | bar: FI; DI DI
Financial | Contingencies | 4.9.5 | Optimism Bias | Finance Digital | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Confirm that optimism bias set at the correct level, in accordance with the HMT Green Book. It is expected that optimism bias will reduce as a scheme progresses through SOC to FBC and greater certainty over costs is ascertained. Optimism Bias should be reduced as close to zero as is appropriate by FBC submission.
Financial | Costs |  |  |  | FI: FI; ES: ES; ESR: ESR; DI DI: DI | Costs
Financial | Costs | 4.10.1 | Costed Equipment Schedule | Finance Digital | FI: FI; ES: ES; ESR: ESR | Confirm that a costed equipment schedule been provided |  |  |  |  | Information must be consistent with costs provided in the business case and Cost (OB) Forms
Financial | Costs | 4.10.2 | Cost of Implementation | Finance Digital | [14 empty] | The FBC will need to include the full costs of implementation and Business as Usual (BAU) within the analysis, over an appropriate timescale. | bar: FI; DI DI
Management |  |  |  |  | FC | CO | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO | WO | NHP | DI
Management | Workshop | 5.1.1 | Workshop 1 Green Book | Assurance | [14 empty] | Workshop 5 completed: Determining the delivery arrangements. Green Book and associated guidance documents. Mandated workshop requirement. |  |  |  |  | Green Book and associated guidance documents. Mandated workshop requirement | bar: FI AS
Management | Other | 5.1.2 | All Documents and Appendices Complete and Included | Assurance | [14 empty] | Confirm all relevant documents and appendices been completed, checked, signed off, listed in the business case and confirmed to be submitted with the Business Case when it is submitted for the review and approval process. Missing documents may cause delay or rejection in relation to the approval process. | bar: FI AS
Management | Project Plan |  |  |  | FC |  | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO |  | NHP | DI | Project Plan
Management | Project Plan | 5.2.1 | Project Plan | Digital | FC | [12 empty] | DI | The FBC should set out the project plan, including the key delivery milestones and activities. This plan should be realistic, outline resources required for activities and any need for specific capabilities and competencies required to manage the design, build and operational phases of the scheme, and include sufficient time for business case review and approval, procurement and negotiation, and construction of the facility, as well as ensuring there is sufficient time allowed for all approvals (NHSE + DHSC, HMT, CO, BSA, etc). Use of any specialist advisers should be detailed. The FBC should also set out the delivery methodologies to be used (e.g. Agile, Waterfall, mix) and outline the resource and contingency plans. Dependencies (e.g. regulatory approvals, linked projects, funding stages )should be identified and mapped accordingly (e.g. in the RAID log and or within the Project Gantt chart). Any key assumptions should also be detailed.
Management | Project Plan | 5.2.2 | Workstream Interdependencies | Design Review Assurance |  |  | DR DA: DR; ESR: ESR; AS AS: AS |  |  |  | The case should confirm other work stream milestones and their interdependencies with the proposal. |  |  |  |  | Other work streams may include workforce, equipment, training, benefits delivery Clear delivery dates and detailed milestones should be provided.
Management | Project Management |  |  |  | FC |  | DR DA | CL | FI | ES | ESR | AS | ST | EC | PO |  | NHP | DI | Project Management
Management | Project Management | 5.3.1 | Project Management | Digital | FC | [12 empty] | DI | The Case should identify the SRO for the project and have identified specific resource to make up a project team. The structure of the programme team and governance arrangements should be identified; this should ensure that assigned roles and responsibilities are assigned (e.g. SRO, Project Board, Delivery team) and that reporting lines and escalation processes are clearly outlined, including Terms of reference. The experience of the SRO and programme team in delivering major schemes should be clearly set out to demonstrate the capacity and capability of the team to deliver the project, as well as the budget and resources required to deliver the project to completion. The Trust should provide an Integrated Assurance and Approvals Plan (IAAP) as part of the FBC. The Trust should identify any actual or potential gaps in resource and capacity that the Trust will need to mitigate to successfully deliver the scheme. External advisors’ capacity and capability (e.g. NEC Project manager, NEC supervisor, Cost advisor, Legal) should be clearly stated - as part of the overall project management structure - to ensure the effective delivery of the scheme. | bar: DR FI
Management | Project Management | 5.3.2 | Project Management Budget | Finance Assurance Strategy Economics |  |  |  |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | A breakdown of the budget should be provided. The budget should incorporate appropriate contingencies (and provide a rationale for these), and be consistent with the financial case.
Management | Project Management | 5.3.3 | Executive Support and Sign Off | Design Review Design Appraisal Finance Assurance Strategy Economics |  |  | DR DA |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | The FBC should set out the project structure to provide assurance that the project has sufficient backing by, and commitment from senior executives and user groups to underpin a successful project.
Management | Project Management | 5.3.4 | Project Management Methodology | Finance Assurance Strategy Economics |  |  |  |  | FI | ES | ESR | AS | ST | EC |  |  |  |  | Confirm that the project management methodology been defined |  |  |  |  | The recommended project methodology is PRINCE 2 - Projects IN Controlled Environments, which is the de facto standard in use within the public sector in the UK.
Management | Project Management | 5.3.5 | Skilled Resource | Assurance | [14 empty] | Confirm there is sufficient and adequately skilled resource available to successfully manage the procurement, implementation and operational stages. |  |  |  |  | The skills set of the team and any skills gaps are identified. Plans are set out on how skill gaps are to be filled, including any plans to use advisers. Who will be responsible for contract management? How does their work fit into the overall project management structure? The role of advisers is set out, including the terms on which they have been appointed, confirmation of the breadth of their appointment, and arrangements to manage their fees; | bar: AS AS
Management | Project Management | 5.3.6 | Better Business Case Training | Assurance | [13 empty] | DI | Confirm that the Business Case Development Lead (ie Project Manager), Finance Lead and Estates Lead (for estates schemes)within the project team completed the mandatory Better Business Case training now required when working on NHS capital schemes and projects. | bar: AS AS
Management | Project Management | 5.3.7 | Management Arrangements for Procurement Process | Assurance | [14 empty] | Confirm that adequate management arrangements been put in place to manage the bids, preferred bidder appointment and contract | bar: AS AS
Management | Project Management | 5.3.8 | Adequate Management Arrangements for External Engagement | Design Review Design Appraisal Assurance |  |  | DR DR DA: DR DR; AS AS: AS |  |  |  | Describe how executive clinical leaders, frontline clinical and non-clinical staff, and other stakeholders have been involved in shaping and influencing proposals, including eliciting and acting on patient feedback. Has the organisation met its duties under s242 of the NHS Act 2006 to involve and where necessary carry out a full public consultation with patients, the public and other stakeholders? The outcome of this involvement has been considered and where appropriate has informed the business case Describe the interface with community partners and development/understanding of patient pathways.
Management | Project Governance Reporting and Monitoring | [16 empty] | DI | Project Reporting and Monitoring | bar: DR DR DA to AS PO
Management | Project Governance Reporting and Monitoring | 5.4.1 | Reporting Structures | Assurance Digital | [13 empty] | DI | Confirm the reporting structure and monitoring arrangements have been set out. |  |  |  |  | This should identify who is involved in reporting and monitoring, when and how this takes place and the anticipated cost. | bar: AS AS
Management | Project Governance Reporting and Monitoring | 5.4.2 | Project Board | Assurance Digital | [13 empty] | DI | Confirm the plan include full details of the membership and terms of reference of the project board and sub-groups in the project management structure. |  |  |  |  | The case should include an organogram or other representation of the project structure and governance (including links to the organisation’s Board). | bar: AS AS
Management | Project Governance Reporting and Monitoring | 5.4.3 | Routes of Escalation | Assurance Digital | [13 empty] | DI | Confirm the governance structure that is operating in support of scheme development and delivery and the routes of escalation across that structure to resolve issues. This should include the authority and delegated limits for decision making roles. | bar: AS AS
Management | Benefits Management |  |  |  | FC |  | DR FI: FI; DR ES: ES; AS AS: AS; AS EC: EC |  |  | DI | Benefits Management
Management | Benefits Management | 5.5.1 | Benefits / Risk Management | Estates Assurance Economics Digital | FC |  | DR ES: ES; AS AS: AS; AS EC: EC |  |  | DI | The FBC needs to set out the benefits realisation and risk mitigation plans for the project and explain what has been agreed and finalised for the successful delivery of the project in accordance with best practice. The strategy for the management of benefits and risks during the key phases of the project should be affirmed in the FBC, with accompanying Benefit and Risk Registers provided for central oversight. Detailed benefit realisation plans should be provided particularly for any Cash-Releasing benefits that support affordability. There needs to be clarity on the governance for delivery and realisation of benefits, any benefits workstreams that are established, the roles and responsibilities for delivering benefits with confirmed Benefits Leads and reporting requirements.
Management | Benefits Management | 5.5.2 | Benefits Realisation | Finance Assurance Economics |  |  | DR FI: FI; AS AS: AS; AS EC: EC |  |  |  | Confirm that there is a benefits realisation table and plan. |  |  |  |  | At OBC stage the benefits strategy should be outlined. At FBC stage a detailed plan should be included. These should cover all benefits, CRB and non-CRB, and should reconcile with the economic benefits identified and valued in the economic case. The benefits should be quantified and measurable. There should be a clear plan to ensure monitoring and evaluation of the quantified benefits. This needs to include a time frame, accountable owner and ensure that the criteria for measurement have been identified.
Management | Benefits Management | 5.5.3 | Benefit Owners | Finance Assurance Economics |  |  | DR FI: FI; AS AS: AS; AS EC: EC |  |  |  | Ensure it is clear what benefits are to be realised by whom, e.g. suppliers, stakeholders etc. There should be confirmed strategic and operational benefit owners in place. |  |  |  |  | Responsibility for monitoring and achieving benefits delivery should be assigned to named post holders. How will delivery of benefits by suppliers be monitored?
Management | Benefits Management | 5.5.4 | Separation of CRB and Non-CRB Benefit Maangement | Finance Assurance Economics |  |  | DR FI: FI; AS AS: AS; AS EC: EC |  |  |  | Confirm that the detailed benefits realisation plan separates CRB from non-CRB, and identifies how qualitative benefits are to be measured. |  |  |  |  | The case should demonstrate how cash is to be released and efficiencies achieved and should identify which budgets will be impacted.
Management | Change Management |  |  |  | FC |  | DR DA | CL | FI | ES |  | AS | ST | EC | PO | WO |  | DI | Change Management
Management | Change Management | 5.6.1 | Contract Management | Digital | FC | [12 empty] | DI | The FBC needs to record the contract management arrangements and plans that have been agreed and finalised for the successful management of the service in accordance with best practice. This should include both the formal and informal arrangements that have been put in place for the strategic and operational management of the contract, as well as detailing the experience and capability of those involved in the ongoing contract management.
Management | Change Management | 5.6.2 | Impact of Preferred Option Considered | Design Review Design Appraisal Workforce |  |  | DR DR DA: DR DA; DR ES: ES; AS AS: AS | WO |  |  | Confirm that the organisational and cultural impact of the preferred option has been considered / described. Confirm the necessary measures been put in place to manage the organisational and cultural changes arising from the impact of the scheme. |  |  |  |  | For example, the identified impact of deployment should be consistent with wider organisational strategies e.g. human resources, estates or clinical services.
Management | Change Management | 5.6.3 | Change Management Plan | Assurance Workforce | [11 empty] | WO |  |  | Confirm there is a detailed, resourced and robust change management plan which also shows interdependencies. The FBC should detail all resource required for this. |  |  |  |  | The change management plan should include a transition plan and details of any necessary training programmes. | bar: AS AS
Management | Change Management | 5.6.4 | User Support Proposals | Assurance | [14 empty] | Confirm the business case demonstrates that users fully support the project and are committed to it. Confirm the business case includes detailed plans for user involvement in the planning and implementation of the project. | bar: AS AS
Management | Risk Management |  |  |  | FC |  | DR CL: CL; DR FI: FI; DR ES: ES; AS AS: AS |  |  | DI | Risk Management
Management | Risk Management | 5.7.1 | Risk Register | Assurance Digital | FC |  | DR ES: ES; ESR ESR: ESR; AS AS: AS |  |  | DI | The FBC should affirm the strategy and plan for the management of risks, especially monitoring and escalation, during the key phases of the project, with an accompanying costed risk register capturing all risks with ratings and showing clear owners for the management and mitigaton of each risk. Updated information should be provided about the nature of the risks, their timing and their potential service and financial impact. The Risk Management plan should be comprehensive and detailed and cover all identified risks and major risks should be addressed within contingency plans. Specific Risks and Mitigations to be discussed within the case include: - Clinical Risk Management Compliance (DCB 0160) - Trust must explicitly demonstrate supplier compliance with DCB 0129 and confirm they will be sent Clinical Safety Case Report and Hazard Log on contract completion. - Incorporate Evidence of Usability Testing - Risk Assessments for Clinical and Digital Transformation - including a plan for how and when a clinical risk assessment for any technology or service will be undertaken. - Interoperability Standards - requiring a p;lan for how integrations and interoperability standards will be addressed. - Evidence of Data Protection and IG Compliance
Management | Risk Management | 5.7.2 | Risk Management / Orange Book | Assurance Digital |  |  | DR CL: CL; DR FI: FI; DR ES: ES; ESR ESR: ESR |  |  |  | The FBC should confirm compliance with the HMT Orange Book, specifically regarding Risk Management, application of the Risk Management Framework and Risk Assurances Processes.
Management | Risk Management | 5.7.3 | Nature of Risks | Clinical Digital Finance |  |  | DR CL: CL; DR FI: FI; DR ES: ES; ESR ESR: ESR |  |  |  | The case should provide updated information about the nature of the risks, their timing and their potential service and financial impact, with a detailed risk management strategy that comprehensively covers all identified risks.
Management | Other | [14 empty] | WO |  |  | Other | bar: DR DR DA to AS PO
Management | Other | 5.8.1 | Business Continuity | Assurance Workforce | [11 empty] | WO |  |  | Describe arrangements for business continuity during the build period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. |  |  |  |  | Describe arrangements for business continuity during the build period, e.g. access for staff, patients and the public takes account of the major incident policy and emergency planning. | bar: AS AS
Management | Assurance |  |  |  | FC |  | DR DA | CL | FI | ES | ESR | AS |  |  |  |  | NHP | DI | Assurance
Management | Project Plan | 5.9.1 | Gateway Reviews | Assurance | [14 empty] | The FBC should confirm the outcomes of previous Gateway review process, and acknowledge all actions taken to comply with the recommendations and / or requirements of the review. | bar: AS AS
Management | Assurance | 5.9.2 | Post Project Evaluation | Design Review Clinical Finance Assurance Digital | FC |  | DR DR DA: DR; DR CL: CL; DR FI: FI; DR ES: ES; AS AS: AS |  |  | DI | The FBC should record: - The arrangements for future Gateway Reviews and organisational Health Checks (if applicable). - The arrangements for post project evaluation. These reviews may be undertaken separately or in conjunction with Gateway Review 5 (operational review and benefits realisation). The Project Implementation Review (PIR) should be undertaken as soon as possible after the implementation of the service to capture lessons learnt. The Post-Evaluation Review (PER) for reviewing how well the service is running and delivering its anticipated benefits should typically take place within 6 to 12 months after the commencement of service, and thereafter as required by the benefits delivery plan.
Management | Project Plan | 5.9.3 | Post-Implementation and PPE | Design Appraisal Clinical Finance Assurance Strategy Economics |  |  | DA | CL | FI | ES | ESR | AS | ST | EC |  |  |  |  | PPE is an important element of any scheme to ensure lessons are learned and improvements made across all aspects of Capital Projects. The trust is to confirm that PPE lessons from previous schemes have been implemented in this scheme and that records are being maintained to enable a full and complete PPE to be prepared and completed for this project. It should also be noted that NHSE have a mandatory requirement that detailed project outturn costs are provided promptly as part of the PPE process. Annex 2 of the Capital Guidance includes post-project evaluation templates that can be utilised by Trusts in undertaking this exercise: https://www.england.nhs.uk/wp-content/uploads/2023/02/B1376iii-annex-2-post-project-evaluation-templates.pdf
Management | Digital | [14 empty] | WO |  | DI | Digital
Management | Digital | 5.10.1 | Training | Workforce Digital | [11 empty] | WO |  | DI | Detail the outline training programme for all relevant staff, both users and project team members. |  |  |  |  | Detail should be provided about whether the organisation has a training infrastructure already, how will training be developed, and who will develop it.
Management | Digital | 5.10.2 | Training Programme | Workforce Digital | [11 empty] | WO |  | DI | The FBC should include a detailed, costed and resourced training programme, covering the training requirements of all relevant staff, both users and project team members. |  |  |  |  | Detail should be provided about how training is being developed and delivered, and by whom.
Management | Digital | 5.10.3 | Delivery Plan | Digital | [13 empty] | DI | The FBC should include a detailed delivery plan that incorporates the full implementation and transition into live running / BAU.
Management | Digital | 5.10.4 | Delivery Plan | Digital | [13 empty] | DI | The case should document the evidence that security and confidentiality have been addressed in accordance with information governance principles.

## 2. BC Appendices Guide
5. Checklist of typical Documents and Appendices commonly provided with a business case and at what stage. For guidance only. Document names in cases should reflect the naming conventions below. This list is NOT exhaustive, nor will all shown apply to all cases. Also see: Tab 3 Mandatory Estates Documents
2024-04-03
Appendix Number | SOC | OBC | FBC | Title or general content. The actual appendices register for the scheme or project (Tab 4) should state the precise full title of each appendix as provided and used within the business case.
Fully titled and named Business Case | ✓ | ✓ | ✓ | Main Business Case Document. Requires clear version control including date of sign-off by SRO, Board and Stakeholders.
Appendix 1 | ✓ | ✓ | ✓ | Mandatory Business Case Checklist and mandatory worksheets within it are to be fully completed and provided with the business case at Fundamental Criteria review stage.
|  | ✓ | ✓ | Benefits Register (SoPB) / Realisation Plan
|  | ✓ |  | Change Management Strategy
|  |  | ✓ | Change Management Plan
| ✓ | ✓ | ✓ | CIA model
|  | ✓ | ✓ | Clinical Governance Diagram
|  | ✓ | ✓ | Clinical Resource Plan
| ✓ | ✓ | ✓ | Costed schedule of project risk
|  | ✓ | ✓ | CQC Report (latest provided)
| ✓ | ✓ | ✓ | Data Migration Plan
| ✓ | ✓ | ✓ | Data Protection Impact Assessment (DPIA)
|  |  | ✓ | Details of Bid Evaluation and Selection of Contractor
|  | ✓ | ✓ | DHSC Digital &Technology Question Set
|  | ✓ | ✓ | Digital Clinical Risk Management System (Digital CRMS)
|  | ✓ |  | Engagement and Communications Strategy
|  |  | ✓ | Engagement and Communications Plan
|  | ✓ | ✓ | Equality and Diversity Impact Assessment
| ✓ | ✓ | ✓ | Evidence of Business Case Approval by Trust Board
| ✓ | ✓ | ✓ | Financial Modelling and Statements
| ✓ | ✓ | ✓ | Financial Reconciliation across Financial and Economic Cases, with Supporting Calculations and Tables for Economic and Finance Cases
| ✓ | ✓ | ✓ | ICS Green Plan
|  | ✓ | ✓ | ICS Digital Clinical Safety Strategy
|  | ✓ | ✓ | ICS Digital Strategy
|  | ✓ | ✓ | ICS Letter of Support
|  | ✓ | ✓ | Integrated Care Addendum
|  | ✓ |  | Invitation to Tender Documentation
|  | ✓ | ✓ | Legal overview of the procurement process
|  | ✓ | ✓ | Lessons Learned Log
| ✓ | ✓ | ✓ | Letter from CFO
| ✓ | ✓ | ✓ | Letters of Support from their ICS and all major commissioning bodies
| ✓ | ✓ | ✓ | Management Control Plan
| ✓ | ✓ | ✓ | Net Zero Carbon documentation. See NHSE 'NHS Net Zero Building Standard' for requirements.
|  | ✓ | ✓ | Output Based Specification
|  | ✓ | ✓ | Procurement report
| ✓ | ✓ | ✓ | Project Programme Plan
|  | ✓ | ✓ | Resource Plan for Implementation
|  | ✓ | ✓ | Risk Strategy / Management Plan
| ✓ | ✓ | ✓ | Risk Register
| ✓ | ✓ | ✓ | Social Value Model
| ✓ | ✓ | ✓ | Stakeholder engagement meeting arrangements and outcomes
|  | ✓ | ✓ | Statement of Planned Benefits - https://future.nhs.uk/NHSDigitalQualityImprovement/view?objectID=184577509
| ✓ | ✓ | ✓ | Timelines, Cost Indexation and Request for Additional Funding
|  | ✓ |  | Training Strategy
|  | ✓ | ✓ | Training Plan
| ✓ | ✓ | ✓ | Trust Clinical Services Strategy
| ✓ | ✓ | ✓ | Trust Digital Strategy
| ✓ | ✓ | ✓ | Trust Workforce Strategy
| ✓ | ✓ | ✓ | Workforce modelling

## 3. Glossary BC Acronyms
6. Glossary of general business case and project related acronyms and words
2024-04-03
Acronym / Word | Explanation of business case related acronyms
AEDET | Achieving Excellence Design Evaluation Toolkit (largely superseded by DQI)
ASPECT | A Staff and Patient Environment Calibration Toolkit (largely superseded by DQI)
BAFO | Best and Final Offer
BAU | Business As Usual
BBC | Better Business Cases. Business Cases accreditation and training programme.
BC | Business Case
BCIS | Building Cost Information Service
BIM | Building Information Modelling
BLM | Backlog Maintenance
BREEAM | BRE Environment Assessment Method (BRE is the trading name of Building Research Establishment Limited)
CCG | Clinical Commissioning Group
CDEL | Capital Departmental Expenditure Limits
CEO | Chief Executive Officer
CFO | Chief Financial Officer
CIA | Capital Investment Appraisal (Model – replaces GEM). Used to appraise vfm in build business cases
CIM | Capital Investment Manual. Dating from 1994. Generally archived but still referenced on occasion. Some elements of which, such as cost forms are still applicable, although a revised version of those and parts of CIM itself will shortly be available (ongoing).
CIP | Cost Improvement Programme
CMS | Common Minimum Standards (for Construction)
Cost Forms | Standard NHS forms for entry of construction and related cost information mandated for use on all construction related business cases. There are two main versions - OB used for OBC and FB used for FBC. Shortly to be updated (2024). Also sometimes called OB / FB Forms.
CRB | Cash Releasing Benefit
CRC | Carbon Reduction Commitment
Devolution | In essence, place-based commissioning and joined-up care pathways
Derogation | In design terms - a proposal to lessen, weaken or ignore a set standard of performance or move away from otherwise acceptable standards
DHSC | Department of Health and Social Care
Digital | In the context of this BC process, Digital refers to business cases prepared for Digital investment as this is now part of the NHSE&I portfolio of responsibilities.
Discount Rate | The rate set by HM Treasury at which costs in the economic case must be discounted (currently 3.5%).
DMBC | Decision Making Business Case
DQI | Design Quality Indicator
DV | District Valuer
e-PIMS | Electronic Property Information Mapping Service (the central database of Government Central Civil Estate)
E&F | Estates and Facilities
EAC | Equivalent Annual Cost
EPR | Electronic Patient Record
ERIC | Estates Return Information Collection
EU | European Union
FBC | Full Business Case
FBC (D) | Full Business Case (Digital). 'D' is purely used to identify and facilitate selection of Digital BC items in the business case worksheet.
FC | Fundamental Criteria (part of the initial triage performed jointly by NHSE and DHSC prior to accepting a business case for review and any possible approval decision
GDE | Global Digital Exemplar
GEM | Generic Economic Model (being replaced by the CIA)
GIA | Gross Internal Area
GMP | Guaranteed Maximum Price
Green Book | The Green Book is guidance issued by HM Treasury on how to appraise policies, programmes and projects in the public sector and is the process followed for NHS projects and capital investment. There are also a series of supporting documents relating to the Green Book that should be used with it. These documents are all available on the .gov.uk website.
GSL | Government Soft Landings
HBN | Health Building Note
HMG | His Majesty's Government
HMT | His Majesty's Treasury
HOSC | Health Overview and Scrutiny Committee
HPCG | Healthcare Premises Cost Guide
HSFF | Health Service Systems Framework
HTM | Health Technical Memorandum
I/E | Income/expenditure (accounting)
ICB | Integrated Care Board
ICS | Integrated Care System
ICT | Information and Communication Technology (Digital Technology)
IM&T | Information Management and Technology
IPA | Infrastructure and Projects Authority
ITPD | Invitation To Participate in Dialogue (procurement stage)
IT | Information Technology
ITT | Invitation To Tender (procurement stage)
JIC | Joint Investment Committee
JISC | Joint Investment Sub Committee
JV | Joint Venture
KLOE | Key Lines of Enquiry
KPI | Key Performance Indicator
LAD | Liquidated and Ascertained Damages
LIFT | Local Infrastructure Finance Trust (delivers infrastructure in NHS primary care and is sometimes referred to as Local Improvement Finance Trust)
LPA | Lease Plus Agreement (used in LIFTs)
LPP | London Procurement Partnership
LPP CDISF | London Procurement Partnership Clinical Digital Information Systems Framework
LRA | Land Retained Agreement (used in LIFTS)
LTFM | Long Term Financial Model
LTP | Long Term Plan
m2 NIA | Square Metres Net Internal Area
M&V | Measurement and Verification
MIPS | Median Index of Public Sector Tender Prices. (Now superseded by Pubsec)
MMC | Modern Methods of Construction
MSCP | Multi Storey Car Park
M&V | Measurement and Verification (process)
MVP | Minimum Viable Product (used in IM&T to indicate minimum necessary service)
NCAT | National Capital Assurance Team (DHSC Investment Appraisals, NHSEI Capital and Cash and NHSEI Estates)
NCRB | Non-Cash Releasing Benefit
NHP | New Hospital Programme
NHS E | NHS England
NICE | National Institute for Health and Care Excellence
NPC | Net Present Cost
NPSC | Net Present Social Cost
NPV | Net Present Value (Mandatory targets are to be achieved for all NHS and public buildings).
NPSV | Net Present Social Value
NZC | Net Zero Carbon
OGC | Office Government and Commerce (the organisation that developed Gateway – OGC is no longer in existence)
OB | Optimism Bias
OB/FB Forms | An term sometimes used to describe Cost Forms (see above). Standard NHS forms for entry of construction and related cost information mandated for use on all construction related business cases. There are two main versions - OB used for OBC and FB used for FBC. Shortly to be updated (early 2023).
OBC | Outline Business Case
OBC (D) | Outline Business Case (Digital) 'D' is purely used to identify and facilitate selection of Digital BC items in the business case worksheet.
OGC | The now closed Office of Government Commerce. Often still used in relation to OGC Gateway [reviews] from Infrastructure and Projects Authority Assurance reviews process.
OJEC | Official Journal of the European Community (outdated usage. Now OJEU). Due to be replaced in UK law in due course.
OJEU | Official Journal of the European Union (covering EU procurment laws)
P21+, P22 & ProCure | ProCure 21 Plus, replaced by P22, are NHS procurement frameworks for construction originally developed by DHSC but taken over by NHS England. Also known as P21+ and P22. Unless contracts have been signed, these are now fully superceded by P23.
P23 & ProCure | The framework for the NHS that has now replaced P21+ and P22
P23 DAT | Procure 23 Design Assurance Tool
PAM | Premises Assurance Model (updated in 2016)
PAU | Project Appraisal Unit (NHS England) - Now replaced by NHSE regional and national appraisal teams
PBC | Programme Business Case
PCBC | Pre-Consultation Business Case
PCR | Post Completion Report
PDC | Public Dividend Capital
PFI / PF2 | Private Finance Initiative and the successor approach, Private Finance 2. The government has announced that it will no longer use PF2, the current model of Private Finance Initiative (PFI) for new government projects. Existing PFI and PF2 contracts will not end because of this announcement.
PFU | Private Finance Unit (replaced by The Procurement, Investment and Commercial Division (PICD) of the Department of Health)
PICD | The Procurement, Investment and Commercial Division of DHSC (see PFU)
PID | Project Initiation Document
PLACE | Patient-Led Assessments of the Care Environment
PMO | Project Management Office
POE | Post Occupancy Evaluation
PPE | Post Project Evaluation on Capital projects (also an acronym used for Personal Protective Equipment)
PPP | Public Private Partnership (replaces PFI)
PQQ | Pre-Qualification Questionnaire
PUBSEC | Tender Price Index of Public Sector Building Non-Housing
QIPP | Quality, Innovation, Productivity and Prevention (NHS quality and efficiency programme)
QALY | Quality Adjusted Life Year
RDD | Regional Delivery Director (NHSE)
RIBA | Royal Institute of British Architects
RoE | Retention of Employment (an NHS and PFI-specific addition to TUPE)
RPA | Risk Potential Assessment
s106 | Section 106 of the Town and Country Planning Act 1990 (as amended), dealing with planning permission & related conditions
s278 | Section 278 of the Highways Act 1980, by which a builder may be required to make highway improvements
SABRE | Security Assurance BRE (BRE is the trading name of Building Research Establishment Limited)
SBS | NHS Shared Business Services
SEP | Strategic Estates Partnership or Strategic Estates Plan(ning)
SFBC | Short Form Business Case
SHAPE | Strategic Health Asset Planning and Evaluation (NHS/DHSC national mapping system)
SME | Small and Medium sized Enterprises/Businesses
SMT | Senior Management Team
SOC | Strategic Outline Case
SOC (D) | Strategic Business Case (Digital) 'D' is purely used to identify and facilitate selection of Digital BC items in the business case worksheet.
SoCI | Statement of Comprehensive Income
SoFP | Statement of Financial Position
SPV | Special Purpose Vehicle (a separate legal entity, usually a limited company or a limited partnership to achieve specific aims, usually around property issues).
SRO | Senior Responsible Officer
STA | Single Tender Action
STP | Sustainability Transformation Plan
Subsidiaries | Wholly owned subsidiaries are an organisational and governance form that NHS providers can legally adopt to manage part of their organisation.
SVM or SV | Social Value Model or Social Value
SWOT | Strengths, Weaknesses, Opportunities, Threats analysis
TDA | Trust Development Authority (became NHS Improvement, now merged with NHS England).
TTF | Treasury Task Force (guidance on PFI/PPP)
TUPE | Transfer of Undertaking, Protection of Employment Regulations
UTF | Unified Tech Fund (digital)
VAT | Value Added Tax
VfM | Value for Money
VOA | Valuation Office Agency
WTE | Whole Time Equivalent (Workforce numbers)