## 1.Direct Award Process B Guide
Introduction
This guide is designed to help relevant authorities with their decision-making under the Provider Selection Regime (PSR), when following direct award process B. A relevant authority must follow direct award process B when the proposed contracting arrangements relate to health care services where patients have a choice of providers, the number of providers is not restricted by the relevant authority, and the relevant authority will offer contracts to all providers to whom an award can be made. This guide is also designed to assist relevant authorities with being able to comply with the transparency and record keeping requirements as set out in the Health Care Services (Provider Selection Regime) Regulations 2023 (the ‘Regulations’) and in the accompanying statutory guidance. It is the responsibility of each relevant authority to satisfy themselves that they are complying with the requirements of the Regulations and the guidance. This guide is intended to be a complimentary "Toolkit product" to help relevant authorities understand the requirements of the new legislation in a structured way. It is not compulsory to use this toolkit in order to fulfil the requirements of the PSR.
Tab: 2. direct award process B - process map
This tool maps out the end to end process for direct award process B. This process is mapped out linearly, showing each of the steps which need to be completed for this provider selection process.
Tab: 3. Decision making record
One of the key requirements of the PSR is good record keeping and evidencing of decisions. An example of a record keeping template is in this tab.
Throughout this guide requirements set out in the Regulations that relevant authorities must comply with are denoted by blue boxes. In some cases, how relevant authorities may choose to comply with the Regulations is also set out here but these are not part of the Regulations.
Throughout this guide recommendations by NHS England as set out in the statutory guidance are denoted by orange boxes.
Direct Award Process B Guide

## 2. Process Map
Circumstance description | 1. Planning phase |  |  |  | 2. Approval to proceed | 3. Award contract and communicate final decision
Direct award process B | Conflict of interest management established | Scope | Is this provider selection process appropriate? | Make a decision and keep records | Review information and seek approval | Award contract | Transparency - Confirmation of Award
direct award process B Where patients have a choice of providers and the number of providers is not restricted by the relevant authority. | Ensure conflicts of interests (CoI) are managed in line with Regulation 21 and with the RA's wider CoI policy. | Ensure that the service being arranged is in scope of the PSR i.e. that the services are health care services or can be procured under the PSR as a mixed procurement as set out in Regulation 3. | This process must be used when patients have a choice of providers and the number of providers is not restricted by the relevant authority. Questions to consider: • Do patients have a choice of providers that is not restricted by the relevant authority (i.e. no provider selection is taking place)? • Are there arrangements in place to enable providers to express an interest in providing the services? • Does the provider meet all requirements in relation to the provision of the health care services to patients? Direct award process B cannot be used: • to conclude a framework agreement or to award a contract based on a framework agreement • to establish a pool of providers where there is a limited number of providers available Relevant authorities must consider the exclusions in Regulation 20 and apply as appropriate. | Relevant authorities must make and keep clear records detailing their decision making process and rationale for direct award process B, as set out in the Regulations. An example of how to record evidence, and what information to record, is outlined in Tab 3 | Ensure that a recommendation to award a contract is approved internally through all of the relevant authority's governance processes. How this should be done is not set out in the Regulations. | Award contract to provider or group of providers. | The relevant authority must publish a confirmation of award on the Find a Tender Service (FTS) website within 30 days of the contract being awarded. The information that is required to be published is set out in Schedule 2 of the Regulations.
Direct Award Process B - PROCESS MAP

## 3.Decision Making Record
Direct award process B Record of decision making on: (insert date)
PART 1 - General
1. Confirmation that this contract award has been made following direct award process B:
2. Name of relevant authority:
3. Contract title and reference:
4. Name and address of the registered office or principal place of business of the provider to whom the contract has been awarded:
5. Description of the relevant health care services to which the contract relates, including the most relevant CPV code:
6. The lifetime value of the contract or, where it is not known, the amounts payable to the provider under the contract:
7. Contract start date:
8. Contract end date:
9. Is the contract for a new or existing service?
10. Is the contract with a new or an existing provider?
PART 2 - Specific Information
11. Provide rationale for why this provider has been awarded the contract for the service (in line with the requirements to award a contract using direct award process B):
12. For mixed procurements, how the procurement meets the requirements for mixed procurement:
13. Provide details of the individual/individuals who made the decision and the date it was made:
14. Provide details of anyone else who gave approval:
15. Any declared conflicts or potential conflicts of interest:
16. Information as to how any conflicts or potential conflicts of interest were managed:
17. Insert date when the contract was awarded:
EXAMPLE OF DECISION MAKING RECORD