## Sheet1
ICS Infrastructure Strategy Structure and Minimum Content
Region
ICS
Regional Delivery Director
Strategic Estates Lead
ICS Senior Responsible Officer
ICS Infrastructure Review Team
Review Date
Theme | Review Point | Evidence | Review Team Learning
Executive Summary | Summary findings from each section | High level concise summary of the strategy, highlighting real issues affecting the ICS/ICB.
| High level "System Roadmap" looking back on what has been achieved over the last few years and high level plans for the next 5 years | Graphical timeline For example, short (5 year) , medium (10 year) and long term with link to the Local Plans (15 - 20 years).
Introduction | Context to ICS. | Size of ICS, type of population, where is the greatest need, where has investment been targeted, local peculiarities, etc Look for Core 20 plus 5 - where investment targeted and why? Addressing health inequalities as a key component Population mapping and service availabilities. How have the ICS assessed / measured the greatest need?
| Outline the system partners and how the ICS works | Individual partner organisations are identified (acute, mental health, community, primary care, ambulance, Local Authority, third sector partners, private providers, voluntary sector). ICS wide representatives are identified (estates, finance, digital, workforce, clinical) One Public Estate Approach is needed Check if other parties as above have been involved in the creation or at least sighted on the strategy and will form part of the planning stage moving forward, as ICS's are about more than NHS estate. Tie into PCN strategies and Trust strategies.
| ICS governance | Evidence of all organisations working in partnership towards a robust infrastructure strategy. For example: ICS Capital Board ICS Estates Group ICS Sustainability Group SRO identified How often are meetings scheduled Includes a structure diagram
National Context | List national drivers such as NHS Long Term Plan, Fuller Stocktake Report, NHS Five Year Forward View – New Models of Care, Joint Forward Plan, NHS Five Year Forward View for General Practice, Naylor Report, Carter Report, One Public Estate, Net Zero Carbon, Sustainability agenda and NHS Estates and Facilities Workforce Action Plan. | What national drivers have the ICS referenced within their strategy? How will the ICS incorporate recommendations from national drivers within local plans?
ICS Priorities | Describes existing ICS priorities, transformation programmes and structure and the importance of estates and infrastructure as an enabler to delivery. | List of priorities and targets (SMART). How has the ICS demonstrated their priorities (what process have they used, criteria, weighting, etc)? May be in the appendix of the strategy Core, flex and tail is identified Local risks (for example RAAC hospitals)
| Future clinical strategy for the ICS is clearly described and details how infrastructure will support it and the required level of investment and resource needed. | List of priorities and targets.
Where are we now? | Describes what estate and infrastructure progress has already been made (e.g. new developments, estates efficiencies) | Table showing investment in the last 5 years (including STP wave funding, eradication of MH dorms, UEC, TIF, CDC, New Hospitals Programme etc) What benefits have been delivered by recent investment and is it measurable?
| Outline the opportunities and challenges with the existing estate and infrastructure across the system including age, backlog maintenance, Critical Infrastructure Risk, non-clinical space, utilisation, possible disposals and investment to date. | Description of key infrastructure issues that need to be tackled
| Captures data and analysis to demonstrate the status of the existing infrastructure | Quantum: Split by health type (Primary Care, Acute, Community & Mental Health) with system maps GIA of existing estate Age of estate Leased estate and expiry Primary Care – split of ownership, list of PCNs Comparison with similar ICS’s (where applicable)
Disposals Existing disposal opportunities (capital receipt, size, timeline, alternative use, etc)
Core, flex and tail - Core: Good quality, fit-for purpose and future proof estate that aligns with the lTP and the ICS's clinical strategy. - Flex: Estate that is of an acceptable quality, or provides unique access to services, but does not fully enable the ambitions of the LTP. - Tail: Poor quality estate that is not fit-for purpose or for patient-facing services and should be phased out when alternative estate is available.
PFI PFI and LIFT contract overview (primary and secondary) PFI and LIFT asset condition (should be condition B?) and compliance status, special situations and expiry PFI change control PFI and LIFT governance and assurance e.g. oversight, performance, finance
Cost Cost of estate (keep all financial information consistent eg to one decimal point £x.xm) Backlog Maintenance cost Critical Infrastructure Risk cost Incidents and impact (e.g. loss of income / cancelled procedures and appointments. + cost) Commercial structures and estates transactions overview e.g. Wholly owned subsidiaries, joint ventures (JVs), third party finance, multi organisation service provision
Utilisation Utilisation Non-clinical space Strategic asset developments - decant provision, peak demand capacity
Demographics Existing population and demographic Population growth Change in demographic
Planning Details of new housing developments (where are they?)
Business Local pressures and issues – ICS specific Significant business cases already in progress and their impact New Hospital Programme schemes
Workforce Current workforce profile and skills gap
Where do we want to be? | Clearly sets out the vision for the ICS estate and infrastructure. | Reviewer note: May be broken into global NHS, clinical and estates. Should include Core20 Plus 5. Virtual wards - all ICSs have submitted system plans for this which will impact on estate
| Describes the key estates and infrastructure priorities for the next five years and describes how this will achieve the ICS overall vision | Themes for the estate and a list of priorities and targets
| Specific objectives are listed. For example, reduce non-clinical space from X% to Y% by a specific date or timeline | List of objectives (make them SMART)
| Confirms how the ICS will incorporate stronger, safer and greener buildings to contribute towards the NHS vision of being net carbon zero by 2040. | Green Plan objectives and priorities are identified and are measurable (make them SMART) Reviewer note: Detail of how ICS delivers this may be included within "How do we get there" section rather than this section.
| Demonstrates how digital transformation and innovation will be used to deliver more and improved capacity out of built and other assets whilst achieving the aims of the Digital Clinical Safety Strategy. | List of key digital transformation initiatives and how it links into the ICS Strategy Confirms how infrastructure will support local digital strategy Reviewer note: Detail of how ICS delivers this may be included within "How do we get there" section rather than this section
| Demonstrates how workforce will be used to used to deliver more and improved capacity out of built and other assets whilst achieving the aims of the NHS Estates and Facilities Workforce Action Plan | Initiatives such as apprenticeship schemes, sharing of subject matter expert resources across ICS like Authorising Persons Confirms how infrastructure will support local workforce strategy Reviewer Note: Detail of how ICS delivers this may be included within "How do we get there" section rather than this section
| Commercial opportunities e.g. income, valued added, invest to save | List of commercial opportunities
| Acquisitions | List of proposed acquisitions
| Considers more efficient allocation and use of resources including local government collaboration to promote effective investment decisions | Description of opportunities to work across One Public Estate Reviewer note: Detail of how ICS delivers this may be included within "How do we get there" section rather than this section
How do we get there? | A set of estate and infrastructure deliverable projects is identified and workstreams are set up to deliver them | Details of a capital programme or investment programme SMART? Cost assessment? Savings and benefits by delivering the strategy? Prioritisation of projects and which have biggest spend and impact? What are the blockers to the delivery - physical/financial?
| The strategy shows how an ICS will achieve the priorities, which organisation is taking the lead and confirms the opportunities and challenges? | Description of how priorities will be delivered and who is responsible for leading. This should be prioritised by the ICS to align with service delivery into a capital list (tools to support prioritisation are available from the previous Estate Workbooks). Prioritisaton matrix (SMART)
| An update on ICS governance and capability is provided to describe how the ICS will deliver the Infrastructure Strategy, how it will support integrated working across estates teams to achieve the vision and how it will move to deliver strategic aims across the whole system, not just at an organisational level | Details of arrangements in place to implement and monitor the strategy
| Documents the risks the ICS would face if the existing and proposed workstreams did not go ahead including proposals to mitigate or manage the risks. | Table showing key risks and mitigating actions
| The strategy should be a living document. Confirm when it will be reviewed and / or updated | Date or timescale
| Have the ICS identified how they will fund their list of priorities | ICS identify potential funding sources
Feedback Overview Include examples of good practice that could be used elsewhere