## Project plan by Step
Project plan "How to improve care navigation in general practice"
Practice Name
Project Lead
[6 empty] | week commencing | 2024-01-06 |  |  |  |  | 2024-01-13 |  |  |  |  | 2024-01-20 |  |  |  |  | 2024-01-27 |  |  |  |  | 2024-02-03 |  |  |  |  | 2024-02-10 |  |  |  |  | 2024-02-17 |  |  |  |  | 2024-02-24 |  |  |  |  | 2024-03-03 |  |  |  |  | 2024-03-10 |  |  |  |  | 2024-03-17 |  |  |  |  | 2024-03-24 |  |  |  |  | 2024-03-31 |  |  |  |  | 2024-04-07
| Task | Assigned to | Progress | Start | End |  | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Understand |  | 100%
1.1 | Review Assessment Tool for Modern General Practice findings |  | 100% | bar: 2024-01-06 6 M
1.2 | Map your existing processes |  | 35% | bar: 2024-01-06 7 T to 2024-01-06 9 T
1.3 | Understand current staff experiences and perspectives | bar: 2024-01-06 7 T to 2024-01-06 10 F
1.4 | Understand current patient experiences and perspective | bar: 2024-01-13 13 M to 2024-01-13 16 T
1.5 | Measure demand and capacity |  | 50% | bar: 2024-01-06 6 M to 2024-01-20 24 F
1.5.1 | Measure total contact demand and capacity for your care navigators |  | 60% | bar: 2024-01-06 6 M to 2024-01-13 17 F
1.5.2 | Measure total appointment demand and capacity for health professionals | bar: 2024-01-13 13 M to 2024-01-20 24 F
1.6 | Audit your avoidable appointments |  | 40% | bar: 2024-01-06 7 T to 2024-01-20 20 M
1.7 | Review what you have learned | bar: 2024-01-27 27 M to 2024-01-27 31 F
2 | Plan |  | 100%
2.1 | Involve both admin and clinical staff to create commitment and a sense of ownership. |  | 30% | bar: 2024-01-06 7 T to 2024-02-24 24 M
2.2 | Involve patients in planning your new process; get patients’ perspectives on your proposals. | bar: 2024-02-17 18 T to 2024-02-24 24 M
2.3 | Map a proposed new care navigation process. | bar: 2024-02-03 4 T to 2024-02-03 6 T
2.4 | Consider what you need from an online consultation tool, phone system and messaging & booking tools. | bar: 2024-02-03 6 T to 2024-02-03 7 F
2.5 | Create a consistent patient experience of care navigation. | bar: 2024-02-03 4 T to 2024-02-03 6 T
2.6 | Review how you capture information from patients. | bar: 2024-02-03 3 M to 2024-02-03 7 F
2.7 | Make a decision about how to allocate patients to the right professional or service to meet their need. | bar: 2024-02-03 3 M to 2024-02-03 7 F
2.8 | Weigh up the need for continuity of care against urgency. | bar: 2024-02-03 5 W to 2024-02-03 7 F
2.9 | Complete a skills matrix for the staff in your practices. |  | 45% | bar: 2024-01-06 7 T to 2024-01-20 20 M
2.1 | Understand what external services are available to your patients. | bar: 2024-01-13 14 T to 2024-01-20 24 F
2.11 | Check your proposed new process is safe for patients and staff. | bar: 2024-02-10 10 M to 2024-02-17 21 F
2.12 | Decide how you will evaluate your success. | bar: 2024-02-10 10 M to 2024-02-10 14 F
3 | Prepare |  | 100%
3.1 | Decide whether you are looking at a small steps or big bang approach. | bar: 2024-02-24 25 T
3.2 | Create and test a single route through which all requests flow, irrespective of their entry point | bar: 2024-02-24 26 W to 2024-02-24 28 F
3.3 | Ensure you have the workforce you need. Refine your internal directory | bar: 2024-02-24 26 W to 2024-02-24 28 F
3.4 | Engage with the external services. Refine your external directory | bar: 2024-02-24 26 W to 2024-02-24 28 F
3.5 | Amend your proposed new process after your testing and document it | bar: 2024-03-03 3 M to 2024-03-03 5 W
3.6 | Align your appointment book to reflect your new process. | bar: 2024-03-03 6 T to 2024-03-10 14 F
3.7 | Train all staff in ‘how things will be done’. | bar: 2024-03-03 6 T to 2024-03-10 14 F
3.8 | Build staff communication skills | bar: 2024-03-03 6 T to 2024-03-10 14 F
3.9 | Inform patients of the proposed changes, what they can expect and how they can be involved. | bar: 2024-03-10 13 T to 2024-03-24 25 T
4 | Implement |  | 100%
4.1 | Last minute checks before you start | bar: 2024-03-17 21 F to 2024-03-24 25 T
4.2 | Go live | bar: 2024-03-24 26 W
4.3 | Monitoring your progress and managing any issues | bar: 2024-03-24 26 W to 2024-04-07 7 M
4.4 | Staff support | bar: 2024-03-17 21 F to 2024-04-07 7 M
4.5 | Patient support | bar: 2024-03-24 26 W to 2024-04-07 7 M
5 | Sustain |  | 100%
5.1 | Regular checks to ensure you are maintaining your improvement and not slipping back into old habits. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.2 | Review your processes periodically to make sure they are still working and are safe. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.3 | Staff development to keep them involved and engaged. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.4 | Ongoing patient engagement; they are your greatest untapped resource. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.5 | Horizon scanning to prepare for changes in the general practice environment. Consider how you might need to adapt. | bar: 2024-03-31 2 W to 2024-04-07 10 T

## Project plan by Activity
Project plan "How to improve care navigation in general practice"
Practice Name
Project Lead
[6 empty] | week commencing | 2024-01-06 |  |  |  |  | 2024-01-13 |  |  |  |  | 2024-01-20 |  |  |  |  | 2024-01-27 |  |  |  |  | 2024-02-03 |  |  |  |  | 2024-02-10 |  |  |  |  | 2024-02-17 |  |  |  |  | 2024-02-24 |  |  |  |  | 2024-03-03 |  |  |  |  | 2024-03-10 |  |  |  |  | 2024-03-17 |  |  |  |  | 2024-03-24 |  |  |  |  | 2024-03-31 |  |  |  |  | 2024-04-07
| Task | Assigned to | Progress | Start | End |  | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Understanding where to start |  | 100%
1.1 | Review Modern General Practice Self-Assessment Tool findings |  | 90% | bar: 2024-01-06 6 M
1.2 | Measure demand and capacity | bar: 2024-01-06 6 M to 2024-01-20 24 F
1.2.1 | Measure total contact demand and capacity for your care navigators | bar: 2024-01-06 6 M to 2024-01-13 17 F
1.2.2 | Measure total appointment demand and capacity for health professionals | bar: 2024-01-13 13 M to 2024-01-20 24 F
1.3 | Audit your avoidable appointments | bar: 2024-01-06 7 T to 2024-01-20 20 M
2 | Involving Staff |  | 100%
2.1 | Understand current staff experiences and perspectives | bar: 2024-01-06 7 T to 2024-01-06 10 F
2.2 | Involve both admin and clinical staff to create commitment and a sense of ownership. |  | 30% | bar: 2024-01-06 7 T to 2024-02-24 24 M
2.3 | Train all staff in ‘how things will be done’. | bar: 2024-03-03 6 T to 2024-03-10 14 F
2.4 | Build staff communication skills | bar: 2024-03-03 6 T to 2024-03-10 14 F
2.5 | Staff support when you go live | bar: 2024-03-17 21 F to 2024-04-07 7 M
2.6 | Staff development to keep them involved and engaged. | bar: 2024-03-31 2 W to 2024-04-07 10 T
3 | Creating a new process |  | 100%
3.1 | Map your existing processes |  | 35% | bar: 2024-01-06 7 T to 2024-01-06 9 T
3.2 | Map a proposed new care navigation process. | bar: 2024-02-03 4 T to 2024-02-03 6 T
3.3 | Create a consistent patient experience of care navigation. | bar: 2024-02-03 4 T to 2024-02-03 6 T
3.4 | Weigh up the need for continuity of care against urgency. | bar: 2024-02-03 5 W to 2024-02-03 6 T
3.5 | Make a decision about how to allocate patients to the right professional or service to meet their need. | bar: 2024-02-03 3 M to 2024-02-03 7 F
3.6 | Check your proposed new process is safe for patients and staff. | bar: 2024-02-10 10 M to 2024-02-17 21 F
3.7 | Create and test a single route through which all requests flow, irrespective of their entry point | bar: 2024-02-24 26 W to 2024-02-24 28 F
3.8 | Amend your proposed new process after your testing and document it | bar: 2024-03-03 3 M to 2024-03-03 5 W
3.9 | Decide whether you are looking at a small steps or big bang approach. | bar: 2024-02-24 25 T
3.1 | Last minute checks before you start | bar: 2024-03-17 21 F to 2024-03-24 25 T
3.11 | Go live | bar: 2024-03-24 26 W
4 | Supporting resources |  | 100%
4.1 | Consider what you need from an online consultation tool and phone system. | bar: 2024-02-03 6 T to 2024-02-03 7 F
4.2 | Review how you capture information from patients. | bar: 2024-02-03 3 M to 2024-02-03 7 F
4.3 | Complete a skills matrix for the staff in your practices. |  | 45% | bar: 2024-01-06 7 T to 2024-01-20 20 M
4.4 | Understand what external services are available to your patients. | bar: 2024-01-13 14 T to 2024-01-20 24 F
4.5 | Engage with the external services. Refine your external directory | bar: 2024-02-24 26 W to 2024-02-24 28 F
5 | Evaluating your process |  | 100%
5.1 | Review what you have learned | bar: 2024-01-27 27 M to 2024-01-27 31 F
5.2 | How can you measure your success? | bar: 2024-02-10 10 M to 2024-02-10 14 F
5.3 | Monitoring your progress and managing any issues | bar: 2024-03-24 26 W to 2024-04-07 7 M
5.4 | Regular checks to ensure you are maintaining your improvement and not slipping back into old habits. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.5 | Review your processes periodically to make sure they are still working and are safe. | bar: 2024-03-31 2 W to 2024-04-07 10 T
5.6 | Horizon scanning to prepare for changes in the general practice environment. Consider how you might need to adapt. | bar: 2024-03-31 2 W to 2024-04-07 10 T
6 | Optimising your workforce |  | 100%
6.1 | Ensure you have the workforce you need. Refine your internal directory | bar: 2024-02-24 26 W to 2024-02-24 28 F
6.2 | Align your appointment book to reflect your new process. | bar: 2024-03-03 6 T to 2024-03-10 14 F
7 | Involving patients |  | 100%
7.1 | Understand current patient experiences and perspective | bar: 2024-01-13 13 M to 2024-01-13 16 T
7.2 | Involve patients in planning your new process; get patients’ perspectives on your proposals. | bar: 2024-02-17 18 T to 2024-02-24 24 M
7.3 | Inform patients of the proposed changes, what they can expect and how they can be involved. | bar: 2024-03-10 13 T to 2024-03-24 25 T
7.4 | Patient support when you go live | bar: 2024-03-24 26 W to 2024-04-07 7 M
7.5 | Ongoing patient engagement; they are your greatest untapped resource. | bar: 2024-03-31 2 W to 2024-04-07 10 T