## Slide 1: NHS England Operational Risk Register Annex 2
NHS England Board
4 June 2026

## Slide 2: NHS England Operational Risk Register
 | ORR Summary | Risk Appetite | Inherent Score | Current Score | Target Score & Date | Move in Score | Risk Owner
 | 18360: Capacity of adult secure inpatient services There is an ongoing capacity risk relating to the bed base in adult secure (staffed, not commissioned) in relation to Adult Secure inpatient services having an impact upon NHSE’s objectives to provide care in the least restrictive environments, reducing the length of stay, improving outcome and experience for patients and carers, admissions from prison within 28 days of referral. This risk score has risen from 16 to 25, primarily following the February 2026 decision by the NHS Executive to direct the movement of all patients from the St Andrew’s Healthcare (StAH) Northampton site as result of continuing patient safety concerns Key controls and mitigations (in response to the rising risk): National EPRR response established for the StAH Northampton incident, providing coordinated system oversight. Patient Placement and Commissioner Response Group in place, with detailed patient cohort mapping, capacity mapping and placement oversight. Clinical Reference Group established, including development of an ethical framework to support complex decision‑making and differing clinical opinions. Enhanced quality improvement and oversight arrangements for affected services. Dedicated finance and contract subgroup managing financial, contractual and commercial impacts. Ongoing collaboration between Specialised Commissioning, Health & Justice, DHSC and MoJ on risk management, operational oversight and system solutions. Continued development of improved capacity monitoring, transfer and remission frameworks, patient flow solutions and alternatives to admission. | Medium | 25 (L5xI5) | 25 (L5xI5) | 9 (L3xI3) 30/09/26 | 2025/26Q2 NEW Q3 ▶ Q4 ► 2026/27 Q1 ▲ | DG, System Development
 | 13180: Cyber secure and resilient NHS England fails to deliver proportionately cyber secure and resilient services resulting in compromised data, unavailability and lost productivity, leading to patient harm and poor outcomes. Key controls and mitigations Controls include secure architecture, change management, cryptography, identity and access controls, and operational resilience measures like CSOC monitoring and backups. Additional safeguards cover vulnerability management, secure configuration, and supplier security. Mitigations focus on asset inventory, integrated assurance frameworks, legacy technology removal, insider threat monitoring and proactive vulnerability management. Actions continue to progress centralised logging and threat modelling, alongside implementation of an enhanced integrated cyber assurance framework to improve compliance, streamline assurance activity and address identified control gaps, including a live pilot relating to vulnerability management. Technical implementation of a centralised asset inventory is advancing to ensure comprehensive visibility and protection of organisational assets. Activity to strengthen supply chain resilience has further matured, with supplier security assurance now embedded as business‑as‑usual and supporting a more systematic and scalable approach to managing third‑party cyber risk. | Low/ Medium | 25 (L5xI5) | 25 (L5xI5) | 16 (L4XI4) 31/03/27 | 2025/26 Q1 ▲ Q2 ▶ Q3 ▶ Q4 ► 2026/27 Q1 ► | DG Technology, Digital and Data
 | 8736: IT system support for the management of performance concerns in professional standards There is a significant operational risk due to delays in the rebuild and re-procurement of two national IT systems: Revalidation Management System and Athena. These systems are essential for continued delivery of the Performers List Regulations, Responsible Officer Regulations, and NHS England policy, and these systems should support efficient case management and reporting. The current platforms are outdated and increasingly unstable, impacting the ability of regional teams to efficiently manage performance concerns, and requiring intensive support from the National Professional Standards Team just to maintain basic functionality. The delay in progressing redevelopment is compounding the pressure, creating a fragile operating environment and increasing the risk of service disruption. Key controls and mitigations: reprioritisation of resources is taking place, though maintaining all systems and supporting rebuilds remains unsustainable. It has been agreed that no re-platforming of Athena should take place until the future target operating model is clear. The scoping exercise is underway and is expected to complete by end of June 2026, and proposals on more stable and sustainable solutions are in development and expected to be considered by the NHSE Executive in July 2026. The deadline for the delivery of the reporting functionality is currently estimated to be December 2026. It is already understood however that this piece of work will only be able to provide very limited reporting. Capacity and risk concerns are being escalated through governance channels. | Medium | 25 (L5xI5) | 25 (L5xI5) | 20 (L4xI5) 31/03/27 | 2025/26Q3 NEW Q4 ► 2026/27 Q1 ► | National Medical Director
Inherent score is the score assigned to a risk before any controls are in place or if the controls fail in their entirety. This is unlikely to change after the original assessment. The inherent score should be higher than or equal to the current score.
Current score is the level of risk that remains aft. er all existing controls have been applied. This will vary over time and should be reassessed each time the risk is reviewed to make sure it accurately reflects the current position.
Target score is the level that future mitigation should aim to achieve, or better. This may vary over time and should be reassessed each time the risk is reviewed to make sure it is achievable in the timeframe. The target score should be lower than or equal to the current score.

## Slide 3: NHS England Operational Risk Register
 | ORR Summary | Risk Appetite | Inherent Score | Current Score | Target Score & Date | Move in Score | Risk Owner
 | 16936: Digital workforce retention and recruitment In the event of being unable to recruit and retain a skilled digital and data workforce of appropriate capacity and capability there is a risk of failing to achieve the 1.2% annual productivity improvements and other health and clinical benefits planned in the Spending Review PBC commitments. Key controls and mitigations. Controls include secure architecture, change management, cryptography, identity and access controls, and operational resilience measures such as CSOC monitoring, incident response and data backups. Additional safeguards cover vulnerability and patch management, secure configuration, and strengthened third‑party and supplier security management. Mitigations focus on asset inventory, integrated assurance frameworks, legacy technology removal, insider threat monitoring and proactive vulnerability management. Actions continue to progress centralised logging and threat modelling, alongside implementation of an enhanced integrated cyber assurance framework to improve compliance, streamline assurance activity and address identified control gaps, including a live pilot relating to vulnerability management. Technical implementation of a centralised asset inventory is advancing to ensure comprehensive visibility and protection of organisational assets. Activity to strengthen supply chain resilience has further matured, with supplier security assurance now embedded as business‑as‑usual and supporting a more systematic and scalable approach to managing third‑party cyber risk. | Low/ Medium | 25 (L5xI5) | 25 (L5xI5) | 12 (L3XI4) 30/06/26 | 2025/26Q1 ► Q2 ▶ Q3 ▶ Q4 ► 2026/27Q1 ► | DG Technology, Digital and Data
 | NEW: Loss of workforce talent and critical capability during pre‑integration with DHSC There is a risk that NHS England loses talented colleagues and critical capability during the period of pre‑integration with DHSC, resulting in reduced organisational capacity and capability to deliver statutory duties and key priorities during 2026/27 and to support safe and effective transition into the future DHSC operating model. Key controls and mitigations: Active re‑profiling of priority delivery areas within Directorates and Regions to protect critical roles and capability. Established mechanisms to enable timely appointment to business‑critical posts. Implementation of the Improving NHSE Together programme to address key drivers of engagement and retention informed by colleague insight and staff survey feedback. Enhanced performance, development and support arrangements through revised appraisal and continuous performance conversation frameworks. Strengthened Learning and Development offer, including expanded provision, strategic partnerships, and increased access to coaching and mentoring. Leadership Support Circles providing structured peer support and leadership development during the transition period. Planned talent and succession planning with senior leaders to identify high‑potential colleagues, single points of failure and flight risk, alongside targeted retention and development actions. Ongoing alignment with DHSC talent and performance approaches, including participation in cross‑government leadership development schemes. | Low | 25 (L5xI5) | 20 (L4xI5) | 12 (L3xI4) 31/03/27 | 2026/27Q1 NEW | COO
 | 19817 There is a risk that historical non-compliance with IR35 regulations in the use of contingent labour may result in a significant financial penalty from HMRC Due to historical non-compliance with IR35 regulations in the use of contingent labour within Health Education England, NHS England may face a significant financial penalty from HMRC. This risk affects a number of role groups, many of whom worked on a sessional basis, making compliance tracking challenging. The final liability may be reduced following a detailed assessment and HMRC’s review. Penalties could be suspended if NHSE demonstrates improved processes and controls, but this is not yet confirmed. Key controls and mitigations: Since Q3 24/25 an NHSE HR Contingent Labour Working Group has been established to review compliance with IR35 regulations since 2017 (pre-HEE merger with NHSE). A detailed IR35 programme position update is now regularly provided to ARAC on this risk. There has been progression made and confidence in discussions with HMRC. Active discussion and negotiation will be ongoing with HMRC over 3 to 6 months to confirm financial liability. As a result the impact scoring of this risk has been reduced to ‘4’ and the target for closure of the risk extended to September 2026. | Medium | 25 (L5xI5) | 20 (L5xI4) | 15 (L3xI5) 30/09/26 | 2025/26Q2: NEW Q3 ► Q4 ► 2026/27Q1 ▼ | Director General, People

## Slide 4: NHS England Operational Risk Register
 | ORR Summary | Risk Appetite | Inherent Score | Current Score | Target Score & Date | Move in Score | Risk Owner
 | 15077: Significant operational disruption to critical digital live services In the event of a significant operational disruption to critical live services there is a risk of negatively impacting patient care, causing patient harm and impacting the operational running of the health and care system. Key controls and mitigations: Preventative controls include regular resilience and failover testing of systems, alongside prioritisation of key recruitment to support live services and resilience. Detective controls include early outage identification and 24/7 proactive monitoring and alerting through the IT Operations Centre, supported by central Cyber Security Operations Centre capabilities. Resilience testing schedules are in place across different service tiers, including formal ITSCM assurance with defined testing cycles. Mitigating actions are supported by established major incident and business continuity arrangements, including post‑incident review processes to identify corrective actions and strengthen recovery capability. Some targeted recruitment activity is underway to address resourcing pressures, although workforce capacity constraints remain a risk to delivery pace. Options continue to be explored for automated monitoring of supplier access and security controls, including testing approaches within PDS before potential wider rollout. An application rationalisation plan remains in development to reduce complexity and cyber risk across the digital estate, with benefits expected over the medium term. Recent red‑team activity simulating a supplier‑led attack has identified further gaps in protective controls, informing ongoing improvement actions. | Low/ Medium | 25 (L5xI5) | 20 (L4xI5) | 15 (L3xI5) 31/12/26 | 2025/26Q1 ► Q2 ► Q3 ▼ Q4 ► 2026/27Q1 ► | DG Technology, Digital and Data
 | 14710: Location, Function, Condition and Age of the NHS Estate provides significant risk to workforce and productivity 45% of estates infrastructure (including RAAC) is not fit for the services the NHS delivers today and hold significant risk, through failing services and poor technical oversight and assurance. This results in disruption to productive clinical services and can lead to significant risks to patient and staff safety. We are also witness an increase in PFI failure through financial distress and Failure of Project Co.s. Key controls and mitigations The Premises Assurance Model and the Estates Return Information Collection data collection are used to monitor estates risks. National programmes are in place to manage RAAC risks and ensure structural assessments. Technical standards and guidance are being developed, with finance reviewing funding for technical assurance team - approved in part and team mobilised. 34 NHS sites now have RAAC, 29 have been eradicated. Business case approval has commenced for 26/27 to 29/30, deep dives and associated site visits ongoing for large and high-risk schemes alongside capital and cash colleagues. Supplier resilience and PFI risks are being managed with limited resources. Long-term infrastructure strategies are being developed with finance and strategy teams. Digital platforms business case is now awaiting final sign off. Pay review outcome was not approved for 26/27. A new SR will need to be submitted for 27/28. | Low | 25 (L5xI5) | 20 (L4xI5) | 16 (L4xI4) 31/03/27 | 2025/26Q1 ► Q2 ▶ Q3 ▶ Q4 ► 2026/27 Q1 ► | DG Finance
 | 13263: Demand and capacity in primary care and community services There is a risk that demand exceeds capacity across primary and community health services. Key controls and mitigations: Controls: Sustained and increased demand for services from patients. Constrained capacity in primary and community services, including workforce and estates. Mitigations: The Medium-Term Planning Framework (MTPF) introduces an 18-week ICB-level target for CHS waits from 2026/27, with targets of 78% by March 2027 and 80% by March 2029. The MTPF asks ICBs to develop a plan to eliminate >52 weeks waiting times in 26/27. National assurance processes will monitor attainment against agreed ICB plans for 18-week performance, which will inform targeted improvement support offers.. PCN test sites being used to test future resource requirements, programme delivery on track and expected to run for another full year. Summary outputs to be developed for sharing more widely once Nuffield Trust have completed their work. | Low/ Medium | 20 (L5xI4) | 20 (L5xI4) | 9 (L3xI3) 31/03/27 | 2025/26Q1 ► Q2 ► Q3 ▶ Q4 ► 2026/27Q1 ► | National Director for Primary Care and Community Services

## Slide 5: NHS England Operational Risk Register
 | ORR Summary | Risk Appetite | Inherent Score | Current Score | Target Score & Date | Move in Score | Risk Owner
 | NEW 22338: TDD Transformation Risk There is a risk that Technology, Digital and Data is unable to deliver live services, meet statutory obligations and planned business objectives (including 10 YHP commitments), as a consequence of the DHSC_NHSE Transformation Programme. Key controls and mitigations focus on maintaining service continuity and managing the impact of workforce and structural change. This includes coordinated management of Voluntary Redundancy and merger processes, with phased exits and appropriate handover arrangements in place, supported by updated business continuity and EPRR plans. Programmes and business‑as‑usual activity are being actively reprioritised to align with reduced capacity and emerging organisational priorities, while collaborative work is underway to shape the future DHSC operating model and workforce structure. Further mitigations include use of retention measures where appropriate, restrictions on VR eligibility for critical roles, and ongoing system‑wide planning with ICBs and providers to ensure future TDD workforce capacity and capability requirements are reflected in 2026/27 and subsequent planning cycles. | Medium | 25 (L5xI5) | 20 (L4xI5) | 16 (L4xI4) 03/07/26 | 2026/27 Q1: NEW | DG, Technology, Digital & Data
 | NEW 22341: New and Updated Software and AI medical devices going live from Spring 2027 There is a risk that NHSE cannot place new and updated software and AI medical devices in clinical use in a lawful manner from Spring 2027 resulting in an Innovation Freeze within the organisation which will impact on our delivery of 10Y plan commitments, such as Intelligent triage on the NHS App. Key controls and mitigations focus on establishing compliance with the new regulatory framework and ensuring organisational readiness for certification. This includes development and implementation of a Quality Management System aligned to ISO 13485 requirements, with NHS England clinical safety, regulatory and programme teams preparing for external certification and up‑classification of legacy products. Internal audits are underway, with non‑conformities identified and subject to root cause analysis and remediation, alongside a programme of further audit activity through 2026/27. Preparatory work is also in place to assess products against new classification requirements and support transition to external notified body approval where required. These measures are intended to enable continued lawful deployment of digital and AI‑enabled clinical products, while mitigating risks to service availability, delivery of strategic commitments and organisational compliance. | Medium | 25 (L5xI5) | 20 (L4xI5) | 16 (L4xI4) 30/09/26 | 2026/27 Q1: NEW | DG, Technology, Digital & Data
 | T20: Morale decline There is a risk of reducing levels of staff morale and engagement during the period of integration with DHSC Key controls and mitigations: include i) use of existing wellbeing support offers such as EAP and OH, which are being reviewed, may provide adequate and appropriate support to colleagues, ii) enhanced support and wellbeing offers to aid staff through change, focusing on stress management, wellbeing, career development and possibly a CBT pilot and iii) continued check points on staff experience i.e. staff survey, union engagement, FTSU check ins, MHFA feedback. All BAU. Comms and engagement controls and mitigations include i) existing and planned communications, maintaining a sensitively optimistic and emotionally informed tone and ii) developing engagement mechanisms including a staff involvement network and 'roadshow' of conversations in different teams. In terms of organisational design, teams across both organisations are to be put at heart of organisation design approach. | Medium | 25 (L5xI5) | 20 (L4xI5) | 12 (L3xI4) 31/03/26 | 2025/26Q2 NEW Q3 ▶ Q4 ► 2026/27 Q1 ▶ | COO
 | Escalated: 11941: Insufficient capacity or capability to prepare for, or respond to, a new and emerging pandemic. There is a risk that there is insufficient capacity or capability for NHS England, or the NHS in England, to prepare for, or respond to, a new and emerging pandemic similar to, or in excess of, the scale of COVID-19. Key Controls and Mitigations: A comprehensive suite of national pandemic plans, governance arrangements and experienced EPRR structures is already in place, underpinned by updated NHS England operating frameworks and strong joint working with DHSC and UKHSA. Learning from Covid‑19 and Exercise Pegasus is being actively implemented, with agreed approaches in place to respond to emerging Inquiry recommendations and to adapt and scale care, including respiratory and critical care surge. Operational resilience is being strengthened through assured critical care, PPE and medical devices stockpiling and deployment arrangements, alongside clear incident management and national and regional coordination structures. These measures are further reinforced by Executive and Board ownership of preparedness, continued multi‑agency collaboration, and implementation of the Government’s Pandemic Preparedness Strategy to maintain and enhance national readiness. | Low/ Medium | 20 (L5xI4) | 16 (L4xI4) | 8 (L2xI4) 31/03/27 | 2026/27 Q1 escalated | COO

## Slide 6: NHS England Operational Risk Register
 | ORR Summary | Risk Appetite | Inherent Score | Current Score | Target Score & Date | Move in Score | Risk Owner
 | 10520: Slow recovery so that the weakest trusts and systems continue with poor performance and finances for many years, providing poor quality healthcare and incurring very large deficits Challenged trusts and systems may take too long to recover, leading to negative impacts on patients, large deficits and NHS brand damage Key controls and mitigations Quarterly reviews and Improvement Directors are used to track progress. Reports are submitted to Regional Support Groups and the Quality & Performance Committee. Exit criteria and metrics are in place to ensure focus. National executives oversee progress through deep dive review meetings. A reporting dashboard and deep dives have been implemented. The National Provider Improvement Programme (NPIP) has now launched, with a standard approach for NPIP developed and formalised in a development manual. Diagnostics now underway for initial cohort of NPIP providers. The budget to support this work has been agreed for the current year.. | Low | 20 (L5xI4) | 16 (L4xI4) | 12 (L3xI4) 31/03/27 | 2025/26Q1 ► Q2 ▶ Q3 ▶ Q4 ► 2026/26 Q1 ► | COO
 | 13275: Urgent and Emergency Care (UEC) capacity If there is failure to create additional UEC capacity to meet demand, there would be an adverse impact on patient outcomes (and system working) Key controls and mitigations There remains a risk of high demand exceeding capacity in place therefore potential increased impact on patient waiting times and experience and performance targets. A new methodology has been developed to identify tiered Trusts linked to NOF, overall performance for 4 hours, 4 hours against plan, 12 hours and ambulance handovers. Moderation undertaken with Regions to define final list of Tiered Trusts. A reset of the UEC delivery framework has been instigated outlining the key deliverables that will support achievement of 4 and 12-hour targets including delivery of a ‘Model ED’ which seeks to drive better performance against UEC Plan headline ambitions. | Low | 25 (L5xI5) | 16 (L4xI4) | 12 (L4xI3) 31/03/27 | 2025/26Q1 ► Q2 ▶ Q3 ▶ Q4 ► 2026/27Q1 ► | COO
 | 15678: Non compliance with statutory duties There is a risk that capacity in compliance, audit or legal functions is reduced through integration with DHSC, resulting in reduced oversight and compliance with statutory duties. This could result in financial loss, formal sanctions, and loss of trust. Key controls and mitigations A Scheme of Delegation outlines statutory duties and responsible individuals or committees. Accountability letters were sent to new DGs, including responsibility for statutory duties currently in the SoD. This clarifies accountabilities from 3 November 2025. Duties are mapped against assurance that they are being delivered in an organisational framework, statutory functions are now mapped to internal audits to identify any functions having not been covered by audits or other assurance reviews – a second tranche of reviews was presented to ECG in October. This has increased in score from 12 to 16 as a result of stopping work on the assurance of statutory duties in light of departures from the responsible team. This risk will remain until NHSE is abolished, however to support existing controls and mitigations number of statutory duty areas will be addressed by internal audits in the 26/27 audit plan.. | Medium | 20 (L5xI4) | 16 (L4xI4) | 9 (L3-I3) 31/03/27 | 2025/26Q1 ► Q2 ▼ Q3 ► Q4 ► 2026/27 Q1 ▲ | COO
 | 18184: Medicines supply issues Number of high-impact medicines supply issues impacting on patient outcomes, clinical services or prescribing cost. Key controls and mitigations The collective focus across DHSC & NHSE is on the ongoing middle east situation. There is currently minimal impact but we expect to see a further impact across shipping and logistics (port constraints, fuel costs impacting commercial outcomes) A task force to oversee the situation has been established. stood up. More routinely, Supplier issues are triaged through established controls. Collaboration with DHSC and suppliers aims to improve supply chain resilience and dormant licence programme now activated. Longer-term, value-based procurement will incentivise suppliers to prioritise reliability. Additional measures include buffer stock compliance, monitoring delivery pipelines, and conducting root cause analysis to prevent recurrence of issues. | Medium | 16 (L4xI4) | 16 (L4xI4) | 9 (L3xI3) 01/10/26 | 2025/26Q1 ► Q2 ▶ Q3 ► Q4 ► 2026/27 Q1 ► | DG Commercial & Growth